## Sheet1
Monitor Field Indicator | Work center | Earliest start date | Earliest start time | Latest Allowed Finish Date | Order Type | Priority | ABC indicator | Earliest finish date | Earliest finish time | Priority text | Order | Activity | Order Description | Object Description | Number | Notes 2 | Unloading Point | Notes 1 | Remaining Work | Work | Actual work | Order User Status | Op User Status | Order System Status | Functional Location | Description of functional location | Revision | Earliest Allowed Start Date
| MTN-ELEC | 2021-11-19 | 15:00 | 2019-12-05 | WDF | 4 |  | 2021-11-20 | 15:00 | 4.Within 2 Months | 2100022553 | 0040 | Order+install new dishwasher+Gorm | Install new cable for dishwasher | 1 | 6 | SR | Keep in plan | 3 | 3 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2019-10-26
| MTN-ELEC | 2021-11-20 | 15:00 | 2019-12-05 | WDF | 4 |  | 2021-11-21 | 15:00 | 4.Within 2 Months | 2100022553 | 0050 | Order+install new dishwasher+Gorm | Install water to diswasher | 1 | 6 | SR | Keep in plan | 3 | 3 | 0 | APPR SMAT RDBL | INIT OPND | REL PRT PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2019-10-26
| MTN-ELEC | 2021-11-10 | 7:00 | 2021-06-20 | WDF | 8 | S | 2021-11-10 | 15:00 | 8.Longer than 1 Year | 2100022813 | 0010 | CMAT:Replace Lamp for level glass | Isolate power to level glass | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /28/GC-LG-0905 | CLOSED DRAINS VESSEL | NOSD | 2019-07-01
| MTN-ELEC | 2021-11-10 | 15:00 | 2021-06-20 | WDF | 8 | S | 2021-11-11 | 11:00 | 8.Longer than 1 Year | 2100022813 | 0020 | CMAT:Replace Lamp for level glass | Replace lamp for LG | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /28/GC-LG-0905 | CLOSED DRAINS VESSEL | NOSD | 2019-07-01
| MTN-ELEC | 2021-11-11 | 11:00 | 2021-06-20 | WDF | 8 | S | 2021-11-11 | 19:00 | 8.Longer than 1 Year | 2100022813 | 0030 | CMAT:Replace Lamp for level glass | De-isolate and test | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /28/GC-LG-0905 | CLOSED DRAINS VESSEL | NOSD | 2019-07-01
| MTN-ELEC | 2021-11-10 | 7:00 | 2020-02-12 | WDF | 4 | V | 2021-11-11 | 19:00 | 4.Within 2 Months | 2100023282 | 0010 | (GC-SWB-6KV) relay back to org. design | Perform a BRUSH FV12 test of relays | 1 | 6 |  | Lars F. Madsen | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61/GC-SWB-6KV | 6KV SWITCHBOARD | NOSD | 2019-11-14
| MTN-ELEC | 2021-11-12 | 11:00 | 2020-02-12 | WDF | 4 | V | 2021-11-14 | 19:00 | 4.Within 2 Months | 2100023282 | 0030 | (GC-SWB-6KV) relay back to org. design | Install relays | 1 | 6 |  | Lars F. Madsen | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61/GC-SWB-6KV | 6KV SWITCHBOARD | NOSD | 2019-11-14
| MTN-ELEC | 2021-11-08 | 7:00 | 2019-11-24 | WDF | 3 | V | 2021-11-08 | 19:00 | 3.Intermedt 1 Month | 2100023287 | 0010 | Borrow backpart to GOFA-N-1840-k1 | Borrow backpart to GOFA-N-1840-k1 | 1 | 4 |  | PR Step | 3 | 20 | 17 | APPR WMAT SCH RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /F /61/GOFA-N-1802-03-J1 | MOTOR STAR.F.CRUDE OIL EX. PUMP PM-3601 | NOSD | 2019-11-04
| MTN-ELEC | 2021-11-10 | 7:00 | 2018-03-20 | WDF | 5 | I | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100023535 | 0010 | SMAT:Defect contact i LCP panel | Prep. permit, spareparts, tools, Toolbox | 1 | 6 | Need new mat |  | 2 | 2 | 0 | APPR SCH RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /50/GC-P-403A | COOLING WATER PUMP | NOSD | 2017-12-20
| MTN-ELEC | 2021-11-10 | 17:00 | 2018-03-20 | WDF | 5 | I | 2021-11-14 | 9:00 | 5.Within 4 Months | 2100023535 | 0030 | SMAT:Defect contact i LCP panel | Replace LCP panel | 1 | 6 | Need new mat |  | 10 | 10 | 0 | APPR SCH RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /50/GC-P-403A | COOLING WATER PUMP | NOSD | 2017-12-20
| MTN-ELEC | 2021-11-14 | 11:00 | 2018-03-20 | WDF | 5 | I | 2021-11-14 | 19:00 | 5.Within 4 Months | 2100023535 | 0050 | SMAT:Defect contact i LCP panel | Test, QC and close out | 1 | 6 | Need new mat |  | 2 | 2 | 0 | APPR SCH RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /50/GC-P-403A | COOLING WATER PUMP | NOSD | 2017-12-20
| MTN-ELEC | 2021-11-10 | 7:00 | 2018-09-22 | WDF | 4 | I | 2021-11-10 | 15:00 | 4.Within 2 Months | 2100024539 | 0045 | SMAT:Breaker tripper Exhaust fan 613 A | Design and set isolation | 1 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /C /09/GC-BM-613A | EXHAUST VENTILATOR MOTOR A | NOSD | 2018-08-13
| MTN-ELEC | 2021-11-10 | 15:00 | 2018-09-22 | WDF | 4 | I | 2021-11-14 | 15:00 | 4.Within 2 Months | 2100024539 | 0050 | SMAT:Breaker tripper Exhaust fan 613 A | Replace Breaker freq convertor | 1 | 6 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /C /09/GC-BM-613A | EXHAUST VENTILATOR MOTOR A | NOSD | 2018-08-13
| MTN-ELEC | 2021-11-14 | 15:00 | 2018-09-22 | WDF | 4 | I | 2021-11-14 | 15:00 | 4.Within 2 Months | 2100024539 | 0070 | SMAT:Breaker tripper Exhaust fan 613 A | De-isolate, repeal inhibits | 1 | 6 |  |  | 0 | 2 | 2 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /C /09/GC-BM-613A | EXHAUST VENTILATOR MOTOR A | NOSD | 2018-08-13
| MTN-ELEC | 2021-11-10 | 7:00 | 2019-02-12 | WDF | 4 | I | 2021-11-10 | 19:00 | 4.Within 2 Months | 2100025633 | 0010 | CMAT:ASTG 2018 Replace cable clamp on GE | Replace earth clamp | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEB-A-4101 | CHEMICAL TANK SKID A-4101 | NOSD | 2019-01-03
| MTN-ELEC | 2021-11-10 | 14:00 | 2019-04-01 | WDF | 6 | I | 2021-11-10 | 18:00 | 6.Within 8 Months | 2100025685 | 0030 | SMAT:Ventilatordæksel på El-motor rusten | Disconnect cables | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEA-PM-3931 | PUMP ELECTRIC MOTOR FOR P-3931 | NOSD | 2018-11-02
| MTN-ELEC | 2021-11-11 | 16:00 | 2019-04-01 | WDF | 6 | I | 2021-11-12 | 8:00 | 6.Within 8 Months | 2100025685 | 0080 | SMAT:Ventilatordæksel på El-motor rusten | Re-Connect cables / test | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEA-PM-3931 | PUMP ELECTRIC MOTOR FOR P-3931 | NOSD | 2018-11-02
| MTN-ELEC | 2021-11-10 | 7:00 | 2019-11-01 | WDF | 4 | V | 2021-11-10 | 7:00 | 4.Within 2 Months | 2100025810 | 0010 | Rep. of HPA breaker Trolly | Rep. of HPA breaker Trolly - Recieve Mat | 1 | 6 | Backload/Lars Fischer |  | 0 | 1 | 1 | APPR SMAT RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /61/GOFA-N-1801 | 6KV SWITCHBOARD | NOSD | 2019-09-22
| MTN-ELEC | 2021-11-10 | 7:00 | 2019-03-29 | WDF | 3 |  | 2021-11-11 | 15:00 | 3.Intermedt 1 Month | 2100025820 | 0010 | SMAT:OperSafe 39 PPE Electrical Safety E | Install. Elec. PPE kit GC Sw.BD room | 2 | 8 |  | 01-07 Lars F + MHN | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /6 | ELECTRIC ENERGY | NOSD | 2019-03-09
| MTN-ELEC | 2021-11-11 | 15:00 | 2019-03-29 | WDF | 3 |  | 2021-11-13 | 11:00 | 3.Intermedt 1 Month | 2100025820 | 0020 | SMAT:OperSafe 39 PPE Electrical Safety E | Install. Elec. PPE kit GE Sw.BD room | 2 | 8 |  | 01-07 Lars F + MHN | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /6 | ELECTRIC ENERGY | NOSD | 2019-03-09
| MTN-ELEC | 2021-11-13 | 11:00 | 2019-03-29 | WDF | 3 |  | 2021-11-14 | 19:00 | 3.Intermedt 1 Month | 2100025820 | 0030 | SMAT:OperSafe 39 PPE Electrical Safety E | Install. Elec. PPE kit GF Sw.BD room | 2 | 8 |  | 01-07 Lars F + MHN | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /6 | ELECTRIC ENERGY | NOSD | 2019-03-09
| MTN-ELEC | 2021-11-13 | 15:00 | 2018-09-08 | WDF | 6 | I | 2021-11-14 | 19:00 | 6.Within 8 Months | 2100026506 | 0050 | Jobs efter eftersyn på V-907 | Repair earth cable | 1 | 6 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEM-V-907 | AIR RECEIVER INSTR. AND UTILITY AIR | NOSD | 2018-04-11
| MTN-ELEC | 2021-11-10 | 11:00 | 2019-10-15 | WDF | 5 | I | 2021-11-12 | 11:00 | 5.Within 4 Months | 2100027103 | 0020 | Faultfind on GOFB-P-3922 | Fault-find on Motor and loop's | 1 | 6 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /F /75/GOFB-P-3922 | H2S SCAVENGER INJECT. PUMP | NOSD | 2019-07-17
| MTN-ELEC | 2021-11-12 | 11:00 | 2019-10-15 | WDF | 5 | I | 2021-11-12 | 19:00 | 5.Within 4 Months | 2100027103 | 0030 | Faultfind on GOFB-P-3922 | De-isolate, repeal inhibits | 2 | 6 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /F /75/GOFB-P-3922 | H2S SCAVENGER INJECT. PUMP | NOSD | 2019-07-17
| MTN-ELEC | 2021-11-13 | 7:00 | 2019-10-15 | WDF | 5 | I | 2021-11-13 | 15:00 | 5.Within 4 Months | 2100027103 | 0040 | Faultfind on GOFB-P-3922 | Test, paperwork and closeout | 1 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /F /75/GOFB-P-3922 | H2S SCAVENGER INJECT. PUMP | NOSD | 2019-07-17
| MTN-ELEC | 2021-11-10 | 9:00 | 2020-03-06 | WDF | 4 | I | 2021-11-10 | 13:00 | 4.Within 2 Months | 2100027272 | 0020 | GC-CM-601A Dokumentations opdattering | Assist PRODTECH | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /41/GC-CM-601A | REFRIG. COMPRESSOR MOTOR | NE | 2020-01-26
| MTN-ELEC | 2021-11-10 | 11:00 | 2020-05-01 | WDF | 4 | V | 2021-11-11 | 15:00 | 4.Within 2 Months | 2100029445 | 0030 | Emg. Gen. G-810 Low temp. jacket water | Dis-connect heater and pump | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /05/GC-G-810 | EMERGENCY GENERATOR |  | 2020-03-22
| MTN-ELEC | 2021-11-16 | 11:00 | 2020-05-01 | WDF | 4 | V | 2021-11-17 | 15:00 | 4.Within 2 Months | 2100029445 | 0070 | Emg. Gen. G-810 Low temp. jacket water | Re-connect heater and pump | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /05/GC-G-810 | EMERGENCY GENERATOR |  | 2020-03-22
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-06-26 | WDF | 4 |  | 2021-11-09 | 15:00 | 4.Within 2 Months | 2100029636 | 0020 | (EE-0058 UPS) Earth fault detect print | replace parts | 2 | 7 |  | PO step | 8 | 8 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /06/GEA-EE-0058 | 230 VAC UPS SYSTEM, GENERAL | NOSD | 2020-08-30
| MTN-ELEC | 2021-11-10 | 7:00 | 2020-05-19 | WDF | 4 | S | 2021-11-10 | 7:24 | 4.Within 2 Months | 2100030409 | 0010 | Replace door handle, Baking oven | Turn off oven, cool down | 1 | 7 |  | Hold Step | 0.1 | 0.1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82/GC-X-07981 | OVEN | NOSD | 2020-04-09
| MTN-ELEC | 2021-11-10 | 8:24 | 2020-05-19 | WDF | 4 | S | 2021-11-10 | 12:24 | 4.Within 2 Months | 2100030409 | 0020 | Replace door handle, Baking oven | Replace door handle | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82/GC-X-07981 | OVEN | NOSD | 2020-04-09
| MTN-ELEC | 2021-11-10 | 12:24 | 2020-05-19 | WDF | 4 | S | 2021-11-10 | 12:48 | 4.Within 2 Months | 2100030409 | 0030 | Replace door handle, Baking oven | Turn on oven | 1 | 7 |  | Hold Step | 0.1 | 0.1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82/GC-X-07981 | OVEN | NOSD | 2020-04-09
| MTN-ELEC | 2021-11-10 | 7:00 | 2020-11-25 | WDF | 4 | I | 2021-11-10 | 11:00 | 4.Within 2 Months | 2100030740 | 0010 | Replace Heater in briscopanel 1201 | Isolate power, Check for powerless cond. | 1 | 8 | Need more investigation | (6) | 1 | 1 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /A /07/GA-HE-903 | ANTI CONDENSATION HEATER | NOSD | 2020-06-28
| MTN-ELEC | 2021-11-10 | 11:00 | 2020-11-25 | WDF | 4 | I | 2021-11-11 | 11:00 | 4.Within 2 Months | 2100030740 | 0020 | Replace Heater in briscopanel 1201 | Replace Heater | 1 | 8 | Need more investigation | (6) | 3 | 3 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /A /07/GA-HE-903 | ANTI CONDENSATION HEATER | NOSD | 2020-06-28
| MTN-ELEC | 2021-11-11 | 11:00 | 2020-11-25 | WDF | 4 | I | 2021-11-11 | 13:00 | 4.Within 2 Months | 2100030740 | 0030 | Replace Heater in briscopanel 1201 | De-isolate | 1 | 8 | Need more investigation | (6) | 0.5 | 0.5 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /A /07/GA-HE-903 | ANTI CONDENSATION HEATER | NOSD | 2020-06-28
| MTN-ELEC | 2021-11-10 | 7:00 | 2020-06-07 | WDF | 4 | S | 2021-11-10 | 15:00 | 4.Within 2 Months | 2100031025 | 0010 | Replace belt tensioner | Adskille og demontere remstrammer | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-X-064021 | TREADMILL | NOSD | 2020-04-28
| MTN-ELEC | 2021-11-10 | 15:00 | 2020-06-07 | WDF | 4 | S | 2021-11-11 | 11:00 | 4.Within 2 Months | 2100031025 | 0020 | Replace belt tensioner | Montering af remstrammer | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-X-064021 | TREADMILL | NOSD | 2020-04-28
| MTN-ELEC | 2021-11-10 | 11:00 | 2020-12-18 | WDF | 6 | S | 2021-11-12 | 19:00 | 6.Within 8 Months | 2100031610 | 0020 | GC-P-902 Sewage plant, Pump need to be c | Changeout GC-P-902 | 1 | 7 |  | Hold Step | 8 | 8 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-P-902 | DOSING PUMP | NOSD | 2020-07-21
| MTN-ELEC | 2021-11-10 | 11:00 | 2020-09-25 | WDF | 5 | I | 2021-11-12 | 11:00 | 5.Within 4 Months | 2100032963 | 0040 | Exchange Bio pump - P-121 | Exchange P-121 | 1 | 6 |  |  | 6 | 6 | 0 | APPR SMAT RDBL | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /E /75/GEA-P-121 | BIOCIDE INJECTION SYSTEM |  | 2020-06-27
| MTN-ELEC | 2021-11-10 | 7:00 | 2020-10-01 | WDF | 5 |  | 2021-11-10 | 7:48 | 5.Within 4 Months | 2100033270 | 0010 | Replace drain hose in oven | Set personal isolation | 1 | 7 |  | Hold Step | 0.2 | 0.2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2020-07-03
| MTN-ELEC | 2021-11-10 | 7:48 | 2020-10-01 | WDF | 5 |  | 2021-11-10 | 15:48 | 5.Within 4 Months | 2100033270 | 0020 | Replace drain hose in oven | Replace broken parts | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2020-07-03
| MTN-ELEC | 2021-11-10 | 7:00 | 2021-02-16 | WDF | 5 | V | 2021-11-10 | 19:00 | 5.Within 4 Months | 2100040115 | 0010 | Replace driver units | Install driver units | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /61/GOFB-N-1804-05-01 | CIRCUIT BREAKER FOR BOOSTER PUMP PM-3502 | NOSD | 2020-11-18
| MTN-ELEC | 2021-11-10 | 13:00 | 2021-02-19 | WDF | 4 | I | 2021-11-12 | 9:00 | 4.Within 2 Months | 2100043686 | 0020 | GC watertreatment damaged junctionboxes | Replace JB's for XZ-1019 and XZ-1030 | 1 | 6 |  |  | 5 | 5 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-XZ-1019 | ALUMINIUM ELECTRODE | NOSD | 2021-01-10
| MTN-ELEC | 2021-11-12 | 9:00 | 2021-02-19 | WDF | 4 | I | 2021-11-12 | 15:00 | 4.Within 2 Months | 2100043686 | 0030 | GC watertreatment damaged junctionboxes | Test funtionality of the units | 1 | 6 |  |  | 1.5 | 1.5 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-XZ-1019 | ALUMINIUM ELECTRODE | NOSD | 2021-01-10
| MTN-ELEC | 2021-11-10 | 7:00 | 2022-04-24 | WDF | 8 |  | 2021-11-10 | 15:00 | 8.Longer than 1 Year | 2100044719 | 0010 | Replace Cooling desk light fixture | Isolate cooling desk and replace fixture | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2021-06-28
| MTN-ELEC | 2021-11-10 | 11:00 | 2021-04-23 | WDF | 4 | I | 2021-11-10 | 19:00 | 4.Within 2 Months | 2100046488 | 0020 | Replace contactor -K1 GOFB-HE-3506 | Replace contactor.. | 1 | 6 | Tavle Team |  | 2 | 2 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /61/GOFB-N-1805-01-G1 | MOTOR STARTER LUBE OIL HEAT GOFB-HE-3506 | NOSD | 2021-03-14
| MTN-ELEC | 2021-11-10 | 11:00 | 2021-07-07 | WDF | 5 | S | 2021-11-10 | 19:00 | 5.Within 4 Months | 2100047347 | 0020 | Troubleshoot space heater trips 3kV JB | Troubleshoot and fix if possible | 2 | 7 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61/GC-LP9B-Q11 | SPACE HEATER 3KV JB | NOSD | 2021-04-08
| MTN-ELEC | 2021-11-10 | 11:00 | 2021-07-28 | WDF | 5 | V | 2021-11-10 | 19:00 | 5.Within 4 Months | 2100048291 | 0020 | Replace GOFA-N-1802 Lamps for ground fau | Troubleshoot and correct faults | 1 | 6 | Tavle Team |  | 2 | 2 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /61/GOFA-N-1802 | NORMAL SUPPLY SWITCHBOARD | NOSD | 2021-04-29
| MTN-ELEC | 2021-11-11 | 7:00 | 2021-07-28 | WDF | 5 | V | 2021-11-11 | 11:00 | 5.Within 4 Months | 2100048291 | 0030 | Replace GOFA-N-1802 Lamps for ground fau | Replace pilot lamps | 1 | 6 | Tavle Team |  | 1 | 1 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /61/GOFA-N-1802 | NORMAL SUPPLY SWITCHBOARD | NOSD | 2021-04-29
| MTN-ELEC | 2021-11-10 | 9:00 | 2021-08-20 | WDF | 5 | V | 2021-11-10 | 17:00 | 5.Within 4 Months | 2100049337 | 0020 | Replace recidual current device | Replace components | 1 | 6 |  | GR Onshore 010721 | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /61/GOFB-N-1830-02-03 | MOV 38039B PIG RECIEVER | NOSD | 2021-05-22
| MTN-ELEC | 2021-11-10 | 11:00 | 2021-12-21 | WDF | 6 | I | 2021-11-10 | 19:00 | 6.Within 8 Months | 2100049500 | 0020 | Replace contactor motor starter | Replace contactor and accessory | 1 | 6 |  | GR onshore 070721 | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /61/GOFB-N-1830-03-06 | WATER CLARIFIER PUMP P-3911B | NOSD | 2021-07-24
| MTN-ELEC | 2021-11-10 | 13:00 | 2021-06-16 | WDF | 3 | S | 2021-11-10 | 19:00 | 3.Intermedt 1 Month | 2100050341 | 0020 | GC-M-900 Sewage plant contactor K9 defec | Replace faulty contactor with a new | 1 | 4 |  | GR Onshore 120721 | 1.5 | 1.5 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-M-900 | SEWAGE TREATMENT PLANT | NOSD | 2021-05-27
| MTN-ELEC | 2021-11-11 | 7:00 | 2021-06-16 | WDF | 3 | S | 2021-11-11 | 11:00 | 3.Intermedt 1 Month | 2100050341 | 0030 | GC-M-900 Sewage plant contactor K9 defec | Test funtionality | 1 | 4 |  | GR Onshore 120721 | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-M-900 | SEWAGE TREATMENT PLANT | NOSD | 2021-05-27
| MTN-ELEC | 2021-11-10 | 7:00 | 2022-02-02 | WDF | 6 | V | 2021-11-10 | 15:00 | 6.Within 8 Months | 2100051270 | 0010 | Cable bundle on west side of 2. upper. | Remove bundle and terminate cable ends | 1 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61 | POWER DISTRIBUTION (HV, LV) | NOSD | 2021-09-05
| MTN-ELEC | 2021-11-10 | 11:00 | 2021-08-21 | WDF | 4 | I | 2021-11-11 | 11:00 | 4.Within 2 Months | 2100051791 | 0020 | Replace HE-114103B in potwater skid | Replace Immersion heater | 1 | 6 |  |  | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-HE-114103B | HEATER | NOSD | 2021-07-12
| MTN-ELEC | 2021-12-13 | 15:28 | 2022-08-10 | WDF | 7 | V | 2021-12-14 | 11:28 | 7.Within 12 Months | 2100054133 | 0030 | GOC Sublight - 12Vdc Chg & batt faulty | Isolate ELEC | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MACM | GO /C /64/GC-XE-09368 | POWER SUPPLY FOR SUBSIDARY LIGHT |  | 2021-12-13
| MTN-ELEC | 2021-12-14 | 11:28 | 2022-08-10 | WDF | 7 | V | 2021-12-17 | 7:28 | 7.Within 12 Months | 2100054133 | 0040 | GOC Sublight - 12Vdc Chg & batt faulty | Fault find | 1 | 6 |  |  | 8 | 8 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MACM | GO /C /64/GC-XE-09368 | POWER SUPPLY FOR SUBSIDARY LIGHT |  | 2021-12-13
| MTN-ELEC | 2021-12-17 | 7:28 | 2022-08-10 | WDF | 7 | V | 2021-12-17 | 15:28 | 7.Within 12 Months | 2100054133 | 0050 | GOC Sublight - 12Vdc Chg & batt faulty | De-isolate | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MACM | GO /C /64/GC-XE-09368 | POWER SUPPLY FOR SUBSIDARY LIGHT |  | 2021-12-13
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-10-19 | WDF | 4 | V | 2021-11-08 | 19:00 | 4.Within 2 Months | 2100054383 | 0030 | Defect relay card to Panalarm | Replace relay | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /05/GEA-K-102 | CTRL PANEL FOR EMERGENCY GENERATOR G-812 |  | 2021-09-09
| MTN-ELEC | 2021-11-10 | 10:22 | 2021-09-23 | WDF | 3 | V | 2021-11-12 | 10:22 | 3.Intermedt 1 Month | 2100054714 | 0030 | Faulty firedamper GC-SOD-380 | Troubleshoot, clean and grease, exercise | 1 | 4 |  |  | 6 | 6 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/GC-SOD-0380 | FIRE DAMPER EXHAUST AIR LOW. LEV. | NOSD | 2021-09-03
| MTN-ELEC | 2021-12-26 | 9:07 | 2021-12-28 | WDF | 5 | V | 2021-12-30 | 9:07 | 5.Within 4 Months | 2100055031 | 0030 | Clean Gorm E fast loop | Check Heat tracing fast loop | 1 | 6 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GE-AE-2901 | SENSOR FOR AT-2901 (METERING) |  | 2021-09-29
| MTN-ELEC | 2021-12-24 | 11:00 | 2020-12-17 | WPM | C | V | 2021-12-25 | 15:00 | Business Critical | 2400065219 | 0011 | 4Y FW PUMP ANODE SKIFT GC-P-402B | Disconnecting power for pump | 1 | 5 | COP/to be cancelled | Hold Step | 4 | 4 | 0 | APPR PMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /01/GC-P-402B | FIREWATER PUMP | NOSD | 2020-06-05
| MTN-ELEC | 2021-11-08 | 7:00 | 2020-10-24 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400065284 | 0010 | 3Y CRUDE OIL PUMP A-117B; EL MOTOR INSP. | MOTOR, MEKANISK TJEK | 2 | 2 |  |  | 24 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /E /25/GEA-PM-117B | ELECTRIC MOTOR FOR CRUDE OIL PUMP |  | 2020-05-26
| MTN-ELEC | 2021-11-12 | 7:00 | 2020-10-24 | WPM | C | V | 2021-11-15 | 19:00 | Business Critical | 2400065284 | 0020 | 3Y CRUDE OIL PUMP A-117B; EL MOTOR INSP. | MOTOR, ELEKTRISK TJEK | 2 | 2 |  |  | 24 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /E /25/GEA-PM-117B | ELECTRIC MOTOR FOR CRUDE OIL PUMP |  | 2020-05-26
| MTN-ELEC | 2021-11-13 | 17:24 | 2020-09-03 | WPM | C | V | 2021-11-14 | 7:24 | Business Critical | 2400065313 | 0350 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SWITCH, FUNKTIONS TEST | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-ELEC | 2021-11-10 | 18:10 | 2021-01-08 | WPM | C | V | 2021-11-10 | 18:10 | Business Critical | 2400089876 | 0250 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SWITCH, FUNKTIONS TEST | 1 | 5 | Dobbel/2400128023 | Hold Step | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089895 | 0010 | 3Y GEA-EE-0022-09 Section | TL-3Y GEA-EE-0022-09 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089896 | 0010 | 3Y GEA-EE-0022-02 Section | TL-3Y GEA-EE-0022-02 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089897 | 0010 | 3Y GEA-EE-0022-07 Section | TL-3Y GEA-EE-0022-07 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089898 | 0010 | 3Y GEA-EE-0022-12 Section | TL-3Y GEA-EE-0022-12 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089899 | 0010 | 3Y GEA-EE-0022-05 Section | TL-3Y GEA-EE-0022-05 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089900 | 0010 | 3Y GEA-EE-0022-10 Section | TL-3Y GEA-EE-0022-10 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2022-01-05 | 19:00 | Non Critical | 2400089901 | 0010 | 3Y GEA-EE-0022 Cabinet/Busbars | TL-3Y GEA-EE-0022 CABINET/BUSBARS | 1 | 5 |  |  | 111 | 111 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089902 | 0010 | 3Y GEA-EE-0022-15 Section | TL-3Y GEA-EE-0022-15 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089903 | 0010 | 3Y GEA-EE-0022-16 Section | TL-3Y GEA-EE-0022-16 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 11:26 | 2021-01-09 | WPM | D | V | 2021-12-08 | 11:26 | Non Critical | 2400089904 | 0010 | 3Y GEA-EE-0022-03 Section | TL-3Y GEA-EE-0022-03 SECTION | 1 | 5 |  |  | 24 | 24 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 11:18 | 2021-01-09 | WPM | D | V | 2021-12-07 | 7:18 | Non Critical | 2400089905 | 0010 | 3Y GEA-EE-0022-14 Section | TL-3Y GEA-EE-0022-14 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-11-30 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-06 | 15:00 | Non Critical | 2400089906 | 0010 | 3Y GEA-EE-0022-00 Section | TL-3Y GEA-EE-0022-00 SECTION | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-12-06 | 7:00 | 2021-01-09 | WPM | D | V | 2021-12-13 | 11:00 | Non Critical | 2400089907 | 0010 | 3Y GEA-EE-0022-01 Section | TL-3Y GEA-EE-0022-01 SECTION | 1 | 5 |  |  | 22 | 22 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /61/GEA-EE-0022 | SWITCHBOARD/TRANSFORMER/LIGHTING |  | 2020-10-02
| MTN-ELEC | 2021-12-24 | 0:00 | 2021-01-09 | WPM | A | V | 2021-12-24 | 24:00 | Assurance | 2400090000 | 0010 | 3Y GEA-EE-0026-B Section | TL-3Y GEA-EE-0026-B SECTION | 1 | 3 | W09-W10 |  | 20 | 20 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /05/GEA-EE-0026 | SWITCHBOARDS/TRANSFORMERS/LIGHTING |  | 2020-11-08
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-06-26 | WPM | A | V | 2021-11-09 | 19:00 | Assurance | 2400126208 | 0010 | 3Y POSITION + ADVARSELSLYS | TL-3Y, POSITION + ADVARSELSLYS | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /64/NAVAIDS | NAVAIDS | NOSD | 2021-04-25
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-07-18 | WPM | C | V | 2021-11-16 | 15:00 | Business Critical | 2400128366 | 0010 | 6M ELEKTRISK HÅNDVÆRKTØJ - GOC | 6M ELEKTRISK HÅNDVÆRKTØJS CHECK | 1 | 5 |  |  | 25 | 25 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61 | POWER DISTRIBUTION (HV, LV) | NOSD | 2021-06-29
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-07-18 | WPM | C | I | 2021-11-16 | 15:00 | Business Critical | 2400128367 | 0010 | 6M ELEKTRISK HÅNDVÆRKTØJ - GOF | 6M ELEKTRISK HÅNDVÆRKTØJS CHECK | 1 | 5 |  |  | 25 | 25 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /84 | WORKSHOP/WAREHOUSE | NOSD | 2021-06-29
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-07-18 | WPM | C | S | 2021-11-16 | 15:00 | Business Critical | 2400128368 | 0010 | 6M ELEKTRISK HÅNDVÆRKTØJ - GOE | 6M ELEKTRISK HÅNDVÆRKTØJS CHECK | 1 | 5 |  |  | 25 | 25 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /84 | WORKSHOP/WAREHOUSE | NOSD | 2021-06-29
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-08-04 | WPM | D | V | 2021-11-11 | 15:00 | Non Critical | 2400128728 | 0010 | 1Y PORTABLE EQUIP. L-AUS EQUIPMENT, MOD | 1Y L-AUS VÆRKTØJS VEDLIGEHOLDELSES CHECK | 1 | 5 |  |  | 10 | 10 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61 | POWER DISTRIBUTION (HV, LV) | NOSD | 2021-06-18
| MTN-ELEC | 2021-11-08 | 11:00 | 2021-09-28 | WPM | C | V | 2021-11-21 | 15:00 | Business Critical | 2400134245 | 0010 | 3M GOC CHECK AF MIDL.TID. EL-INSTAL. | 3M MIDL. EL-INST. VEDLIGEHOLDELSES CHECK | 1 | 5 |  |  | 40 | 40 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /61 | POWER DISTRIBUTION (HV, LV) | NOSD | 2021-09-17
| MTN-ELEC | 2021-11-10 | 7:00 | 2021-09-23 | WPM | C | I | 2021-11-10 | 15:00 | Business Critical | 2400134417 | 0010 | 1Y IT-STATIC SWITCH | IT-SWITCH | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /08/DATA-NETWORK | DATA NETWORK | NOSD | 2021-08-18
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-10 | 19:00 | Business Critical | 2400134557 | 0010 | 6M EE-0522, 24VDC COMP. + TURB. M5ROOF | A. BATTERIRUMMETS TILSTAND | 1 | 5 |  |  | 9 | 9 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/GC-EE-0522 | 24V SYS 3 COMP/TURBINE MODULE 5 |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400134567 | 0010 | 6M AE-1820/1, 24VDC TURB., L3 | GOF-19C01 PM-CODE: | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400134576 | 0010 | 6M EE-0421, 24 VDC GEN. + TURB., M4U | A. BATTERIER | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/GC-EE-0421 | 24V DC UPS SYSTEM, GENERAL |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400134581 | 0010 | 6M EE-0014, 110VDC DW. GEAR POWER, M3L | A. BATTERIER | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/GC-EE-0014 | 110V DC SWITCHGEAR POWER SUPPLIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-10 | 19:00 | Business Critical | 2400134585 | 0010 | 6M AE-1901/2, 24VDC FIRE W. PUMP C.DECK | 03.01.2013 | 1 | 5 |  |  | 9 | 9 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400134590 | 0010 | 6M UPS-06185/-06186, INST. UPS, M6U | 6M VEDLIGEHOLDELSESPROCEDURE FOR GORM C | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-10 | 11:00 | Business Critical | 2400134594 | 0010 | 6M G-812, 24 VDC EMERG. GEN. L. DECK | A. BATTERIER GEA-BR-812-01/02 | 1 | 5 |  |  | 7 | 7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /05/GEA-G-812 | EMERGENCY DIESEL GENERATORS |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400134605 | 0010 | 6M EE-0422, 110VDC/380VAC SWBD, M4U | A. BATTERIRUMMETS TILSTAND | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/GC-EE-0422 | 110 VDC/220 VAC UPS SYSTEM, GENERAL |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400134615 | 0010 | 6M EE-0027, 110VDC POWER, L. DECK | 6M VEDLIGEHOLDELSESPROCEDURE FOR GORM E | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /06/GEA-EE-0027 | 110V DC UPS SYSTEM GENERAL |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400134617 | 0010 | 6M G-811, 24 VDC EMERG. GEN., M3L | A. BATTERIER. | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400134619 | 0010 | 6M EE-0058, 380VAC POWER, L. DECK | 6M VEDLIGEHOLDELSESPROCEDURE FOR GORM E | 1 | 5 |  |  | 13 | 13 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400134641 | 0010 | 6M G-810, 24VDC EMERG. GEN., M3L | A. BATTERIER GC-BR-810-01/02 | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400134645 | 0010 | 6M AE-1909A/B, 380VAC UPS PANEL, L1 | 6M VEDLIGEHOLDELSESPROCEDURE FOR GORM F | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /06/UNINTERRUPTED-POWER | UPS AND BATTERIES |  | 2021-08-28
| MTN-ELEC | 2021-11-12 | 7:00 | 2021-10-10 | WPM | B | V | 2021-11-15 | 19:00 | Safety & Env.Related | 2400134805 | 0012 | 6M TILSTANDSCHECK/SMØRING ESD/BD VENTILE | VENTILCHECK | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-09-24
| MTN-ELEC | 2021-11-10 | 7:00 | 2021-10-31 | WPM | D | I | 2021-11-13 | 19:00 | Non Critical | 2400150864 | 0010 | 1Y WORKSHOP TOOLS GOC TOOLS GOC | TJEK AF UDSTYR I WORKSHOP | 1 | 5 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /84 | WORKSHOP/WAREHOUSE | NOSD | 2021-09-14
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-11-07 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400150936 | 0010 | 6M AE-1905, 24VDC G-1628, L3 | A. BATTERIER | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /06/GOFC-AE-1905 | GENERATOR BATTERY AND CHARGER/INVERTER |  | 2021-10-19
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-11-14 | WPM | D | I | 2021-11-09 | 15:00 | Non Critical | 2400151169 | 0010 | 1M TØRRETUMBLERE OG VASKEMASKINER MODU | TL-1 M TØRRETUMBLERE OG VASKEMASKINER MO | 1 | 5 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /82/LAUNDRY-EQUIPMENT | LAUNDRY EQUIPMENT | NOSD | 2021-11-08
| MTN-ELEC | 2021-11-25 | 7:00 | 2021-12-01 | WPM | D | S | 2021-11-26 | 11:00 | Non Critical | 2400157371 | 0010 | 1M DRIKKEVAND KULFILTER SKIFT GORM | UDSKIFTNING AF KULFILTRE | 1 | 5 |  |  | 4 | 4 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MACM | GO /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT | NOSD | 2021-11-25
| MTN-ELEC | 2021-11-08 | 7:00 | 2021-12-03 | WPM | C | S | 2021-11-09 | 19:00 | Business Critical | 2400157450 | 0010 | 3Y KLOAKBEHANDLINGSENHED, GC-M-900 | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 6 | 6 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-M-900 | SEWAGE TREATMENT PLANT | NOSD | 2021-09-20
| MTN-ELEC | 2021-11-22 | 7:00 | 2021-12-22 | WPM | A | V | 2021-11-28 | 11:00 | Assurance | 2400160565 | 0010 | 1Y GOE, TYRA INLET HIPPS ASSUR. (IFA) | TL-1Y, GOE, TYRA INLET HIPPS ASSUR. (IFA | 1 | 2 |  |  | 19 | 19 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /03/HIPS-SYSTEM | HIPS SYSTEM |  | 2021-11-22
| MTN-ELEC | 2021-12-08 | 7:00 | 2021-12-14 | WPM | D | I | 2021-12-09 | 15:00 | Non Critical | 2400160572 | 0010 | 1M TØRRETUMBLERE OG VASKEMASKINER MODU | TL-1 M TØRRETUMBLERE OG VASKEMASKINER MO | 1 | 5 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /82/LAUNDRY-EQUIPMENT | LAUNDRY EQUIPMENT | NOSD | 2021-12-08
| MTN-INST | 2021-11-08 | 11:00 | 2019-05-12 | WDF | 4 | V | 2021-11-09 | 11:00 | 4.Within 2 Months | 2100022717 | 0020 | Replace XCV-0519 Actuator it's possibel | Dis-connect Sw.box & tubing | 1 | 6 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-XCV-0511 | INSTRUMENT AIR TO IP GAS COMPR. | NOSD | 2019-04-02
| MTN-INST | 2021-11-10 | 17:00 | 2019-05-12 | WDF | 4 | V | 2021-11-11 | 17:00 | 4.Within 2 Months | 2100022717 | 0050 | Replace XCV-0519 Actuator it's possibel | Connect Sw.box and tubing | 1 | 6 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-XCV-0511 | INSTRUMENT AIR TO IP GAS COMPR. | NOSD | 2019-04-02
| MTN-INST | 2021-11-08 | 7:00 | 2021-04-07 | WDF | 8 | I | 2021-11-08 | 7:00 | 8.Longer than 1 Year | 2100023649 | 0010 | BACKLOAD AF INSTRUMENTER FOR RE-CAL. | BACKLOAD AF INSTRUMENTER FOR RE-CAL. | 1 | 8 | No planning General job | No planning General job | 0 | 8 | 8 | APPR CMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /84 | WORKSHOP/WAREHOUSE | NOSD | 2019-04-18
| MTN-INST | 2021-11-08 | 7:00 | 2017-10-05 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100023854 | 0010 | GC-PCV-0210 check stroke, rep. supports | Check stroke mm. | 1 | 6 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /20/GC-PCV-0210 | FLARE V-102 | NOSD | 2017-07-07
| MTN-INST | 2021-11-10 | 15:00 | 2017-10-05 | WDF | 5 | V | 2021-11-13 | 11:00 | 5.Within 4 Months | 2100023854 | 0020 | GC-PCV-0210 check stroke, rep. supports | Reparer supportering af instrumentering. | 1 | 6 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /20/GC-PCV-0210 | FLARE V-102 | NOSD | 2017-07-07
| MTN-INST | 2021-11-08 | 11:00 | 2019-04-06 | WDF | 4 | I | 2021-11-12 | 11:00 | 4.Within 2 Months | 2100025635 | 0060 | Troubleshoot on GC-FIT-02262 | Replace FIT, test and calibrate | 1 | 6 |  |  | 12 | 12 | 0 | APPR PROK RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /75/GC-FIT-02262 | ANTI-FOAM INJECT FLOW INDIC. TRANSM. | NOSD | 2019-02-25
| MTN-INST | 2021-11-08 | 7:00 | 2018-06-30 | WDF | 3 | V | 2021-11-11 | 19:00 | 3.Intermedt 1 Month | 2100025717 | 0030 | Kalibrering af GOFD-PCV-34067A | Change positioner from reverse to direct | 1 | 8 | DISCUSS W. PRD | Hold Step | 12 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /11/GOFD-PCV-34067A | V-3420 TO HP FLARE HEADER | NOSD | 2018-06-10
| MTN-INST | 2021-11-12 | 9:00 | 2018-06-30 | WDF | 3 | V | 2021-11-16 | 9:00 | 3.Intermedt 1 Month | 2100025717 | 0050 | Kalibrering af GOFD-PCV-34067A | Change the PCV | 2 | 8 | DISCUSS W. PRD | Hold Step | 24 | 24 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /11/GOFD-PCV-34067A | V-3420 TO HP FLARE HEADER | NOSD | 2018-06-10
| MTN-INST | 2021-11-13 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-14 | 19:00 | 6.Within 8 Months | 2100025750 | 0032 | Exchange ESDV-33052 | Dismantle valve inst | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-INST | 2021-11-20 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-21 | 19:00 | 6.Within 8 Months | 2100025750 | 0055 | Exchange ESDV-33052 | Install new valve inst | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-INST | 2021-11-08 | 13:00 | 2018-09-12 | WDF | 6 | S | 2021-11-11 | 17:00 | 6.Within 8 Months | 2100025769 | 0020 | CMAT:RW Repair broken connection/fitting | Disconnect power cables for LG light | 1 | 7 | No planning General job | No planning General job | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /27/GOFB-LG-50294 | GAUGEREJECT COLLE.VESSEL V-5008 | NOSD | 2018-04-15
| MTN-INST | 2021-11-17 | 17:00 | 2018-09-12 | WDF | 6 | S | 2021-11-21 | 9:00 | 6.Within 8 Months | 2100025769 | 0050 | CMAT:RW Repair broken connection/fitting | Connect light for LG | 1 | 7 |  | No planning General job | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /27/GOFB-LG-50294 | GAUGEREJECT COLLE.VESSEL V-5008 | NOSD | 2018-04-15
| MTN-INST | 2021-11-10 | 15:00 | 2018-09-08 | WDF | 6 | I | 2021-11-11 | 11:00 | 6.Within 8 Months | 2100026506 | 0020 | Jobs efter eftersyn på V-907 | Prep. permit, spare parts, tools, Toolbo | 1 | 6 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEM-V-907 | AIR RECEIVER INSTR. AND UTILITY AIR | NOSD | 2018-04-11
| MTN-INST | 2021-11-08 | 7:00 | 2021-02-07 | WDF | 4 | I | 2021-11-08 | 7:00 | 4.Within 2 Months | 2100042857 | 0010 | FIT-53021 signal error - GOF Coolingwate | FIT-53021 signal error - GOF Coolingwate | 1 | 6 | To add material/220621 |  | 0 | 0.5 | 8 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /76/GOFA-FIT-53021 | FIT SIGNAL FR FE-53021 TO FIC-53021 |  | 2020-12-29
| MTN-INST | 2021-11-09 | 17:00 | 2021-02-17 | WDF | 4 | V | 2021-11-10 | 13:00 | 4.Within 2 Months | 2100043627 | 0040 | Air leak from actuator esdv-12740 | mount ZSO/ZSC | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /37/GA-ESDV-12740 | EMERGENCY SHUTDOWN VALVE | NE | 2021-01-08
| MTN-INST | 2021-12-27 | 7:06 | 2021-05-20 | WDF | 5 | I | 2021-12-27 | 15:06 | 5.Within 4 Months | 2100044957 | 0050 | PCV-0542 is leaking by piston | Mount instruments | 1 | 2 |  | GR Onshore 251121 | 2 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /71/GC-PCV-0542 | FUEL GAS CONTROL VALVE | NOSD | 2021-02-19
| MTN-INST | 2021-11-08 | 7:00 | 2021-05-15 | WDF | 5 | V | 2021-11-11 | 19:00 | 5.Within 4 Months | 2100044958 | 0010 | Replace Coriolis meter GOFB-FE-36224 | Replace Coriolis meter GOF-FT-36224 | 1 | 6 |  | Hold Step | 12 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /23/GOFB-FE-36224 | EXPORT OIL MEASUREMENT (METERING) |  | 2021-02-14
| MTN-INST | 2021-11-10 | 13:00 | 2021-03-14 | WDF | 3 | V | 2021-11-11 | 9:00 | 3.Intermedt 1 Month | 2100046088 | 0045 | ESDV-01189B - not full closure at trip | Hook up instruments | 1 | 4 |  | Hold Step | 2 | 2 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /31/GC-ESDV-01189B | EMERGENCY SHUTDOWN VALVE | NE | 2021-02-22
| MTN-INST | 2021-11-08 | 7:00 | 2021-04-08 | WDF | 3 | V | 2021-11-09 | 19:00 | 3.Intermedt 1 Month | 2100047342 | 0010 | ABB Safeguard Fan Alarm (change fan) | ABB Safeguard Fan Alarm (change fan) | 1 | 4 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/GC-CP-0420 | MASTER SAFEGUARD, FIRE & GAS/ESD PANEL |  | 2021-03-19
| MTN-INST | 2021-11-08 | 7:00 | 2021-04-08 | WDF | 3 | V | 2021-11-11 | 19:00 | 3.Intermedt 1 Month | 2100047446 | 0020 | H2s analyser IP-B poor condition | Replace flow meter FI-05785 + filter | 1 | 6 |  | Hold Step | 12 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /36/GC-FP-05788 | H2S ANALYSER PANEL, I.P. GAS TRAIN A |  | 2021-03-19
| MTN-INST | 2021-11-10 | 17:00 | 2021-07-15 | WDF | 5 | V | 2021-11-11 | 13:00 | 5.Within 4 Months | 2100047676 | 0050 | V-3411 PCV-34225-1 int. leaking | Calibrate and test | 1 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /20/GOFB-PCV-34225_1 | PRES. CTRL IN GAS DISCH FROM LP SEP. | NOSD | 2021-04-16
| MTN-INST | 2021-11-10 | 11:00 | 2021-07-21 | WDF | 5 | V | 2021-11-11 | 11:00 | 5.Within 4 Months | 2100048013 | 0030 | FCV-1503 stock open | Test and callibrate | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-FCV-1504 | CRUDE OIL TRANSFER SYSTEM | NOSD | 2021-04-22
| MTN-INST | 2021-11-10 | 11:00 | 2021-07-21 | WDF | 5 | V | 2021-11-11 | 11:00 | 5.Within 4 Months | 2100048014 | 0030 | FCV-1504 stock open | Test and callibrate | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-FCV-1504 | CRUDE OIL TRANSFER SYSTEM | NOSD | 2021-04-22
| MTN-INST | 2021-11-10 | 11:00 | 2021-07-21 | WDF | 5 | V | 2021-11-11 | 11:00 | 5.Within 4 Months | 2100048015 | 0030 | FCV-1507 is stock | Test and callibrate | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-FCV-1507 | CRUDE OIL TRANSFER SYSTEM | NOSD | 2021-04-22
| MTN-INST | 2021-11-08 | 11:00 | 2021-07-16 | WDF | 4 | I | 2021-11-08 | 19:00 | 4.Within 2 Months | 2100050343 | 0020 | Defect temp indicator on hyd-vessel | Replace Storage Tank - Miscellaneous | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /76/GOFA-T-5304 | HYDR.TANK, COOL.WATER PUMPS (HYDRAULIC) |  | 2021-06-06
| MTN-INST | 2021-11-08 | 13:00 | 2021-07-26 | WDF | 4 | V | 2021-11-10 | 9:00 | 4.Within 2 Months | 2100050750 | 0020 | Discharge valve on P-117D opens only 90% | Troubleshoot on valve | 1 | 6 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-PCV-36049 | CRUDE OIL FLOW TO DISCH. MANIFOLD | NE | 2021-06-16
| MTN-INST | 2021-11-08 | 11:00 | 2021-09-24 | WDF | 5 | S | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100050751 | 0020 | Emergeny stop malfunctioning | Replace Normal push/pull button | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /28/GC-PBS-090201 | PUSH BUTTON |  | 2021-06-26
| MTN-INST | 2021-11-09 | 11:00 | 2021-09-24 | WDF | 5 | S | 2021-11-09 | 15:00 | 5.Within 4 Months | 2100050751 | 0040 | Emergeny stop malfunctioning | Functional test | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /28/GC-PBS-090201 | PUSH BUTTON |  | 2021-06-26
| MTN-INST | 2021-11-10 | 9:57 | 2021-07-31 | WDF | 4 | V | 2021-11-11 | 13:57 | 4.Within 2 Months | 2100050909 | 0030 | Dismantle Gorm E Export meter for clean | De-isolate meter and open bypass | 1 | 6 |  |  | 4 | 4 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /26/GEB-FE-36166 | FLOW ELEMENT (METERING) |  | 2021-06-21
| MTN-INST | 2021-11-08 | 9:00 | 2021-09-09 | WDF | 5 | I | 2021-11-08 | 17:00 | 5.Within 4 Months | 2100051439 | 0020 | Extern Leak in hydrauilik panel GOF. | changeout valve | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /07/GOFA-PCV-31363 | HYDR. REGULATOR 344 BAR SUPPLY HEADER | NOSD | 2021-06-11
| MTN-INST | 2021-11-09 | 7:00 | 2021-09-09 | WDF | 5 | I | 2021-11-09 | 9:00 | 5.Within 4 Months | 2100051439 | 0040 | Extern Leak in hydrauilik panel GOF. | adjust S/P. | 1 | 6 |  | Hold Step | 0.5 | 0.5 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /07/GOFA-PCV-31363 | HYDR. REGULATOR 344 BAR SUPPLY HEADER | NOSD | 2021-06-11
| MTN-INST | 2021-11-09 | 11:00 | 2021-09-09 | WDF | 5 | I | 2021-11-09 | 19:00 | 5.Within 4 Months | 2100051439 | 0060 | Extern Leak in hydrauilik panel GOF. | changeout valve | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /07/GOFA-PCV-31363 | HYDR. REGULATOR 344 BAR SUPPLY HEADER | NOSD | 2021-06-11
| MTN-INST | 2021-11-10 | 9:00 | 2021-09-09 | WDF | 5 | I | 2021-11-10 | 11:00 | 5.Within 4 Months | 2100051439 | 0080 | Extern Leak in hydrauilik panel GOF. | adjust S/P. | 1 | 6 |  | Hold Step | 0.5 | 0.5 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /07/GOFA-PCV-31363 | HYDR. REGULATOR 344 BAR SUPPLY HEADER | NOSD | 2021-06-11
| MTN-INST | 2021-11-08 | 11:00 | 2021-07-16 | WDF | 3 | I | 2021-11-08 | 19:00 | 3.Intermedt 1 Month | 2100051480 | 0020 | Sensor for conductivity in potwater brok | Replace | 1 | 4 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-AIT-0355B | CONDUCTIVITY MONITOR |  | 2021-06-26
| MTN-INST | 2021-11-09 | 11:00 | 2021-07-16 | WDF | 3 | I | 2021-11-09 | 15:00 | 3.Intermedt 1 Month | 2100051480 | 0040 | Sensor for conductivity in potwater brok | Functional test | 1 | 4 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-AIT-0355B | CONDUCTIVITY MONITOR |  | 2021-06-26
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 11:00 | 3.Intermedt 1 Month | 2100051695 | 0030 | Calibrate level transmitter | Demount Instrumentation | 1 | 4 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0328 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 15:00 | 3.Intermedt 1 Month | 2100051695 | 0040 | Calibrate level transmitter | Calibrate Contact Level transmitter (flo | 1 | 4 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0328 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 15:00 | 3.Intermedt 1 Month | 2100051695 | 0050 | Calibrate level transmitter | Check Contact Level transmitter (float, | 1 | 4 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0328 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 15:00 | 3.Intermedt 1 Month | 2100051695 | 0060 | Calibrate level transmitter | Clean Contact Level transmitter (float, | 1 | 4 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0328 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 11:00 | 3.Intermedt 1 Month | 2100051695 | 0080 | Calibrate level transmitter | Mount Instrumentation | 1 | 4 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0328 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 11:00 | 3.Intermedt 1 Month | 2100051696 | 0030 | Calibrate level transmitter | Demount Instrumentation | 1 | 4 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0331 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-08 | 15:00 | 3.Intermedt 1 Month | 2100051696 | 0040 | Calibrate level transmitter | Calibrate Contact Level transmitter (flo | 1 | 4 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0331 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-08 | 15:00 | 2021-07-21 | WDF | 3 | I | 2021-11-09 | 11:00 | 3.Intermedt 1 Month | 2100051696 | 0050 | Calibrate level transmitter | Check Contact Level transmitter (float, | 1 | 4 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0331 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-09 | 11:00 | 2021-07-21 | WDF | 3 | I | 2021-11-09 | 19:00 | 3.Intermedt 1 Month | 2100051696 | 0060 | Calibrate level transmitter | Clean Contact Level transmitter (float, | 1 | 4 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0331 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-09 | 7:00 | 2021-07-21 | WDF | 3 | I | 2021-11-09 | 11:00 | 3.Intermedt 1 Month | 2100051696 | 0080 | Calibrate level transmitter | Mount Instrumentation | 1 | 4 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/GC-LT-0331 | LEVEL CONTROL TRANSMITTER | NOSD | 2021-07-01
| MTN-INST | 2021-11-09 | 9:00 | 2021-10-26 | WDF | 5 | V | 2021-11-09 | 17:00 | 5.Within 4 Months | 2100052130 | 0030 | XCV-0509 on C-202A Internal Leaking | demount SOV + ZS | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /32/GC-XCV-0509 | IP GAS COMPR. | NE | 2021-07-28
| MTN-INST | 2021-11-11 | 13:00 | 2021-10-26 | WDF | 5 | V | 2021-11-12 | 9:00 | 5.Within 4 Months | 2100052130 | 0060 | XCV-0509 on C-202A Internal Leaking | Mount SOV + ZS | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /32/GC-XCV-0509 | IP GAS COMPR. | NE | 2021-07-28
| MTN-INST | 2021-11-08 | 10:00 | 2021-08-03 | WDF | 3 | I | 2021-11-09 | 10:00 | 3.Intermedt 1 Month | 2100052448 | 0030 | GC-F-901A SOV-03359 defect INST. AIR PRE | Changeout GC-F-901A SOV-03359 | 1 | 4 |  | PO Step | 3 | 3 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-F-901A | INSTRUMENT AIR PRE-FILTER | NOSD | 2021-07-14
| MTN-INST | 2021-11-08 | 11:00 | 2021-11-13 | WDF | 5 | V | 2021-11-08 | 15:00 | 5.Within 4 Months | 2100053032 | 0020 | Glycol offgass ejector pessure transmitt | Demount Instrument, general | 1 | 6 |  | GR Onshore 090921 | 1 | 1 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /30/GC-PT-40101 | GAS FROM V-501 TO LP FLARE |  | 2021-08-15
| MTN-INST | 2021-11-08 | 15:00 | 2021-11-13 | WDF | 5 | V | 2021-11-09 | 11:00 | 5.Within 4 Months | 2100053032 | 0030 | Glycol offgass ejector pessure transmitt | Replace Pressure transmitter | 1 | 6 |  | GR Onshore 090921 | 2 | 2 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /30/GC-PT-40101 | GAS FROM V-501 TO LP FLARE |  | 2021-08-15
| MTN-INST | 2021-11-09 | 11:00 | 2021-11-13 | WDF | 5 | V | 2021-11-09 | 15:00 | 5.Within 4 Months | 2100053032 | 0040 | Glycol offgass ejector pessure transmitt | Mount Instrument, general | 1 | 6 |  | GR Onshore 090921 | 1 | 1 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /30/GC-PT-40101 | GAS FROM V-501 TO LP FLARE |  | 2021-08-15
| MTN-INST | 2021-11-10 | 7:00 | 2021-11-13 | WDF | 5 | V | 2021-11-10 | 11:00 | 5.Within 4 Months | 2100053032 | 0060 | Glycol offgass ejector pessure transmitt | Functional test | 1 | 6 |  | GR Onshore 090921 | 1 | 1 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /30/GC-PT-40101 | GAS FROM V-501 TO LP FLARE |  | 2021-08-15
| MTN-INST | 2021-11-10 | 7:00 | 2021-11-13 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100053032 | 0070 | Glycol offgass ejector pessure transmitt | Update MEL | 1 | 6 |  | GR Onshore 090921 | 2 | 2 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /30/GC-PT-40101 | GAS FROM V-501 TO LP FLARE |  | 2021-08-15
| MTN-INST | 2021-12-01 | 15:24 | 2021-10-06 | WDF | 4 | V | 2021-12-02 | 15:24 | 4.Within 2 Months | 2100053788 | 0020 | Gas seep on PCV Replace. | changeout PCV | 1 | 6 |  |  | 3 | 3 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /C /70/GC-PCV-0277 | GLYCOL HEATER | NE | 2021-08-27
| MTN-INST | 2021-12-02 | 15:24 | 2021-10-06 | WDF | 4 | V | 2021-12-03 | 7:24 | 4.Within 2 Months | 2100053788 | 0030 | Gas seep on PCV Replace. | adjust PCV | 1 | 6 |  |  | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /C /70/GC-PCV-0277 | GLYCOL HEATER | NE | 2021-08-27
| MTN-INST | 2021-11-08 | 15:00 | 2021-09-11 | WDF | 3 | V | 2021-11-09 | 15:00 | 3.Intermedt 1 Month | 2100053999 | 0020 | Deluge valve S/P 6,1 bar to be verified | Adjust/Test/Verify Deluge valve S/P | 1 | 4 |  |  | 3 | 3 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-0951 | DELUGE VALVE MOD 2 MEZZ DECK | NOSD | 2021-08-22
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-19 | WDF | 4 | I | 2021-11-08 | 15:00 | 4.Within 2 Months | 2100054384 | 0020 | LT-1518 på G-812 periodisk fejl. | Calibrate Contact Level transmitter (flo | 1 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /71/GEA-LT-1518 | LEVEL TRANSMITTER | NOSD | 2021-09-09
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-19 | WDF | 4 | I | 2021-11-08 | 15:00 | 4.Within 2 Months | 2100054384 | 0030 | LT-1518 på G-812 periodisk fejl. | Check Contact Level transmitter (float, | 1 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /71/GEA-LT-1518 | LEVEL TRANSMITTER | NOSD | 2021-09-09
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-19 | WDF | 4 | I | 2021-11-08 | 15:00 | 4.Within 2 Months | 2100054384 | 0040 | LT-1518 på G-812 periodisk fejl. | Replace Sensing element | 1 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /71/GEA-LT-1518 | LEVEL TRANSMITTER | NOSD | 2021-09-09
| MTN-INST | 2021-11-13 | 17:00 | 2020-01-15 | WPM | C | V | 2021-11-19 | 15:00 | Business Critical | 2400049973 | 0012 | 1Y FIRED HEATER | Fired heater | 1 | 5 |  |  | 17.5 | 17.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /72 | HOT WATER GENERATION AND DISTRIBUTION | NE | 2019-11-22
| MTN-INST | 2021-11-08 | 15:00 | 2020-02-01 | WPM | D | I | 2021-11-10 | 9:00 | Non Critical | 2400050051 | 0012 | CMAT:1Y ENWAMATIC FILTER | 1Y ENWAMATIC FILTER | 1 | 5 |  | Hold/CMAT | 4.5 | 4.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /51 | FILTRATION (MAIN AND PRELIMINARY) | NOSD | 2019-11-22
| MTN-INST | 2021-11-12 | 15:00 | 2020-02-23 | WPM | C | I | 2021-11-13 | 19:00 | Business Critical | 2400050402 | 0011 | 1Y BRISCO SSSV CONTROL PANEL - GOB | Registration of working hours | 1 | 5 |  | Hold Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /B /07/GB-FP-1377 | HYDRAULIC BOOSTER PANEL | NOSD | 2020-01-27
| MTN-INST | 2021-11-11 | 7:00 | 2020-02-22 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400050448 | 0030 | 2Y GC-A-0294 OIL EXPORT - METERING | Metering maintenance procedure for udski | 1 | 5 |  |  | 12 | 12 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /26/GC-A-0294 | PACKAGE EQUIPMENT SKID | NOSD | 2020-01-14
| MTN-INST | 2021-11-10 | 13:00 | 2019-10-19 | WPM | C | V | 2021-11-12 | 19:00 | Business Critical | 2400050512 | 0012 | 1Y RENSNING AF DRÆNSYSTEM | P&ID REF: GOFA-05-01014-0001, REV.19 | 1 | 5 |  |  | 7.5 | 7.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /27 | OILY WATER PROCESSING | NOSD | 2019-08-30
| MTN-INST | 2021-11-14 | 7:00 | 2019-10-24 | WPM | C | V | 2021-11-19 | 19:00 | Business Critical | 2400050513 | 0012 | 1Y RENSNING AF DRÆNSYSTEM | P&ID REF: GOCY-05-01057-0001, REV.24 | 1 | 5 |  |  | 18 | 18 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27 | OILY WATER PROCESSING | NE | 2019-08-30
| MTN-INST | 2021-11-08 | 17:00 | 2020-01-17 | WPM | C | I | 2021-11-09 | 13:00 | Business Critical | 2400050542 | 0012 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-3910 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-3910 | 1 | 5 | await 2100025740 |  | 2 | 2 | 0 | APPR | APPR OPND | REL PRT PCNF PRC SETC MANC NMAT | GO /F /75/GOFA-P-3910 | CATALYST PUMP | NE | 2019-12-24
| MTN-INST | 2021-11-08 | 17:00 | 2020-02-12 | WPM | C | V | 2021-11-09 | 13:00 | Business Critical | 2400050703 | 0012 | CHEMICAL INJECTION RACKS, GORM F | DER LAVES EN WORK PERMIT FOR AT UDFØ | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | NE | 2019-12-26
| MTN-INST | 2021-11-08 | 15:00 | 2020-05-30 | WPM | C | I | 2021-11-09 | 19:00 | Business Critical | 2400051329 | 0020 | 1Y VAND & GLYCOLEKS KØLEVANDS TANK T-403 | Registration of working hours | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /51 | FILTRATION (MAIN AND PRELIMINARY) | NE | 2020-04-13
| MTN-INST | 2021-11-08 | 7:00 | 2020-05-08 | WPM | C | S | 2021-11-09 | 19:00 | Business Critical | 2400051332 | 0010 | 3 WAVE RADAR SENSOR GOC | Wave sensor | 1 | 5 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /08/WEATHER-MONITORING | WEATHER MONITORING SYSTEM | NOSD | 2020-03-30
| MTN-INST | 2021-11-24 | 7:00 | 2020-06-27 | WPM | B | V | 2021-11-27 | 19:00 | Safety & Env.Related | 2400051345 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117E | Instrument ventiler - generelt | 1 | 3 |  | Hold Step | 12 | 12 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117E | CRUDE OIL EXPORT PUMP | NE | 2020-05-23
| MTN-INST | 2021-11-10 | 11:00 | 2020-05-19 | WPM | D | V | 2021-11-11 | 11:00 | Non Critical | 2400051363 | 0012 | 1YA BREATHING AIR COMPRESSOR GC-A-5401/5 | 1YA BREATHING AIR COMPRESSOR GC-A-5401/5 | 1 | 5 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /02/GC-A-5401 | BREATHING AIR COMPRESSOR | NOSD | 2020-03-09
| MTN-INST | 2021-11-08 | 7:00 | 2020-04-22 | WPM | C | I | 2021-11-08 | 17:00 | Business Critical | 2400051559 | 0012 | 1YA FERRIC SULPHATE INJECTION GOF-P-3901 | EX check | 1 | 5 |  |  | 2.5 | 2.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFD-V-3901 | FERRIC-SULPHATE STORAGE TANK | NE | 2020-03-29
| MTN-INST | 2021-11-11 | 7:00 | 2020-04-28 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400051596 | 0030 | 3Y RFA SEP. GC-V-104 - METERING | Metering maintenance procedure for udski | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /11/GC-V-104 | ROLF SEPARATOR | NOSD | 2020-03-18
| MTN-INST | 2021-11-11 | 17:00 | 2020-05-30 | WPM | C | V | 2021-11-14 | 13:00 | Business Critical | 2400051673 | 0012 | 1YA WATER CLARIFIER INJECTION GOF-P-3911 | 1YA WATER CLARIFIER INJECTION GOF-P-3911 | 1 | 5 |  |  | 8 | 8 | 0 | APPR | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFB-A-3904 | WATER CLARIFIER PUMP SKID | NE | 2020-05-03
| MTN-INST | 2021-11-10 | 7:00 | 2020-05-15 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400051694 | 0012 | MEXEL INJECTION RACKS, GORM C | DER LAVES EN WORK PERMIT FOR AT UDFØ | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | NE | 2020-03-27
| MTN-INST | 2021-11-08 | 15:00 | 2020-05-26 | WPM | C | V | 2021-11-10 | 9:00 | Business Critical | 2400051706 | 0012 | 1Y SIKKERHEDSDRÆN | GOF-53A01 PM-Code: | 1 | 5 |  |  | 4.5 | 4.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /28 | CLOSED DRAINS/OPEN DRAINS | NE | 2020-04-07
| MTN-INST | 2021-11-19 | 12:57 | 2020-05-12 | WPM | B | V | 2021-11-22 | 14:57 | Safety & Env.Related | 2400051953 | 0012 | 1Y BOOSTER PUMPER GC-P-101A/B/C/D MODUL2 | 1Y BOOSTER PUMPER GC-P-101A/B/C/D MODUL2 | 1 | 5 | W01-W02/ptw-270720/271013 |  | 9.5 | 9.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC MANC NMAT | GO /C /23/GC-P-101A | CRUDE OIL BUSTER PUMP | NE | 2020-04-09
| MTN-INST | 2021-11-10 | 11:00 | 2020-06-28 | WPM | C | I | 2021-11-11 | 11:00 | Business Critical | 2400051969 | 0012 | 2Y INST. & UTILITY AIR DRYER. GC-X-0986 | 2Y INST. & UTILITY AIR DRYER. GC-X-0986 | 1 | 5 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /07/GC-X-0986 | AIR DRYER PACKAGE | NE | 2020-04-16
| MTN-INST | 2021-11-11 | 9:00 | 2020-05-09 | WPM | C | V | 2021-11-12 | 13:00 | Business Critical | 2400052002 | 0040 | 1Y GOFA-FT-35979 - PW METERING | FØR OPSTART AF VEDLIGEHOLD, SKAL DER OPR | 1 | 5 | SR | Pick/Pack/Myndighedskrav | 4 | 4 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NE | 2020-03-22
| MTN-INST | 2021-11-12 | 11:00 | 2020-05-08 | WPM | C | V | 2021-11-13 | 11:00 | Business Critical | 2400052042 | 0020 | 1Y BRISCO SSSV CONTROL PANEL - GOA | Registration of working hours | 1 | 5 |  | Hold Step | 3 | 3 | 0 | APPR PMAT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /07/GA-FP-1207 | EXTENSION FOR BRISCO PANEL BOOSTER PANEL | NOSD | 2020-04-11
| MTN-INST | 2021-11-08 | 7:00 | 2020-03-20 | WPM | C | V | 2021-11-16 | 11:00 | Business Critical | 2400052065 | 0010 | 6M DRAG REDUCER INJECTION | 6M DRAG REDUCER INJECTION | 1 | 5 |  |  | 25 | 25 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | NE | 2020-02-19
| MTN-INST | 2021-11-12 | 17:00 | 2020-03-31 | WPM | C | I | 2021-11-16 | 9:00 | Business Critical | 2400052228 | 0012 | 1YA WATERCLARIFIER GC-P-1122A-D, GC-P-11 | Instrument ventiler - generelt | 1 | 5 |  |  | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-P-1122A | WTR CLARIFICATION INJ. PUMP FOR GC-V-101 | NE | 2020-03-03
| MTN-INST | 2021-11-10 | 11:00 | 2020-04-24 | WPM | C | I | 2021-11-15 | 19:00 | Business Critical | 2400052735 | 0020 | 1Y COOLING WATER PUMPS P-5305A/B, LEVEL | Registration of working hours | 1 | 5 |  |  | 17 | 17 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /76/GOFA-E-5303 | CIRC. OIL TANK HEATER | NE | 2020-03-05
| MTN-INST | 2021-11-09 | 11:00 | 2020-04-21 | WPM | A |  | 2021-11-12 | 15:00 | Assurance | 2400052743 | 0020 | 3Y KØLEVANDSFILTRE GC-F-402A/B/C | Registration of working hours | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /76 | COOLING WATER | NE | 2020-03-12
| MTN-INST | 2021-11-09 | 11:00 | 2020-04-10 | WPM | C | V | 2021-11-10 | 9:00 | Business Critical | 2400052780 | 0012 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-4604 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-4604 | 1 | 5 |  |  | 2.5 | 2.5 | 0 | APPR | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFB-A-3903 | H2S SCAV. INJECTION PUMP SKID | NE | 2020-03-16
| MTN-INST | 2021-11-08 | 7:00 | 2020-05-02 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400052799 | 0010 | 2Y BARRIERER I GOFA-CP-02/03/05 | BEMÆRK: | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2020-02-18
| MTN-INST | 2021-11-08 | 7:00 | 2020-04-06 | WPM | C | I | 2021-11-08 | 15:00 | Business Critical | 2400053068 | 0010 | 3Y HYDROCYCLON SKID, V-5021 | 08.09.2012 | 1 | 5 |  | Create route | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27/GC-V-5021 | TEST SEPARATOR HYDROCYCLONE (ROLF) | NE | 2020-02-28
| MTN-INST | 2021-11-09 | 11:00 | 2018-08-21 | WPM | C | V | 2021-11-12 | 9:00 | Business Critical | 2400053269 | 0012 | SMAT:1Y COOLING WATER PUMP, P-5302. | 1Y COOLING WATER PUMP, P-5302. | 1 | 5 | After 2100025573 | Await 2100042857 + 2100025573 | 8.5 | 8.5 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /F /76 | COOLING WATER | NE | 2018-07-02
| MTN-INST | 2021-11-09 | 11:00 | 2018-09-25 | WPM | C | I | 2021-11-09 | 11:00 | Business Critical | 2400053290 | 0012 | SMAT:1YA SCALE INH P-3902A/B/C&P-3915A/B | 28.05.2013 | 1 | 5 |  |  | 0 | 3 | 3 | APPR PROK RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2018-08-31
| MTN-INST | 2021-11-09 | 13:00 | 2018-04-21 | WPM | C |  | 2021-11-12 | 19:00 | Business Critical | 2400053328 | 0012 | SMAT:KØLEVANDSFILTRE GC-F-402A/B/C | 1. KONTROLLER FILTRENE FOR UDVENDIGE S | 1 | 5 | Done after 2100027130 |  | 10.5 | 10.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /76 | COOLING WATER | NOSD | 2018-03-25
| MTN-INST | 2021-11-08 | 7:00 | 2019-11-12 | WPM | D | V | 2021-11-09 | 15:00 | Non Critical | 2400053861 | 0030 | 6M GLYCOL DEHYDRATION PACKAGE, GC-P-501A | GLYKOL-CIRKULATIONSPUMPE | 1 | 5 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /30 | DEHYDRATION/SWEETENING | NOSD | 2019-02-28
| MTN-INST | 2021-11-08 | 7:00 | 2018-02-13 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400055125 | 0010 | SMAT:WIRELINE OVERRIDE PANELER, GA/GB. | PANELER INKL. ALLE TILHØRENDE SLANGER SE | 1 | 5 |  |  | 1 | 12 | 11 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2017-06-10
| MTN-INST | 2021-11-08 | 7:00 | 2020-10-02 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400064923 | 0010 | 3Y GOFC-FE-57233 - CO2 METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /70/GOFC-FE-57233 | FUEL GAS FLOW CALCULATION (METERING) | NOSD | 2020-05-07
| MTN-INST | 2021-11-09 | 7:00 | 2020-08-21 | WPM | C |  | 2021-11-09 | 19:00 | Business Critical | 2400065431 | 0020 | 1Y OLIE FRA ROLF (TIE IN) VALVE/INST | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /12/INSTRUMENTS | INSTRUMENTS |  | 2020-06-10
| MTN-INST | 2021-11-22 | 15:00 | 2020-08-07 | WPM | C | V | 2021-11-26 | 11:00 | Business Critical | 2400065550 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117G | INSTRUMENT VENTILER - GENERELT | 1 | 5 | Dobbel/2400125984 | Hold Step | 11 | 11 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-05-18
| MTN-INST | 2021-11-24 | 7:00 | 2020-07-20 | WPM | B | V | 2021-11-27 | 19:00 | Safety & Env.Related | 2400065584 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117F | INSTRUMENT VENTILER - GENERELT | 1 | 5 | Dobbel/2400125708 | Hold Step | 12 | 12 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /E /25/GEA-P-117F | CRUDE OIL EXPORT PUMP |  | 2020-05-12
| MTN-INST | 2021-11-08 | 7:00 | 2020-09-10 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400065609 | 0010 | 6M HP FLARE DRUM + PUMP GOF | TL-6M HP FLARE DRUM + PUMP GOF | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /36/GOFA-V-4001 | HP FLARE DRUM |  | 2020-08-02
| MTN-INST | 2021-11-09 | 15:00 | 2020-10-14 | WPM | C | I | 2021-11-10 | 17:00 | Business Critical | 2400065837 | 0012 | 1Y CHEMICAL INJEC. RACK GA-A-1202, GB-A | TL-1YA CHEMICAL INJEC. RACK GA-A-1202, G | 1 | 5 |  |  | 3.5 | 3.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /A /75/GA-A-1202 | CHEMICAL INJ. RACK | NOSD | 2020-08-02
| MTN-INST | 2021-11-09 | 11:00 | 2020-10-27 | WPM | D | S | 2021-11-09 | 19:00 | Non Critical | 2400065908 | 0012 | 1Y UTIL/INSTR AIR HOSE REELS | TL-1Y UTIL/INSTR AIR HOSE REELS | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/INST-AIR-HOSEREELS | INST AIR HOSE REELS |  | 2020-07-25
| MTN-INST | 2021-11-08 | 7:00 | 2020-10-21 | WPM | B | V | 2021-11-09 | 11:00 | Safety & Env.Related | 2400066256 | 0010 | 1Y W-MIST NOZ GC-A-0483 FOR GC-C-202C | 1Y W-MIST NOZ GC-A-0483 FOR GC-C-202C | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0483 | FINE WATER HI-FOG SKID FOR C-202C | NOSD | 2020-08-22
| MTN-INST | 2021-11-08 | 7:00 | 2020-11-21 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400066316 | 0010 | 3Y GEA-FE-1512 - CO2 METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /70/GEA-FE-1512 | FLOW ELEMENT (METERING) | NOSD | 2020-06-26
| MTN-INST | 2021-11-08 | 7:00 | 2020-11-18 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400066321 | 0010 | 3Y GORM E GAS EXPORT - METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /34/METERING | METERING PRODUCED GAS, TRANSFER | NOSD | 2020-06-23
| MTN-INST | 2021-11-08 | 7:00 | 2020-11-08 | WPM | C | S | 2021-11-15 | 19:00 | Business Critical | 2400069597 | 0010 | 1Y MANUAL OPERATED BLOCK VALVES | GOC-34Z02 PM-CODE: | 1 | 5 |  |  | 24 | 24 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /20/GC-HCV-3408 | HAND CONTROL VALVE - VBB6FF | NOSD | 2020-08-25
| MTN-INST | 2021-11-08 | 7:00 | 2020-10-20 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400076899 | 0010 | 3Y GORM B REINJECTION GAS - METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /B /37/METERING | METERING PRODUCED GAS, INJECTION | NOSD | 2020-08-07
| MTN-INST | 2021-11-08 | 7:00 | 2020-10-20 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400076900 | 0010 | 3Y GORM B LIFT GAS - METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 0 | 5 |  |  | 1.5 | 1.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /B /37/METERING | METERING PRODUCED GAS, INJECTION | NOSD | 2020-08-07
| MTN-INST | 2021-11-08 | 7:00 | 2020-10-20 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400076933 | 0010 | 6M FW BOOSTER PUMPS, INST | BRANDVANDSBOOSTERPUMPER, INST | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/FW-PUMPS | FIREWATER PUMPS | NOSD | 2020-10-01
| MTN-INST | 2021-11-24 | 7:00 | 2020-10-22 | WPM | B | V | 2021-11-27 | 19:00 | Safety & Env.Related | 2400076940 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117C | INSTRUMENT VENTILER - GENERELT | 1 | 5 | Dobbel/2400115934 | Hold Step | 12 | 12 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /E /25/GEA-P-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-09-22
| MTN-INST | 2021-11-08 | 7:00 | 2020-12-14 | WPM | D | I | 2021-11-08 | 15:00 | Non Critical | 2400086652 | 0010 | 2Y VÆRKTØJSSKAB | VÆRKTØJSSKAB INKL. VARMELEGME OG TEMP. S | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /F /84 | WORKSHOP/WAREHOUSE | NOSD | 2020-10-02
| MTN-INST | 2021-11-09 | 17:00 | 2020-12-17 | WPM | C | I | 2021-11-11 | 9:00 | Business Critical | 2400087126 | 0012 | 1Y CHEMICAL INJECTION, BIOCIDE - GOE | TL-1YA CHEMICAL INJECTION, BIOCIDE - GOE | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /75/GEA-P-121 | BIOCIDE INJECTION SYSTEM | NOSD | 2020-11-11
| MTN-INST | 2021-11-12 | 7:00 | 2020-12-26 | WPM | C | I | 2021-11-14 | 15:00 | Business Critical | 2400087392 | 0012 | 1Y DEMULSIFIER INJECTION GOF-P-3913/39 | 09.09.2012 | 1 | 5 |  | Hold Step | 8 | 8 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /75/GOFA-P-3913 | RECIPROCATING PUMP | NOSD | 2020-11-20
| MTN-INST | 2021-11-09 | 15:00 | 2021-01-14 | WPM | C | I | 2021-11-10 | 17:00 | Business Critical | 2400096752 | 0012 | 1Y SODIUM HYPOCHLORITE INJECTION GOF-P- | TL-1YA SODIUM HYPOCHLORITE INJECTION GOF | 1 | 5 |  |  | 3.5 | 3.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3905 | SODIUM HYPOCHLORITE PUMP, 50 L/HR |  | 2020-12-09
| MTN-INST | 2021-11-09 | 7:00 | 2021-01-15 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400096753 | 0012 | 1Y H2S SCAV. INJEC, GOF-P-3909 | KONTROLRUM ADVISERES OM AT PUMPEN STOPPE | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3909 | H2S SCAVENGER PUMP |  | 2020-12-10
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102289 | 0010 | 1Y DRY CHECK, GC-XCV-1110 | DEL VALVE GC-XCV-1110 - 6M/1Y | 1 | 3 |  | Hold Step/2400102289 + 2400129633 | 8 | 8 | 0 | APPR SECE CMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /01/GC-XCV-1110 | DELUGE VALVE CRANE T-804B PEDESTAL | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102292 | 0010 | 1Y DRY CHECK, GC-XCV-0631 | 6M/1Y - DEL VALVE GC-XCV-0631 | 1 | 3 |  | 2400102292 + 2400129627 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-0631 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102293 | 0010 | 1Y DRY CHECK, GA-XCV-1223 | DEL VALVE GA-XCV-1223 - 6M/1Y | 1 | 3 |  | 2400102293 + 2400129641 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /A /01/GA-XCV-1223 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102295 | 0010 | 1Y DRY CHECK, GB-XCV-1322 | DEL VALVE GB-XCV-1322 - 6M/1Y | 1 | 3 |  | 2400102295 + 2400129640 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /B /01/GB-XCV-1322 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102296 | 0010 | 1Y DRY CHECK, GC-XCV-1111 | DEL VALVE GC-XCV-1111 - 6M/1Y | 1 | 3 |  | Hold Step/2400102296 + 2400129636 | 8 | 8 | 0 | APPR SECE CMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /01/GC-XCV-1111 | DELUGE VALVE CRANE T-804A PEDESTAL | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102300 | 0010 | 1Y DRY CHECK, GA-XCV-1224 | 6M/1Y DEL VALVE GA-XCV-1224 | 1 | 3 |  | 2400102300 + 2400129638 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /A /01/GA-XCV-1224 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102301 | 0010 | 1Y DRY CHECK, GC-XCV-0331 | 6M/1Y - DEL VALVE GC-XCV-0331 | 1 | 3 |  | 2400102301 + 2400129635 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-0331 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102302 | 0010 | 1Y DRY CHECK, GC-XCV-0949 | 6M/1Y - DEL VALVE GC-XCV-0949 | 1 | 3 |  | 2400102302 + 2400129630 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /01/GC-XCV-0949 | DELUGE VALVE IN CABINET A-0949 | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102303 | 0010 | 1Y DRY CHECK, GB-XCV-1321 | DEL VALVE GB-XCV-1321 - 6M/1Y | 1 | 3 |  | 2400102303 + 2400129637 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /B /01/GB-XCV-1321 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102304 | 0010 | 1Y DRY CHECK, GA-XCV-1225 | DEL VALVE GA-XCV-1225 - 6M/1Y | 1 | 3 |  | 2400102304 + 2400129639 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /A /01/GA-XCV-1225 | DELUGE VALVE | NOSD | 2021-01-23
| MTN-INST | 2021-11-08 | 11:00 | 2021-02-22 | WPM | A | V | 2021-11-10 | 19:00 | Assurance | 2400102305 | 0010 | 1Y DRY CHECK, GC-XCV-1569 | 6M/1Y - DEL VALVE GC-XCV-1569 | 1 | 3 |  | 2400102305 + 2400129628 | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-1569 | DELUGE VALVE IN CABINET A-1509 | NOSD | 2021-01-23
| MTN-INST | 2021-11-13 | 13:00 | 2021-03-01 | WPM | C | I | 2021-11-17 | 9:00 | Business Critical | 2400102985 | 0012 | 1Y ANTIFOAM PUMP SKID, GC-A-0289 | 08.09.2012 | 1 | 5 |  |  | 11 | 11 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-A-0289 | ANTIFOAM INJECTION PACKAGE |  | 2021-01-24
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-06 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400103743 | 0040 | 3Y GC-FE-500031 - PW METERING | METERING - DIFFERENSTRYKTRANSMITTER | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27/GC-FE-500031 | FLOW ELEMENT (METERING) | NOSD | 2020-12-22
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105547 | 0010 | 6M WATERMIST GC-A-0488 FOR GC-G-802 | 8.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0488 | FIREWATER MIST SKID FOR G-802 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105549 | 0010 | 6M WATERMIST GC-A-0491 FOR GC-G-805 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0491 | FIREWATER MIST SKID FOR G-805 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105553 | 0010 | 6M W-MIST GOFC-A-0455 FOR GOFC-PT-3521 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFC-A-0455 | WATER MIST SKID FOR PT-3521 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105560 | 0010 | 6M WATERMIST GOFA-A-0457 FOR GOFA-A-1701 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFA-A-0457 | FIREWATER MIST SKID FOR GOFA-A-1701 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105561 | 0010 | 6M WATERMIST GEB-A-0492 FOR GEB-GT-815 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /01/GEB-A-0492 | FIREWATER MIST SKID FOR GEB-GT-815 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105570 | 0010 | 6M W-MIST GOFB-A-0454 FOR GOFB-PT-3506 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFB-A-0454 | FIREWATER MIST SKID FOR P-3506 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105574 | 0010 | 6M WATERMIST GC-A-0490 FOR GC-G-804 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0490 | FIREWATER MIST SKID FOR G-804 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105577 | 0010 | 6M W-MIST GOFA-A-0453 FOR GOFA-PT-3503 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFA-A-0453 | FIREWATER MIST SKID FOR P-3503 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105578 | 0010 | 6M WATERMIST GC-A-0480 FOR GC-C-201/205 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0480 | FINE WATER HI-FOG SKID FOR C-201/205 | NOSD | 2021-03-01
| MTN-INST | 2021-11-15 | 7:00 | 2021-03-16 | WPM | C | V | 2021-11-16 | 15:00 | Business Critical | 2400105581 | 0030 | 3Y SSSV BOOSTER PANEL - GOA | REGISTRATION OF WORKING HOURS | 1 | 5 |  | Hold Step | 5 | 5 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /A /07/GA-FP-1215 | SSSV BOOSTER PANEL N-61/W61 | NOSD | 2021-01-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105584 | 0010 | 6M WATERMIST GC-A-0481 FOR GC-C-202A | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0481 | FINE WATER HI-FOG SKID FOR C-202A | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105585 | 0010 | 6M WATERMIST GEA-A-0493 FOR GC-G-812 | 08.11.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /01/GEA-A-0493 | FIREWATER MIST SKID FOR GOE EMG. ROOM | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105591 | 0010 | 6M WATERMIST GC-A-0483 FOR GC-C-202C | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /01/GC-A-0483 | FINE WATER HI-FOG SKID FOR C-202C | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105592 | 0010 | 6M WATERMIST GC-A-0489 FOR GC-G-803 | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0489 | FIREWATER MIST SKID FOR G-803 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400105593 | 0010 | 6M WATERMSIT GC-A-0484 FOR GC-C-203A | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0484 | FINE WATER HI-FOG SKID FOR C-203A | NOSD | 2021-02-26
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400105596 | 0010 | 6M WATERMSIT GC-A-0482 FOR GC-C-202B | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0482 | FINE WATER HI-FOG SKID FOR C-202B | NOSD | 2021-02-26
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105597 | 0010 | 6M WATERMIST GC-C-0486 FOR GC-G-810/811 | 05.12.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0486 | HI-FOG SKID FOR MOD 3 LAYDOWN AREA | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105598 | 0010 | 6M WATERMIST GC-A-0487 FOR GC-G-801 | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0487 | FIREWATER MIST SKID FOR G-801 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105601 | 0010 | 6M W-MIST GOFD-A-0456 FOR GOFD-C-4201 | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFD-A-0456 | FIREWATER MIST SKID FOR A-4201 | NOSD | 2021-03-01
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-17 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400105603 | 0010 | 6M WATERMIST GC-A-0485 FOR GC-C-203B | 08.11.2013 | 1 | 3 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0485 | FINE WATER HI-FOG SKID FOR C-203B | NOSD | 2021-03-01
| MTN-INST | 2021-11-09 | 13:00 | 2021-03-19 | WPM | C | I | 2021-11-10 | 13:00 | Business Critical | 2400105660 | 0012 | 1Y OXYGEN SCAVENGER INJECTION GOF-P-390 | TL-1YA OXYGEN SCAVENGER INJECTION GOF-P- | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3907 | OXYGEN SCAVENGER PUMP |  | 2021-02-11
| MTN-INST | 2021-11-10 | 7:00 | 2021-02-19 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400105892 | 0012 | 3M FW PUMPS GC-P-401A/B AND P-402A/B | 3M FW PUMPS GC-P-401A/B + 402A/B | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/FW-PUMPS | FIREWATER PUMPS | NOSD | 2021-02-08
| MTN-INST | 2021-11-08 | 7:00 | 2021-03-26 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400106028 | 0010 | 1Y W-MIST NOZ GOFA-A-0457 F GOFA-A-1701 | 21.02.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFA-A-0457 | FIREWATER MIST SKID FOR GOFA-A-1701 |  | 2021-02-24
| MTN-INST | 2021-11-09 | 11:00 | 2021-03-27 | WPM | C | S | 2021-11-12 | 15:00 | Business Critical | 2400106126 | 0020 | 6M KØLEVANDSFILTRE GC-F-402A/B/C | REGISTRATION OF WORKING HOURS | 1 | 8 | +2100030939 | (5)After/2100029442 | 10 | 10 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /51/GC-F-402A | COOLING WATER FILTER |  | 2021-03-08
| MTN-INST | 2021-11-09 | 7:00 | 2021-04-09 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400108387 | 0012 | 1Y KEMIKALIE INJECTION PUMPE GOF-P-3906 | TL-1YAKEMIKALIE INJECTION PUMPE GOF-P-39 | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3906 | BIOCIDE PUMP |  | 2021-03-04
| MTN-INST | 2021-11-09 | 15:00 | 2021-04-13 | WPM | C | V | 2021-11-13 | 19:00 | Business Critical | 2400115939 | 0020 | 3Y COOLING WATER PUMP, P-5301 | REGISTRATION OF WORKING HOURS | 1 | 5 |  | Hold Step | 13 | 13 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /76/GOFA-A-5301 | SKID |  | 2021-01-29
| MTN-INST | 2021-11-08 | 7:00 | 2021-05-02 | WPM | B | S | 2021-11-08 | 15:00 | Safety & Env.Related | 2400116213 | 0010 | 3M AVIATION FUEL DISPENSER - GOC | 6M AVIATION DISPENSER UNIT: | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-04-22
| MTN-INST | 2021-11-08 | 7:00 | 2021-04-30 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400116374 | 0010 | 6M W-MIST GOFC-A-0452 FOR GOFC-A-1601 | FØR DER UDFØRES PM-CHECK INDHENTES TILLA | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFC-A-0452 | WATER MIST SKID FOR GOFC-A-1601 | NOSD | 2021-04-14
| MTN-INST | 2021-11-11 | 11:00 | 2021-05-07 | WPM | B | V | 2021-11-12 | 15:00 | Safety & Env.Related | 2400116474 | 0020 | 1Y AIR COMP GC-C-901A | 1Y AIR COMP. GC-C-901A | 1 | 5 |  | STPO Step | 4 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /07/GC-C-901A | SCREW COMPR. FOR INSTR AND UTILITY AIR |  | 2021-04-07
| MTN-INST | 2021-11-08 | 7:00 | 2021-05-13 | WPM | D | S | 2021-11-10 | 9:00 | Non Critical | 2400116595 | 0010 | 9M FISCALE MÅLEINSTRUMENTER | 12.09.2013 | 1 | 5 |  |  | 6.5 | 6.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /84/TEST-EQUIPMENT | TEST EQUIPMENT | NOSD | 2021-03-27
| MTN-INST | 2021-11-08 | 7:00 | 2021-06-05 | WPM | C | S | 2021-11-08 | 11:00 | Business Critical | 2400124808 | 0010 | 2Y FIRED HEATER, EX-CHECK, AUXIL. EQUIP. | GOF-11B02 PM-CODE: | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /72/GOFA-F-1101 | FIRED HEAT. DUTY 7000/5584.7 KW | NOSD | 2021-04-11
| MTN-INST | 2021-11-08 | 11:00 | 2021-06-05 | WPM | C | S | 2021-11-08 | 15:00 | Business Critical | 2400124808 | 0012 | 2Y FIRED HEATER, EX-CHECK, AUXIL. EQUIP. | GOF-11B02 PM-CODE: | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /72/GOFA-F-1101 | FIRED HEAT. DUTY 7000/5584.7 KW | NOSD | 2021-04-11
| MTN-INST | 2021-11-08 | 7:00 | 2021-06-03 | WPM | D | S | 2021-11-09 | 19:00 | Non Critical | 2400124822 | 0010 | 1Y SERVICE OF SIMULTAN AEROTEST | 28.06.2013 | 1 | 5 |  | Hold Step | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /84/TEST-EQUIPMENT | TEST EQUIPMENT | NOSD | 2021-04-17
| MTN-INST | 2021-11-08 | 7:00 | 2021-06-15 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400125655 | 0010 | 3Y SEPARATOR GC-V-102 - METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /20/METERING | SEPARATION METERING | NOSD | 2021-04-02
| MTN-INST | 2021-11-10 | 17:00 | 2021-06-11 | WPM | C | I | 2021-11-12 | 17:00 | Business Critical | 2400125701 | 0012 | 3Y H2S SCAVENGER INJECTION | 27.08.2012 | 1 | 5 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-A-1096 | H2S SCAVENGER CHEM INJECTION PUMP SKID |  | 2021-03-29
| MTN-INST | 2021-11-09 | 7:00 | 2021-06-19 | WPM | D | V | 2021-11-09 | 11:00 | Non Critical | 2400125843 | 0012 | 1Y BAUER KOMPRESSOR | TL-YA BAUER KOMPRESSOR | 1 | 8 | Forkert mat/030621 | PO Step | 1 | 1 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PRC SETC GMPS MANC | GO /E /07/GEB-C-5440 | COMPRESSOR |  | 2021-05-03
| MTN-INST | 2021-11-08 | 7:00 | 2021-06-18 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400125972 | 0010 | 3Y HYDROCYCLONE SKID | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /27/GOFB-V-5006A | SKJOLD B HYDROCLYCLONE |  | 2021-04-05
| MTN-INST | 2021-11-09 | 15:00 | 2021-07-12 | WPM | C | V | 2021-11-13 | 19:00 | Business Critical | 2400128030 | 0020 | 3Y COOLING WATER PUMP, P-5302 | REGISTRATION OF WORKING HOURS | 1 | 5 |  | PO Step | 13 | 13 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /76/GOFA-A-5301 | SKID |  | 2021-04-29
| MTN-INST | 2021-11-09 | 15:00 | 2021-08-08 | WPM | C | I | 2021-11-13 | 19:00 | Business Critical | 2400129026 | 0020 | 3Y KØLEVANDSCIRK.PUMP. + EKSP.TANK GC-P- | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 13 | 13 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /76/GC-T-0500 | COOLING WATER HEAD TANK |  | 2021-05-26
| MTN-INST | 2021-11-09 | 11:00 | 2021-08-10 | WPM | C | I | 2021-11-10 | 9:00 | Business Critical | 2400129028 | 0012 | 3Y WATER CLARIFIER PUMPS | OSP031 HÅNDTERING AF AFFALD FØLGES | 1 | 5 |  |  | 2.5 | 2.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /75/GEA-A-3913 | CHEMICAL INJECTION SKID (WATER CLARIFIER |  | 2021-05-28
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | B | V | 2021-11-10 | 15:00 | Safety & Env.Related | 2400129627 | 0010 | 6M DRY CHECK, GC-XCV-0631 | 6M/1Y - DEL VALVE GC-XCV-0631 | 1 | 5 |  | 2400102292 + 2400129627 | 7 | 7 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-0631 | DELUGE VALVE | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | A | V | 2021-11-10 | 15:00 | Assurance | 2400129628 | 0010 | 6M DRY CHECK, GC-XCV-1569 | 6M/1Y - DEL VALVE GC-XCV-1569 | 1 | 3 |  | 2400102305 + 2400129628 | 7 | 7 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-1569 | DELUGE VALVE IN CABINET A-1509 | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | A | V | 2021-11-10 | 15:00 | Assurance | 2400129630 | 0010 | 6M DRY CHECK, GC-XCV-0949 | 6M/1Y - DEL VALVE GC-XCV-0949 | 1 | 3 |  | 2400102302 + 2400129630 | 7 | 7 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-0949 | DELUGE VALVE IN CABINET A-0949 | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | A | V | 2021-11-10 | 15:00 | Assurance | 2400129633 | 0010 | 6M DRY CHECK, GC-XCV-1110 | DEL VALVE GC-XCV-1110 - 6M/1Y | 1 | 3 |  | 2400102289 + 2400129633 | 7 | 7 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-1110 | DELUGE VALVE CRANE T-804B PEDESTAL | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | B | V | 2021-11-10 | 15:00 | Safety & Env.Related | 2400129635 | 0010 | 6M DRY CHECK, GC-XCV-0331 | 6M/1Y - DEL VALVE GC-XCV-0331 | 1 | 5 |  | 2400102301 + 2400129635 | 7 | 7 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-0331 | DELUGE VALVE | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | A | V | 2021-11-10 | 15:00 | Assurance | 2400129636 | 0010 | 6M DRY CHECK, GC-XCV-1111 | DEL VALVE GC-XCV-1111 - 6M/1Y | 1 | 3 |  | 2400102296 + 2400129636 | 7 | 7 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-1111 | DELUGE VALVE CRANE T-804A PEDESTAL | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400129637 | 0010 | 6M DRY CHECK, GB-XCV-1321 | DEL VALVE GB-XCV-1321 - 6M/1Y | 1 | 5 |  | 2400102303 + 2400129637 | 7 | 7 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /B /01/GB-XCV-1321 | DELUGE VALVE | NOSD | 2021-08-03
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400129638 | 0010 | 6M DRY CHECK, GA-XCV-1224 | 6M/1Y DEL VALVE GA-XCV-1224 | 1 | 5 |  | 2400102300 + 2400129638 | 7 | 7 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /A /01/GA-XCV-1224 | DELUGE VALVE | NOSD | 2021-08-03
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400129639 | 0010 | 6M DRY CHECK, GA-XCV-1225 | DEL VALVE GA-XCV-1225 - 6M/1Y | 1 | 5 |  | 2400102304 + 2400129639 | 7 | 7 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /A /01/GA-XCV-1225 | DELUGE VALVE | NOSD | 2021-08-03
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400129640 | 0010 | 6M DRY CHECK, GB-XCV-1322 | DEL VALVE GB-XCV-1322 - 6M/1Y | 1 | 5 |  | 2400102295 + 2400129640 | 7 | 7 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /B /01/GB-XCV-1322 | DELUGE VALVE | NOSD | 2021-08-03
| MTN-INST | 2021-11-08 | 11:00 | 2021-08-22 | WPM | A | V | 2021-11-10 | 15:00 | Assurance | 2400129641 | 0010 | 6M DRY CHECK, GA-XCV-1223 | DEL VALVE GA-XCV-1223 - 6M/1Y | 1 | 3 |  | 2400102293 + 2400129641 | 7 | 7 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /A /01/GA-XCV-1223 | DELUGE VALVE | NOSD | 2021-08-06
| MTN-INST | 2021-11-10 | 7:00 | 2021-08-18 | WPM | A | I | 2021-11-10 | 17:00 | Assurance | 2400129671 | 0012 | 3M INST. + UTILITY AIR DRYER, GC-D-901 A | MICROFILTER, GC-F-901 | 1 | 5 |  | Hold Step | 2.5 | 2.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-D-901A | AIR DRYER FOR INSTR AND UTILITY AIR |  | 2021-08-08
| MTN-INST | 2021-11-14 | 7:00 | 2021-08-17 | WPM | A | V | 2021-11-19 | 19:00 | Assurance | 2400129678 | 0012 | 1Y GC-G-803 SOLAR GEN | TL-9M GC-G-803, SOLAR GEN | 1 | 3 |  | Hold Step | 18 | 18 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /60/GC-A-803 | MAIN GENERATOR UNIT |  | 2021-07-18
| MTN-INST | 2021-11-11 | 15:00 | 2021-08-22 | WPM | B | V | 2021-11-15 | 11:00 | Safety & Env.Related | 2400129681 | 0012 | 6M CHECK AF DELUGE DYSER + RØR | TL-6M CHECK AF DELUGE DYSER + RØR | 1 | 5 |  |  | 11 | 11 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /A /01/DELUGE-SKIDS | DELUGE SKIDS | NOSD | 2021-08-06
| MTN-INST | 2021-11-08 | 7:00 | 2021-08-21 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400129685 | 0010 | 6M HP FLARE DRUM + PUMP GOF | TL-6M HP FLARE DRUM + PUMP GOF | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /36/GOFA-V-4001 | HP FLARE DRUM |  | 2021-08-02
| MTN-INST | 2021-11-24 | 7:00 | 2021-08-18 | WPM | B | V | 2021-11-27 | 19:00 | Safety & Env.Related | 2400129686 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117B | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  | Hold Step | 12 | 12 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-07-19
| MTN-INST | 2021-11-13 | 11:00 | 2021-08-26 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400129829 | 0040 | 2Y GOFA-V-3401 - METERING | METERING MAINTENANCE PROCEDURE FOR UDSKI | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20/METERING | SEPARATION METERING | NOSD | 2021-07-02
| MTN-INST | 2021-11-13 | 11:00 | 2021-08-26 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400129830 | 0040 | 2Y GOFB-V-3410 - METERING | METERING MAINTENANCE PROCEDURE FOR UDSKI | 1 | 5 |  | Refurbish/Return | 10 | 10 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20/METERING | SEPARATION METERING | NOSD | 2021-07-02
| MTN-INST | 2021-11-08 | 7:00 | 2021-08-26 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400129876 | 0010 | 6M HP FLARE DRUM OG PUMPS GOB(GOC-40D01) | TL-6M HP FLARE DRUM OG PUMPS GORM B | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /B /36/GOBZ-V-4010 | HP FLARE DRUM |  | 2021-08-07
| MTN-INST | 2021-11-09 | 9:00 | 2021-09-01 | WPM | C | I | 2021-11-11 | 17:00 | Business Critical | 2400129883 | 0012 | 6M KØLEVANDGC-03SPUMPER GC-P-403A/B/C | TAG NO. P-403A, P-403B OG P-403C | 1 | 5 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /50/GC-P-403A | COOLING WATER PUMP |  | 2021-08-13
| MTN-INST | 2021-11-08 | 7:00 | 2021-09-30 | WPM | C | S | 2021-11-15 | 19:00 | Business Critical | 2400134246 | 0010 | 1Y MANUAL OPERATED BLOCK VALVES | GOC-34Z02 PM-CODE: | 1 | 5 |  |  | 24 | 24 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /20/GC-HCV-3408 | HAND CONTROL VALVE - VBB6FF | NOSD | 2021-08-25
| MTN-INST | 2021-11-09 | 15:00 | 2021-09-07 | WPM | C | I | 2021-11-10 | 17:00 | Business Critical | 2400134247 | 0012 | 1Y CHEMICAL INJEC. RACK GA-A-1202, GB-A | TL-1YA CHEMICAL INJEC. RACK GA-A-1202, G | 1 | 5 |  |  | 3.5 | 3.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /A /75/GA-A-1202 | CHEMICAL INJ. RACK | NOSD | 2021-08-02
| MTN-INST | 2021-11-14 | 7:00 | 2021-09-23 | WPM | C |  | 2021-11-19 | 19:00 | Business Critical | 2400134250 | 0012 | 1Y RENSNING AF DRÆNSYSTEM | P+ID REF: GOCY-05-01057-0001, REV.24 | 1 | 5 |  |  | 18 | 18 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27/P-G | PIPING GROUP |  | 2021-08-18
| MTN-INST | 2021-11-08 | 7:00 | 2021-09-04 | WPM | D | S | 2021-11-09 | 19:00 | Non Critical | 2400134252 | 0010 | 6M PROCESS CALIBRATION EQUIPMENT | MAINTENANCE TEXT: | 1 | 5 |  | Hold Step | 6 | 6 | 0 | APPR WMAT AWSD RDBL | APPR OPND | REL PRC SETC MANC | GO /C /84/TEST-EQUIPMENT | TEST EQUIPMENT | NOSD | 2021-08-10
| MTN-INST | 2021-11-09 | 11:00 | 2021-09-11 | WPM | C | I | 2021-11-10 | 9:00 | Business Critical | 2400134258 | 0012 | 1Y SCALE INHIB, P-3902A/B/C + P-3915A/B | 28.05.2013 | 1 | 5 |  | Hold Step | 2.5 | 2.5 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-08-06
| MTN-INST | 2021-11-10 | 13:00 | 2021-09-23 | WPM | C | V | 2021-11-12 | 19:00 | Business Critical | 2400134259 | 0012 | 1Y RENSNING AF DRÆNSYSTEM | P+ID REF: GOFA-05-01014-0001, REV.19 | 1 | 5 |  |  | 7.5 | 7.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /28/DRAIN-DISPOSAL | DRAIN DISPOSAL | NOSD | 2021-08-18
| MTN-INST | 2021-11-09 | 11:00 | 2021-09-10 | WPM | D | S | 2021-11-09 | 19:00 | Non Critical | 2400134410 | 0012 | 1Y UTIL/INSTR AIR HOSE REELS | TL-1Y UTIL/INSTR AIR HOSE REELS | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/INST-AIR-HOSEREELS | INST AIR HOSE REELS |  | 2021-07-25
| MTN-INST | 2021-11-11 | 17:00 | 2021-09-11 | WPM | C | I | 2021-11-14 | 13:00 | Business Critical | 2400134562 | 0012 | 3M H2S SCAVENGER INJECTION | TL-3M H2S SCAVENGER INJECTION | 1 | 5 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-A-1096 | H2S SCAVENGER CHEM INJECTION PUMP SKID |  | 2021-08-31
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-03 | WPM | C | V | 2021-11-14 | 15:00 | Business Critical | 2400134582 | 0010 | 3M FIRE DAMPER | TL-3M, FIRE DAMPER | 1 | 5 |  |  | 20 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-09-22
| MTN-INST | 2021-11-12 | 11:00 | 2021-09-16 | WPM | C | V | 2021-11-13 | 13:00 | Business Critical | 2400134607 | 0012 | 6M SSSV BOOSTER PANEL - GOA | BEMÆRK! | 1 | 5 |  | Hold Step | 3.5 | 3.5 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /A /07/GA-FP-1215 | SSSV BOOSTER PANEL N-61/W61 | NOSD | 2021-08-28
| MTN-INST | 2021-11-24 | 7:00 | 2021-10-13 | WPM | B | V | 2021-11-27 | 19:00 | Safety & Env.Related | 2400134801 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117D | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  | Hold Step | 12 | 12 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-13
| MTN-INST | 2021-11-10 | 15:00 | 2021-10-12 | WPM | D | I | 2021-11-11 | 19:00 | Non Critical | 2400134802 | 0012 | 6M BREATHING AIR COMPRESSOR GC-A-5401/54 | TL-6M BREATHING AIR COMPRESSOR GC-A-5401 | 1 | 5 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /02/BREATHING-AIR-SYSTEM | GO /B /02/BREATHING-AIR-SYSTEM | NOSD | 2021-09-17
| MTN-INST | 2021-11-08 | 11:00 | 2021-10-12 | WPM | C | V | 2021-11-09 | 9:00 | Business Critical | 2400134804 | 0012 | 3M COOLING WATER PUMP, P-5302 | INSTRUMENTATION FOR, P-5302 | 1 | 5 |  |  | 2.5 | 2.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /76/GOFA-A-5301 | SKID |  | 2021-10-01
| MTN-INST | 2021-11-08 | 11:00 | 2021-10-13 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400134806 | 0012 | 6M COOLING WATER PUMP, P-5301 | INSTRUMENTATION FOR, P-5301 | 1 | 5 |  | STPO Step | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /76/GOFA-A-5301 | SKID |  | 2021-09-24
| MTN-INST | 2021-11-20 | 7:00 | 2021-10-18 | WPM | C | V | 2021-11-22 | 19:00 | Business Critical | 2400139143 | 0012 | 6M BOOSTER PUMPER GC-P-101A/B/C/D MODUL2 | BOOSTER-PUMPE | 1 | 5 |  |  | 9 | 9 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /23/GC-P-101A | CRUDE OIL BUSTER PUMP |  | 2021-09-29
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-21 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400139151 | 0010 | 3M FIRE DAMPER SS WORKSHOP | TL-3M, FIRE DAMPER SS WORKSHOP | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-10-10
| MTN-INST | 2021-11-11 | 11:00 | 2021-10-24 | WPM | C | S | 2021-11-12 | 9:00 | Business Critical | 2400139153 | 0012 | 6M SALTVANDSSERVICEPUMPER GC-P-404A/B | 1. TAG NO. PI-0937, PI-0938 OG PI-0939 | 1 | 5 |  |  | 2.5 | 2.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /50/GC-P-404A | SERVICE WATER SUPPLY PUMP |  | 2021-10-05
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-23 | WPM | B | V | 2021-11-10 | 15:00 | Safety & Env.Related | 2400139154 | 0010 | 3M FIRE DAMPER MODUL 6 UPPER | TL-3M FIRE DAMPER MODUL 6 UPPER | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-10-13
| MTN-INST | 2021-11-24 | 7:00 | 2021-10-22 | WPM | B | V | 2021-11-27 | 19:00 | Safety & Env.Related | 2400139156 | 0012 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117C | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  | Hold Step | 12 | 12 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-22
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-21 | WPM | D | I | 2021-11-09 | 11:00 | Non Critical | 2400139157 | 0010 | 6M GLYCOL DEHYDRATION PACKAGE, GC-P-501A | GLYKOL-CIRKULATIONSPUMPE | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /30/GC-P-501A | GLYCOL CIRCULATING PUMP P-501 A/B |  | 2021-09-26
| MTN-INST | 2021-11-08 | 7:00 | 2021-11-02 | WPM | B | S | 2021-11-08 | 15:00 | Safety & Env.Related | 2400150903 | 0010 | 3M AVIATION FUEL DISPENSER - GOC | 6M AVIATION DISPENSER UNIT: | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-10-23
| MTN-INST | 2021-11-10 | 7:00 | 2021-11-05 | WPM | C | I | 2021-11-11 | 11:00 | Business Critical | 2400150911 | 0020 | 1Y LAUNCHER GAS GOE-TYE EP-3803 | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /34/GEA-EP-3803 | GORM GAS EXPORT LAUNCHER |  | 2021-09-30
| MTN-INST | 2021-11-08 | 7:00 | 2021-11-01 | WPM | B | V | 2021-11-09 | 15:00 | Safety & Env.Related | 2400150915 | 0010 | 3M FIRE DAMPER GOF VAERKSTED LEVEL 3 | TL-3M, FIRE DAMPER GOF VAERKSTED LEVEL 3 | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-10-22
| MTN-INST | 2021-11-12 | 7:00 | 2021-11-03 | WPM | A | V | 2021-11-15 | 19:00 | Assurance | 2400150921 | 0012 | 1Y V-5002, INSTRUMENTER OG PUMPER | TL-YA V-5002, INSTRUMENTER OG PUMPER | 1 | 3 |  |  | 12 | 12 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27/GC-V-5002 | RETENTION TANK |  | 2021-10-04
| MTN-INST | 2021-11-12 | 7:00 | 2021-11-05 | WPM | C | V | 2021-11-12 | 19:00 | Business Critical | 2400150927 | 0012 | 6M BRISCO PANEL - GOB | BEMÆRK! ARBEJDET UDFØRES EFTER AFTALE OG | 1 | 5 |  | Hold Step | 3 | 3 | 0 | APPR WMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /B /07/WELLHEAD-CONTROL-PANEL | WELLHEAD CONTROL PANEL | NOSD | 2021-10-17
| MTN-INST | 2021-11-08 | 7:00 | 2021-10-26 | WPM | B | V | 2021-11-10 | 15:00 | Safety & Env.Related | 2400150934 | 0010 | 3M FIRE DAMPER GOF INDBLAESNING LEVEL 1 | TL-3M, FIRE DAMPER GOF INDBLAESNING LEVE | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-10-16
| MTN-INST | 2021-11-08 | 7:00 | 2021-11-04 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400150935 | 0010 | 3M FIRE DAMPER GOE, WORKSH. + GEN. MOD | TL-3M. FIRE DAMPER GOE, WORKSH. + GEN. M | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-10-24
| MTN-INST | 2021-11-08 | 11:00 | 2021-10-30 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400150940 | 0012 | 3M DIESEL FORDELINGSPUMPER FIL P-801A/B | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/DIESEL-PUMPS | DIESEL PUMPS |  | 2021-10-19
| MTN-INST | 2021-11-12 | 15:00 | 2021-10-04 | WPM | C | I | 2021-11-14 | 15:00 | Business Critical | 2400150943 | 0012 | 3M POT WATER TREATMENT, GOC | VIGTIGT! DETTE CHECK SKAL UDFØRES A | 1 | 5 |  |  | 6 | 6 | 0 | APPR CMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-T-420 | TANK | NOSD | 2021-09-23
| MTN-INST | 2021-11-08 | 7:00 | 2021-11-21 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400151241 | 0010 | 1Y GC-FE-0507 - CO2 METERING | 1Y METERING MAINTENANCE PROCEDURE FOR VI | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /70/GC-FE-0507 | FUEL GAS FLOW CALCULATION (METERING) | NOSD | 2021-10-16
| MTN-INST | 2021-11-08 | 7:00 | 2021-11-18 | WPM | C | V | 2021-11-08 | 12:12 | Business Critical | 2400151242 | 0010 | 1Y GORM C DIESEL - CO2 METERING | FISCAL VIS OG FUNKT DIFFTRYKTRANSM | 0 | 5 |  |  | 1.3 | 1.3 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/METERING | DIESEL/GAS FUEL METERING | NOSD | 2021-10-13
| MTN-INST | 2021-11-14 | 15:00 | 2021-11-18 | WPM | C | I | 2021-11-17 | 13:00 | Business Critical | 2400151280 | 0012 | 6M INST. + UTILITY AIR DRYER, GC-D-901 A | MICROFILTER, GC-F-901 | 1 | 5 |  | Hold Step | 8.5 | 8.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-D-901A | AIR DRYER FOR INSTR AND UTILITY AIR |  | 2021-10-30
| MTN-INST | 2021-11-08 | 7:00 | 2021-11-27 | WPM | C | V | 2021-11-10 | 13:00 | Business Critical | 2400157244 | 0010 | 6M BAKER PANEL - GOA | BEMÆRK! | 1 | 5 |  |  | 7.5 | 7.5 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /A /07/WELLHEAD-CONTROL-PANEL | WELLHEAD CONTROL PANEL | NOSD | 2021-11-08
| MTN-INST | 2021-11-10 | 13:00 | 2021-11-27 | WPM | C | V | 2021-11-11 | 9:00 | Business Critical | 2400157244 | 0012 | 6M BAKER PANEL - GOA | BEMÆRK! | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /A /07/WELLHEAD-CONTROL-PANEL | WELLHEAD CONTROL PANEL | NOSD | 2021-11-08
| MTN-INST | 2021-11-08 | 7:00 | 2021-12-05 | WPM | A | V | 2021-11-12 | 15:00 | Assurance | 2400157372 | 0010 | 1Y INSTRUMENTER, GAS SHIPPING LINE | INSTRUMENTER, GAS SHIPPING LINE | 1 | 3 |  |  | 14 | 14 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /03/ESD-SYSTEM | ESD SYSTEM | NOSD | 2021-11-05
| MTN-INST | 2021-11-09 | 15:00 | 2021-12-03 | WPM | A | I | 2021-11-11 | 11:00 | Assurance | 2400157373 | 0012 | 1Y PRODUCED WATER BOOSTER PUMP | TL-PRODUCED WATER BOOSTER PUMP | 1 | 3 |  |  | 5 | 5 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /54/GOFA-P-5009 | DMA PROD. WTR PUMP ECCENTRIC SCREW PUMP | NOSD | 2021-11-03
| MTN-INST | 2021-11-21 | 11:00 | 2021-12-01 | WPM | C | V | 2021-11-23 | 15:00 | Business Critical | 2400157448 | 0012 | 6M RÅOLIE SHIPPING PUMPE - GEA-P-117E | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  |  | 7 | 7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-P-117E | CRUDE OIL EXPORT PUMP |  | 2021-11-12
| MTN-INST | 2021-11-10 | 7:00 | 2021-12-03 | WPM | C | S | 2021-11-11 | 19:00 | Business Critical | 2400157450 | 0020 | 3Y KLOAKBEHANDLINGSENHED, GC-M-900 | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 6 | 6 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-M-900 | SEWAGE TREATMENT PLANT | NOSD | 2021-09-20
| MTN-INST | 2021-11-30 | 15:00 | 2021-12-11 | WPM | C | V | 2021-12-02 | 17:00 | Business Critical | 2400157568 | 0012 | 6M RÅOLIE SHIPPING PUMPE - GEA-P-117F | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  |  | 6.5 | 6.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-P-117F | CRUDE OIL EXPORT PUMP |  | 2021-11-22
| MTN-INST | 2021-11-19 | 7:00 | 2021-12-19 | WPM | A | V | 2021-11-21 | 15:00 | Assurance | 2400160566 | 0010 | 1Y FIRE DAMPER GOC LAGGERVAERKSTED | TL-1Y, FIRE DAMPER GOC LAGGERVAERKSTED | 1 | 3 |  |  | 8 | 8 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-11-19
| MTN-INST | 2021-12-09 | 11:00 | 2021-12-23 | WPM | C | V | 2021-12-10 | 15:00 | Business Critical | 2400160567 | 0012 | 6M RÅOLIE SHIPPING PUMPE - GEA-P-117G | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-P-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-12-04
| MTN-MECH | 2021-11-08 | 7:00 | 2019-09-22 | WDF | 4 | S | 2021-11-08 | 11:00 | 4.Within 2 Months | 2100022413 | 0010 | Replace 300 Bar hoses GOFA-A-5417 | Isolate system | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /02/GOFA-A-5417 | PRESSURE REDUCTION STATION | NOSD | 2019-08-13
| MTN-MECH | 2021-11-08 | 11:00 | 2019-09-22 | WDF | 4 | S | 2021-11-09 | 11:00 | 4.Within 2 Months | 2100022413 | 0020 | Replace 300 Bar hoses GOFA-A-5417 | Replace hoses | 1 | 7 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /02/GOFA-A-5417 | PRESSURE REDUCTION STATION | NOSD | 2019-08-13
| MTN-MECH | 2021-11-09 | 11:00 | 2019-09-22 | WDF | 4 | S | 2021-11-09 | 15:00 | 4.Within 2 Months | 2100022413 | 0030 | Replace 300 Bar hoses GOFA-A-5417 | De-isolate | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /02/GOFA-A-5417 | PRESSURE REDUCTION STATION | NOSD | 2019-08-13
| MTN-MECH | 2021-11-08 | 9:00 | 2019-12-13 | WDF | 4 |  | 2021-11-08 | 17:00 | 4.Within 2 Months | 2100022548 | 0020 | Stuck hcv on bypass for fe-50288 gof | Skift adaptor | 2 | 7 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | NE | 2019-11-03
| MTN-MECH | 2021-11-10 | 7:00 | 2019-12-05 | WDF | 4 |  | 2021-11-17 | 19:00 | 4.Within 2 Months | 2100022553 | 0010 | Order+install new dishwasher+Gorm | Order and install new dishwasher. | 1 | 7 | SR | Keep in plan | 24 | 24 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2019-10-26
| MTN-MECH | 2021-11-08 | 13:00 | 2019-11-17 | WDF | 4 | V | 2021-11-10 | 17:00 | 4.Within 2 Months | 2100022637 | 0020 | CMAT:Replace defective valve on GE-EMS-0 | L2 Replace defective valve | 1 | 6 |  | Hold/CMAT | 7 | 7 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /E /02/GE-EMS-0601 | SAFETY SHOWER WITH EYEBATH | NOSD | 2019-10-08
| MTN-MECH | 2021-11-09 | 11:00 | 2019-05-12 | WDF | 4 | V | 2021-11-10 | 11:00 | 4.Within 2 Months | 2100022717 | 0030 | Replace XCV-0519 Actuator it's possibel | Replace actuator XCV-0511 | 2 | 6 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-XCV-0511 | INSTRUMENT AIR TO IP GAS COMPR. | NOSD | 2019-04-02
| MTN-MECH | 2021-11-11 | 17:00 | 2019-05-12 | WDF | 4 | V | 2021-11-12 | 17:00 | 4.Within 2 Months | 2100022717 | 0075 | Replace XCV-0519 Actuator it's possibel | Test, paperwork and close out | 1 | 6 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-XCV-0511 | INSTRUMENT AIR TO IP GAS COMPR. | NOSD | 2019-04-02
| MTN-MECH | 2021-11-13 | 13:00 | 2019-05-12 | WDF | 4 | V | 2021-11-13 | 17:00 | 4.Within 2 Months | 2100022717 | 0085 | Replace XCV-0519 Actuator it's possibel | Prep. for backload | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-XCV-0511 | INSTRUMENT AIR TO IP GAS COMPR. | NOSD | 2019-04-02
| MTN-MECH | 2021-11-08 | 13:00 | 2019-06-07 | WDF | 4 | S | 2021-11-11 | 17:00 | 4.Within 2 Months | 2100022775 | 0020 | CMAT:LG-50013 extern leak | Remove level glass | 1 | 7 |  | Hold/CMAT | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-LG-50013 | LEVEL GLASS, HYDROCARBON DRAINS | NOSD | 2019-04-28
| MTN-MECH | 2021-11-09 | 13:00 | 2019-06-07 | WDF | 4 | S | 2021-11-12 | 17:00 | 4.Within 2 Months | 2100022775 | 0050 | CMAT:LG-50013 extern leak | Mount Level glass | 1 | 7 |  | Hold/CMAT | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-LG-50013 | LEVEL GLASS, HYDROCARBON DRAINS | NOSD | 2019-04-28
| MTN-MECH | 2021-12-01 | 11:00 | 2019-08-09 | WDF | 5 | V | 2021-12-03 | 11:00 | 5.Within 4 Months | 2100022789 | 0020 | GC-PSV-0231A replace | Replace PSV-0231A | 1 | 6 | Mat status await SR | HOLD/PSV STPO0 | 6 | 6 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC | GO /C /30/GC-PSV-0231A | PRESSURE SAFETY VALVE | NOSD | 2019-05-11
| MTN-MECH | 2021-12-01 | 11:00 | 2019-08-09 | WDF | 5 | V | 2021-12-03 | 11:00 | 5.Within 4 Months | 2100022791 | 0020 | GC-PSV-0231B replace | Replace PSV-0231B | 1 | 6 | Mat status await SR | HOLD/PSV STPO0 | 6 | 6 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC | GO /C /30/GC-PSV-0231B | PRESSURE SAFETY VALVE | NOSD | 2019-05-11
| MTN-MECH | 2021-11-08 | 7:00 | 2019-09-17 | WDF | 5 | V | 2021-11-13 | 19:00 | 5.Within 4 Months | 2100022933 | 0010 | Re-locate deluge pipe supports on Aviati | Modify supports in workshop | 1 | 6 |  |  | 18 | 18 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC CSER MANC NMAT | GO /C /81 | HELIDECK (INCLUDING KEROSENE) | NOSD | 2019-06-19
| MTN-MECH | 2021-11-14 | 7:00 | 2019-09-17 | WDF | 5 | V | 2021-11-18 | 15:00 | 5.Within 4 Months | 2100022933 | 0020 | Re-locate deluge pipe supports on Aviati | Mount Supports | 1 | 6 |  |  | 14 | 14 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC CSER MANC NMAT | GO /C /81 | HELIDECK (INCLUDING KEROSENE) | NOSD | 2019-06-19
| MTN-MECH | 2021-11-08 | 11:00 | 2020-01-07 | WDF | 3 | I | 2021-11-09 | 11:00 | 3.Intermedt 1 Month | 2100023002 | 0020 | HCV Upstream PCV-0102 is stuck | mount gearbox | 1 | 4 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /31/GC-PCV-0102 | SEAWATER TO LUBE OIL COOLER FOR C-204B | NE | 2019-12-18
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-04 | WDF | 4 | V | 2021-11-08 | 19:00 | 4.Within 2 Months | 2100023034 | 0040 | GC-G-810 missing exhaust insulation | measure, draw and order missing exhaust | 1 | 6 | Aligne 810? |  | 3 | 3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /05/GC-G-810 | EMERGENCY GENERATOR | NOSD | 2019-12-26
| MTN-MECH | 2021-11-09 | 13:00 | 2020-02-04 | WDF | 4 | V | 2021-11-13 | 13:00 | 4.Within 2 Months | 2100023034 | 0060 | GC-G-810 missing exhaust insulation | mount missing exhaust isolation | 1 | 6 | Aligne 810? |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /05/GC-G-810 | EMERGENCY GENERATOR | NOSD | 2019-12-26
| MTN-MECH | 2021-12-24 | 7:00 | 2020-06-22 | WDF | 6 |  | 2021-12-24 | 11:00 | 6.Within 8 Months | 2100023311 | 0010 | Kitchen table/sink to be replaced | Uninstall watersupply and drain | 2 | 7 | Await drawer and mat | Pick-pack | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2020-01-24
| MTN-MECH | 2021-12-24 | 11:00 | 2020-06-22 | WDF | 6 |  | 2021-12-24 | 15:00 | 6.Within 8 Months | 2100023311 | 0020 | Kitchen table/sink to be replaced | Replace table with new model | 2 | 7 | Await drawer and mat | Pick-pack | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2020-01-24
| MTN-MECH | 2021-12-24 | 15:00 | 2020-06-22 | WDF | 6 |  | 2021-12-25 | 11:00 | 6.Within 8 Months | 2100023311 | 0030 | Kitchen table/sink to be replaced | Install faucet and drains - cleanup | 2 | 7 | Await drawer and mat | Pick-pack | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2020-01-24
| MTN-MECH | 2021-12-01 | 13:16 | 2020-01-28 | WDF | 4 | V | 2021-12-01 | 13:16 | 4.Within 2 Months | 2100023331 | 0030 | Replace bearings in GC-P-101C | Exchange pump | 2 | 2 | /RCE | 130921/Awating new spares | 0 | 6 | 12 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-P-101C | CRUDE OIL BUSTER PUMP | NOSD | 2019-12-19
| MTN-MECH | 2021-12-01 | 13:16 | 2020-01-28 | WDF | 4 | V | 2021-12-02 | 9:16 | 4.Within 2 Months | 2100023331 | 0040 | Replace bearings in GC-P-101C | Alignment of pump & motor | 2 | 2 | /RCE | 130921/Awating new spares | 4 | 4 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-P-101C | CRUDE OIL BUSTER PUMP | NOSD | 2019-12-19
| MTN-MECH | 2021-12-01 | 18:52 | 2020-01-28 | WDF | 4 | V | 2021-12-02 | 14:52 | 4.Within 2 Months | 2100023331 | 0050 | Replace bearings in GC-P-101C | Install coupling | 2 | 2 | /RCE | 130921/Awating new spares | 4 | 4 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-P-101C | CRUDE OIL BUSTER PUMP | NOSD | 2019-12-19
| MTN-MECH | 2021-11-08 | 7:00 | 2018-05-08 | WDF | 4 | I | 2021-11-11 | 19:00 | 4.Within 2 Months | 2100023460 | 0020 | GOA sumptank pump doesn't work | Make a temporary and bigger air supply | 1 | 6 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /A /28/GA-P-305 | SUMP PUMP | NOSD | 2018-03-29
| MTN-MECH | 2021-11-12 | 7:00 | 2018-05-08 | WDF | 4 | I | 2021-11-12 | 15:00 | 4.Within 2 Months | 2100023460 | 0030 | GOA sumptank pump doesn't work | Design and do isolation | 1 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /A /28/GA-P-305 | SUMP PUMP | NOSD | 2018-03-29
| MTN-MECH | 2021-11-12 | 15:00 | 2018-05-08 | WDF | 4 | I | 2021-11-14 | 15:00 | 4.Within 2 Months | 2100023460 | 0040 | GOA sumptank pump doesn't work | Test pump | 1 | 6 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /A /28/GA-P-305 | SUMP PUMP | NOSD | 2018-03-29
| MTN-MECH | 2021-12-30 | 13:00 | 2019-05-07 | WDF | 6 | V | 2022-01-01 | 9:00 | 6.Within 8 Months | 2100023624 | 0020 | SMAT:REPL 1" Corroded valve Skjold impo | Replace 1" valve Skjold import | 1 | 7 |  |  | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2018-12-08
| MTN-MECH | 2021-11-08 | 7:00 | 2018-09-20 | WDF | 5 | V | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100023758 | 0010 | SMAT:DC8 Replace 12" Butterfly valve | Design and do isolation/inhibits CCR | 1 | 6 | Control Tower Change |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2018-06-22
| MTN-MECH | 2021-11-09 | 7:00 | 2018-09-20 | WDF | 5 | V | 2021-11-10 | 19:00 | 5.Within 4 Months | 2100023758 | 0020 | SMAT:DC8 Replace 12" Butterfly valve | Rigging assistance to replace 12" valve | 1 | 6 | Control Tower Change |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2018-06-22
| MTN-MECH | 2021-11-11 | 7:00 | 2018-09-20 | WDF | 5 | V | 2021-11-14 | 19:00 | 5.Within 4 Months | 2100023758 | 0030 | SMAT:DC8 Replace 12" Butterfly valve | Replace butterfly valve | 2 | 7 | Control Tower Change |  | 24 | 24 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2018-06-22
| MTN-MECH | 2021-11-15 | 7:00 | 2018-09-20 | WDF | 5 | V | 2021-11-15 | 19:00 | 5.Within 4 Months | 2100023758 | 0040 | SMAT:DC8 Replace 12" Butterfly valve | De-isolate, repeal inhibits | 1 | 7 | Control Tower Change |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2018-06-22
| MTN-MECH | 2021-11-16 | 7:00 | 2018-09-20 | WDF | 5 | V | 2021-11-16 | 19:00 | 5.Within 4 Months | 2100023758 | 0050 | SMAT:DC8 Replace 12" Butterfly valve | Test, QC and close out | 1 | 7 | Control Tower Change |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2018-06-22
| MTN-MECH | 2021-11-17 | 7:00 | 2018-09-20 | WDF | 5 | V | 2021-11-18 | 19:00 | 5.Within 4 Months | 2100023758 | 0060 | SMAT:DC8 Replace 12" Butterfly valve | Rigging assistance | 1 | 7 | Control Tower Change |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NOSD | 2018-06-22
| MTN-MECH | 2021-11-08 | 13:00 | 2018-11-07 | WDF | 5 | I | 2021-11-11 | 9:00 | 5.Within 4 Months | 2100023781 | 0020 | Replace gasket at flange on F-402C | Replace Gasket | 1 | 6 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /51/GC-XCV-5303 | COOLING WATER FILTERS | NOSD | 2018-08-09
| MTN-MECH | 2021-11-11 | 15:00 | 2018-11-07 | WDF | 5 | I | 2021-11-12 | 11:00 | 5.Within 4 Months | 2100023781 | 0040 | Replace gasket at flange on F-402C | Test, QC and close out | 1 | 7 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /51/GC-XCV-5303 | COOLING WATER FILTERS | NOSD | 2018-08-09
| MTN-MECH | 2021-11-08 | 7:00 | 2018-04-20 | WDF | 6 | S | 2021-11-15 | 11:00 | 6.Within 8 Months | 2100023877 | 0010 | Hul på rør fra V-3909 | Hul på rør fra V-3909 | 1 | 7 |  |  | 22 | 24 | 2 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /75/GOFD-V-3909 | ANTI-FOAM STORAGE TANK | NOSD | 2017-11-21
| MTN-MECH | 2021-11-08 | 11:00 | 2019-07-25 | WDF | 6 | V | 2021-11-10 | 11:00 | 6.Within 8 Months | 2100023932 | 0020 | Replace DP indicator GOFA-PDI-35028 | Replace DP-ind. & Isol. valve | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /F /53/GOFA-V-3501 | DEAERATOR | NOSD | 2019-02-25
| MTN-MECH | 2021-11-10 | 12:36 | 2019-07-25 | WDF | 6 | V | 2021-11-11 | 8:36 | 6.Within 8 Months | 2100023932 | 0040 | Replace DP indicator GOFA-PDI-35028 | Test, paperwork and close out | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /F /53/GOFA-V-3501 | DEAERATOR | NOSD | 2019-02-25
| MTN-MECH | 2021-11-08 | 11:00 | 2019-06-04 | WDF | 5 | I | 2021-11-09 | 11:00 | 5.Within 4 Months | 2100024058 | 0020 | CMAT:Install filter in strainer GOFA-P-3 | Install filter | 1 | 6 |  | Hold/CMAT | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-P-3905 | SODIUM HYPOCHLORITE PUMP, 50 L/HR | NOSD | 2019-03-06
| MTN-MECH | 2021-11-08 | 13:00 | 2019-02-15 | WDF | 4 | I | 2021-11-10 | 13:00 | 4.Within 2 Months | 2100024117 | 0020 | SMAT:Replace drip ring | Replace Drip ring | 1 | 6 | Y HJA - long txt |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /72/GOFA-PSV-11012B | HEATING MEDIUM EXPANSION V-1101 | NOSD | 2019-01-06
| MTN-MECH | 2021-11-08 | 12:00 | 2016-01-29 | WDF | 4 | I | 2021-11-12 | 12:00 | 4.Within 2 Months | 2100024470 | 0010 | SMAT: Utæt pakdåse på LCV-36094B | Utæt pakdåse på LCV-36094B | 1 | 6 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /21/GEB-LCV-36094B | LEVEL CONTROL VALVE | NOSD | 2015-12-20
| MTN-MECH | 2021-11-08 | 0:00 | 2019-05-31 | WDF | 3 | I | 2021-11-08 | 24:00 | 3.Intermedt 1 Month | 2100025573 | 0160 | Pull Cooling water pump GOFA-P-5301 | Test pump (FRAMO) | 1 | 8 | RCE/awating 2100042857 | (2)Await 2100042857/SMAT | 3 | 8 | 5 | APPR CMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /F /76/GOFA-P-5301 | COOLING/SERVICE WATER PUMP | NOSD | 2019-05-11
| MTN-MECH | 2021-11-08 | 11:00 | 2019-09-01 | WDF | 4 | I | 2021-11-10 | 11:00 | 4.Within 2 Months | 2100025603 | 0020 | Replace GEM-Pcv-39170 | Replace PCV | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /75/GEM-PCV-39170 | PRESSURE CONTROL VALVE FOR P-3919 | NOSD | 2019-07-23
| MTN-MECH | 2021-11-10 | 15:00 | 2019-09-01 | WDF | 4 | I | 2021-11-11 | 15:00 | 4.Within 2 Months | 2100025603 | 0040 | Replace GEM-Pcv-39170 | Test, paperwork and close-out | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /75/GEM-PCV-39170 | PRESSURE CONTROL VALVE FOR P-3919 | NOSD | 2019-07-23
| MTN-MECH | 2021-11-08 | 11:00 | 2019-09-01 | WDF | 4 | I | 2021-11-10 | 11:00 | 4.Within 2 Months | 2100025604 | 0020 | Replace GEM-Pcv-39171 | Replace PCV | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /75/GEM-PCV-39171 | PRESSURE CONTROL VALVE FOR P-3919 | NOSD | 2019-07-23
| MTN-MECH | 2021-11-10 | 15:00 | 2019-09-01 | WDF | 4 | I | 2021-11-11 | 15:00 | 4.Within 2 Months | 2100025604 | 0040 | Replace GEM-Pcv-39171 | Test, paperwork and close-out | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /75/GEM-PCV-39171 | PRESSURE CONTROL VALVE FOR P-3919 | NOSD | 2019-07-23
| MTN-MECH | 2021-12-31 | 11:00 | 2019-11-09 | WDF | 5 | I | 2022-01-01 | 19:00 | 5.Within 4 Months | 2100025634 | 0020 | Replace mambrane in GC-P-0287A | Replace Membrane | 1 | 6 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-P-0287A | ANTI-FOAM PUMP | NOSD | 2019-08-11
| MTN-MECH | 2021-11-08 | 17:00 | 2020-01-29 | WDF | 3 | V | 2021-11-09 | 13:00 | 3.Intermedt 1 Month | 2100025637 | 0030 | GEA-PM-117D Trouble shoot noise from blo | Dismantle ventilation duct | 2 | 4 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-MECH | 2021-11-10 | 8:00 | 2020-01-29 | WDF | 3 | V | 2021-11-10 | 14:00 | 3.Intermedt 1 Month | 2100025637 | 0050 | GEA-PM-117D Trouble shoot noise from blo | Check blower for damage & repair if poss | 2 | 4 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-MECH | 2021-11-10 | 18:00 | 2020-01-29 | WDF | 3 | V | 2021-11-11 | 14:00 | 3.Intermedt 1 Month | 2100025637 | 0070 | GEA-PM-117D Trouble shoot noise from blo | Mount ventilation duct | 2 | 4 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-MECH | 2021-11-10 | 18:00 | 2019-04-01 | WDF | 6 | I | 2021-11-11 | 14:00 | 6.Within 8 Months | 2100025685 | 0040 | SMAT:Ventilatordæksel på El-motor rusten | Remove motor | 2 | 6 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEA-PM-3931 | PUMP ELECTRIC MOTOR FOR P-3931 | NOSD | 2018-11-02
| MTN-MECH | 2021-11-11 | 8:00 | 2019-04-01 | WDF | 6 | I | 2021-11-11 | 16:00 | 6.Within 8 Months | 2100025685 | 0060 | SMAT:Ventilatordæksel på El-motor rusten | Install motor | 2 | 6 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEA-PM-3931 | PUMP ELECTRIC MOTOR FOR P-3931 | NOSD | 2018-11-02
| MTN-MECH | 2021-11-09 | 15:00 | 2018-04-29 | WDF | 3 | S | 2021-11-13 | 15:00 | 3.Intermedt 1 Month | 2100025689 | 0030 | GORM F. H2S SCAVENGER TANK T-3902 | Fabricate and replace support bracket. | 1 | 4 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /75/GOFB-T-3902 | H2S SCAVENGER TANK | NOSD | 2018-04-09
| MTN-MECH | 2021-11-14 | 11:00 | 2018-04-29 | WDF | 3 | S | 2021-11-14 | 15:00 | 3.Intermedt 1 Month | 2100025689 | 0050 | GORM F. H2S SCAVENGER TANK T-3902 | Document performed work | 1 | 4 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /75/GOFB-T-3902 | H2S SCAVENGER TANK | NOSD | 2018-04-09
| MTN-MECH | 2021-11-08 | 7:00 | 2019-01-23 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100025699 | 0010 | Backload BA station GOFC-AB-0688 for ser | Disconnect and backload BA station. | 1 | 6 | 2100025698 to be comp 1st |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/GOFC-AB-0628 | BREATHING AIR MANIFOLD | NOSD | 2018-10-25
| MTN-MECH | 2021-11-08 | 7:00 | 2019-01-23 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100025700 | 0010 | Backload BA station GOFC-AB-0641 for ser | Disconnect and backload BA station. | 1 | 6 | 2100025699 to be comp 1st |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/GOFC-AB-0641 | BREATHING AIR MANIFOLD | NOSD | 2018-10-25
| MTN-MECH | 2021-11-10 | 15:00 | 2019-01-23 | WDF | 5 | V | 2021-11-13 | 11:00 | 5.Within 4 Months | 2100025700 | 0020 | Backload BA station GOFC-AB-0641 for ser | Reinstall BA station | 1 | 6 | 2100025699 to be comp 1st |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/GOFC-AB-0641 | BREATHING AIR MANIFOLD | NOSD | 2018-10-25
| MTN-MECH | 2021-11-08 | 7:00 | 2019-01-23 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100025701 | 0010 | Backload BA station GOFC-AB-0642 for ser | Disconnect and backload BA station. | 1 | 6 | 2100025700 to be comp 1st |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/GOFC-AB-0642 | BREATHING AIR MANIFOLD | NOSD | 2018-10-25
| MTN-MECH | 2021-11-10 | 15:00 | 2019-01-23 | WDF | 5 | V | 2021-11-13 | 11:00 | 5.Within 4 Months | 2100025701 | 0020 | Backload BA station GOFC-AB-0642 for ser | Reinstall BA station | 1 | 6 | 2100025700 to be comp 1st |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/GOFC-AB-0642 | BREATHING AIR MANIFOLD | NOSD | 2018-10-25
| MTN-MECH | 2021-11-08 | 7:00 | 2018-12-01 | WDF | 5 | I | 2021-11-11 | 19:00 | 5.Within 4 Months | 2100025740 | 0050 | Demount GOFA-P-3907 for refurb & return. | Mount pump, gear & motor. | 1 | 6 |  |  | 12 | 12 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /75/GOFA-P-3907 | OXYGEN SCAVENGER PUMP | NOSD | 2018-09-02
| MTN-MECH | 2021-12-12 | 7:00 | 2018-12-01 | WDF | 5 | I | 2021-12-13 | 19:00 | 5.Within 4 Months | 2100025740 | 0052 | Demount GOFA-P-3907 for refurb & return. | Drauftsman to create dwg for pipe | 1 | 6 | /OTL/Awat SR | Hold Step | 6 | 6 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /75/GOFA-P-3907 | OXYGEN SCAVENGER PUMP | NOSD | 2018-09-02
| MTN-MECH | 2021-11-08 | 7:00 | 2018-12-01 | WDF | 5 | I | 2021-11-08 | 11:00 | 5.Within 4 Months | 2100025740 | 0070 | Demount GOFA-P-3907 for refurb & return. | additional mat | 1 | 6 |  |  | 1 | 1 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /75/GOFA-P-3907 | OXYGEN SCAVENGER PUMP | NOSD | 2018-09-02
| MTN-MECH | 2021-11-13 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-14 | 19:00 | 6.Within 8 Months | 2100025750 | 0030 | Exchange ESDV-33052 | Dismantle valve | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-MECH | 2021-11-20 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-21 | 19:00 | 6.Within 8 Months | 2100025750 | 0050 | Exchange ESDV-33052 | Install new valve | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-MECH | 2021-11-11 | 11:00 | 2020-01-04 | WDF | 3 | I | 2021-11-24 | 15:00 | 3.Intermedt 1 Month | 2100025766 | 0040 | GOFA-P-5002B Leak closed drain pump, pum | Replace GOFA-P-5002B | 1 | 4 |  | Hold Step | 40 | 40 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-P-5002B | PUMP | NOSD | 2019-12-15
| MTN-MECH | 2021-11-13 | 17:00 | 2018-09-12 | WDF | 6 | S | 2021-11-17 | 17:00 | 6.Within 8 Months | 2100025769 | 0040 | CMAT:RW Repair broken connection/fitting | Replace LG-50294 | 1 | 7 | No planning General job | No planning General job | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /27/GOFB-LG-50294 | GAUGEREJECT COLLE.VESSEL V-5008 | NOSD | 2018-04-15
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-08 | 7:00 | 8.Longer than 1 Year | 2100025771 | 0010 | SMAT:Bleed ventil defekt på drip ring | Bleed ventil defekt på drip ring | 1 | 6 |  |  | 0 | 8 | 10 | APPR RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /F /72/GOFA-PSV-11020B | FIRED HEATER LEVEL 1 | NOSD | 2018-02-27
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-11 | 11:00 | 8.Longer than 1 Year | 2100025772 | 0010 | GC-PSV-02168B Up&ned strøms bleed ventil | Up og ned strøms bleed ventiler defekt | 1 | 6 |  | Hold Step | 10 | 12 | 2 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-09 | 19:00 | 8.Longer than 1 Year | 2100025772 | 0020 | GC-PSV-02168B Up&ned strøms bleed ventil | Rig-up scaffold, access to PSV-02168A/B | 3 | 6 |  | Hold Step | 18 | 18 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-10 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-10 | 19:00 | 8.Longer than 1 Year | 2100025772 | 0030 | GC-PSV-02168B Up&ned strøms bleed ventil | Rig-up hoist | 2 | 6 |  | Hold Step | 6 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-11 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-11 | 19:00 | 8.Longer than 1 Year | 2100025772 | 0040 | GC-PSV-02168B Up&ned strøms bleed ventil | Isolate PS-02168A/B | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-12 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-13 | 11:00 | 8.Longer than 1 Year | 2100025772 | 0050 | GC-PSV-02168B Up&ned strøms bleed ventil | Remove small valves in old drip rings | 2 | 6 |  | Hold Step | 8 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-13 | 11:00 | 2020-02-17 | WDF | 8 | I | 2021-11-14 | 19:00 | 8.Longer than 1 Year | 2100025772 | 0060 | GC-PSV-02168B Up&ned strøms bleed ventil | Replace drip rings either side of PSV's | 2 | 6 |  | Hold Step | 10 | 10 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-15 | 7:00 | 2020-02-17 | WDF | 8 | I | 2021-11-16 | 11:00 | 8.Longer than 1 Year | 2100025772 | 0070 | GC-PSV-02168B Up&ned strøms bleed ventil | Re-install small valves again | 2 | 6 |  | Hold Step | 8 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-16 | 11:00 | 2020-02-17 | WDF | 8 | I | 2021-11-17 | 11:00 | 8.Longer than 1 Year | 2100025772 | 0080 | GC-PSV-02168B Up&ned strøms bleed ventil | De-isolate PSV-02168A/B | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-17 | 11:00 | 2020-02-17 | WDF | 8 | I | 2021-11-18 | 11:00 | 8.Longer than 1 Year | 2100025772 | 0090 | GC-PSV-02168B Up&ned strøms bleed ventil | Rig-down hoist | 2 | 6 |  | Hold Step | 6 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-18 | 11:00 | 2020-02-17 | WDF | 8 | I | 2021-11-19 | 19:00 | 8.Longer than 1 Year | 2100025772 | 0100 | GC-PSV-02168B Up&ned strøms bleed ventil | Rig-down scaffold and clean area | 3 | 6 |  | Hold Step | 15 | 15 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /23/GC-PSV-02168B | PRESSURE SAFETY VALVE | NOSD | 2018-02-27
| MTN-MECH | 2021-11-08 | 7:00 | 2020-08-01 | WDF | 8 | S | 2021-11-09 | 11:00 | 8.Longer than 1 Year | 2100026163 | 0010 | CMAT:Mount new operation hand wheel on H | Mount new handles on HCV. | 1 | 7 |  | Hold/CMAT | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /C /26/GC-HCV-02955 | HCV SLAVE STREAM 1 OUTLET | NOSD | 2018-08-12
| MTN-MECH | 2021-11-10 | 7:00 | 2018-09-08 | WDF | 6 | I | 2021-11-10 | 15:00 | 6.Within 8 Months | 2100026506 | 0010 | Jobs efter eftersyn på V-907 | Prep. permit, spareparts, tools, Toolbox | 1 | 6 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEM-V-907 | AIR RECEIVER INSTR. AND UTILITY AIR | NOSD | 2018-04-11
| MTN-MECH | 2021-11-11 | 11:00 | 2018-09-08 | WDF | 6 | I | 2021-11-12 | 11:00 | 6.Within 8 Months | 2100026506 | 0030 | Jobs efter eftersyn på V-907 | Change to coorect bolts | 1 | 6 |  |  | 3 | 3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEM-V-907 | AIR RECEIVER INSTR. AND UTILITY AIR | NOSD | 2018-04-11
| MTN-MECH | 2021-11-12 | 11:00 | 2018-09-08 | WDF | 6 | I | 2021-11-13 | 15:00 | 6.Within 8 Months | 2100026506 | 0040 | Jobs efter eftersyn på V-907 | Replace Flange - 150# | 1 | 6 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEM-V-907 | AIR RECEIVER INSTR. AND UTILITY AIR | NOSD | 2018-04-11
| MTN-MECH | 2021-11-15 | 7:00 | 2018-09-08 | WDF | 6 | I | 2021-11-15 | 15:00 | 6.Within 8 Months | 2100026506 | 0060 | Jobs efter eftersyn på V-907 | Test, QC and close out | 1 | 6 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEM-V-907 | AIR RECEIVER INSTR. AND UTILITY AIR | NOSD | 2018-04-11
| MTN-MECH | 2021-11-08 | 7:00 | 2017-05-23 | WDF | 5 | S | 2021-11-08 | 7:00 | 5.Within 4 Months | 2100027027 | 0010 | R Check af Exd kapslinger (GOFA-FP-1101) | Check af Exd kapslinger | 1 | 7 |  |  | 0 | 38 | 38 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /72/GOFA-FP-1101 | FIELD PANEL FOR FIRED HEATER | NOSD | 2017-02-22
| MTN-MECH | 2021-11-08 | 7:00 | 2016-01-27 | WDF | 4 | V | 2021-11-08 | 7:00 | 4.Within 2 Months | 2100027038 | 0010 | SMAT:R skift orifice GA-FE-121021 GAN 60 | skift af orife GA-FE-121021 GAN 60 | 1 | 6 |  |  | 0 | 8 | 8 | APPR RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /A /37/GA-FE-121021 | FLOW ELEMENT (METERING) SPP-2"-36-102-GY | NOSD | 2015-12-18
| MTN-MECH | 2021-11-08 | 11:00 | 2016-10-15 | WDF | 3 | I | 2021-11-09 | 19:00 | 3.Intermedt 1 Month | 2100027088 | 0010 | PM-3911A does not sound well the be | PM-3911A lyder ikke godt i lejerne | 1 | 4 |  | Hold Step | 5 | 12 | 7 | APPR CMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /F /75/GOFB-PM-3911A | DRIVER FOR WTR CLARIFIER INJECTION PUMP | NOSD | 2016-09-25
| MTN-MECH | 2021-11-08 | 7:00 | 2018-02-12 | WDF | 5 | V | 2021-11-08 | 7:00 | 5.Within 4 Months | 2100027131 | 0010 | Montering af gc-psv-0532+drip ring | RW - montering af gc-psv-0532 | 1 | 6 |  |  | 0 | 1 | 1 | APPR SECE SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /C /32/GC-PSV-0532 | PRESSURE SAFETY VALVE GAS COMPRESSION HP | NOSD | 2017-11-14
| MTN-MECH | 2021-11-08 | 11:00 | 2018-02-12 | WDF | 5 | V | 2021-11-08 | 15:00 | 5.Within 4 Months | 2100027131 | 0030 | Montering af gc-psv-0532+drip ring | Klargør værktøj & permit, afhold toolbox | 2 | 6 |  |  | 2 | 2 | 0 | APPR SECE SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /C /32/GC-PSV-0532 | PRESSURE SAFETY VALVE GAS COMPRESSION HP | NOSD | 2017-11-14
| MTN-MECH | 2021-11-09 | 7:00 | 2018-02-12 | WDF | 5 | V | 2021-11-09 | 15:00 | 5.Within 4 Months | 2100027131 | 0040 | Montering af gc-psv-0532+drip ring | montering af PSV & dripring | 2 | 6 |  |  | 4 | 4 | 0 | APPR SECE SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /C /32/GC-PSV-0532 | PRESSURE SAFETY VALVE GAS COMPRESSION HP | NOSD | 2017-11-14
| MTN-MECH | 2021-11-10 | 7:00 | 2018-02-12 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100027131 | 0060 | Montering af gc-psv-0532+drip ring | Oprydning & Qc / close out | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /C /32/GC-PSV-0532 | PRESSURE SAFETY VALVE GAS COMPRESSION HP | NOSD | 2017-11-14
| MTN-MECH | 2021-11-08 | 7:00 | 2018-05-24 | WDF | 6 | V | 2021-11-08 | 7:00 | 6.Within 8 Months | 2100027137 | 0020 | SMAT:GC-PSV-0519 overdue | PSV TO BE INSTALLED AFTER ONSHORE RECAL | 1 | 6 |  |  | 0 | 6 | 9 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC MANC | GO /C /32/GC-PSV-0519 | M,5,L, V-202C SCRUBBER | NOSD | 2017-12-25
| MTN-MECH | 2021-11-08 | 7:00 | 2019-08-10 | WDF | 4 | V | 2021-11-08 | 11:00 | 4.Within 2 Months | 2100027669 | 0010 | Repair XCV EMS-06449-failed to close | Isolate system | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /02/GC-EMS-06449 | SAFETY SHOWER WITH EYEBATH | NOSD | 2019-07-01
| MTN-MECH | 2021-11-08 | 11:00 | 2019-08-10 | WDF | 4 | V | 2021-11-10 | 19:00 | 4.Within 2 Months | 2100027669 | 0020 | Repair XCV EMS-06449-failed to close | Fault find on XCV-06449 | 1 | 6 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /02/GC-EMS-06449 | SAFETY SHOWER WITH EYEBATH | NOSD | 2019-07-01
| MTN-MECH | 2021-11-11 | 7:00 | 2019-08-10 | WDF | 4 | V | 2021-11-11 | 11:00 | 4.Within 2 Months | 2100027669 | 0030 | Repair XCV EMS-06449-failed to close | De-isolate system | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /02/GC-EMS-06449 | SAFETY SHOWER WITH EYEBATH | NOSD | 2019-07-01
| MTN-MECH | 2021-11-08 | 7:00 | 2042-12-31 | WDF | 6 | I | 2021-11-08 | 7:00 | 6.Within 8 Months | 2100028028 | 0010 | Removal GOFA-PSV-34056A/B | Removal of GOFA-PSV-34056A/B | 1 | 6 |  |  | 0 | 4 | 4 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /F /20/GOFA-PSV-34056A | TRIM HEATER, E-3402 | NOSD | 2017-06-19
| MTN-MECH | 2021-11-08 | 7:00 | 2018-11-15 | WDF | 5 | V | 2021-11-09 | 11:00 | 5.Within 4 Months | 2100028039 | 0010 | SMAT:The gear on the HCV is broken. | Mount gear on valve | 1 | 6 |  |  | 4 | 4 | 0 | APPR PROK RDBL | APPR OPND | REL PRC SETC MANC | GO /C /26/GC-XCV-02960 | SLAVE STREAM 2 INLET | NOSD | 2018-08-17
| MTN-MECH | 2021-11-09 | 13:00 | 2020-04-25 | WDF | 4 | I | 2021-11-10 | 13:00 | 4.Within 2 Months | 2100029130 | 0030 | GOC GC-TCV-0314 Cooling W. TCV-0314 Stuc | De mount aktuator and positioner | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /76/GC-TCV-0314 | COOLING WATER FROM E-401A |  | 2020-03-16
| MTN-MECH | 2021-11-10 | 13:00 | 2020-04-25 | WDF | 4 | I | 2021-11-11 | 13:00 | 4.Within 2 Months | 2100029130 | 0040 | GOC GC-TCV-0314 Cooling W. TCV-0314 Stuc | mount new actuator | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /76/GC-TCV-0314 | COOLING WATER FROM E-401A |  | 2020-03-16
| MTN-MECH | 2021-11-08 | 7:00 | 2020-03-27 | WDF | 3 | S | 2021-11-15 | 19:00 | 3.Intermedt 1 Month | 2100029442 | 0030 | F-402B Filter unit cleaning | Montering filter | 2 | 4 | FIlters/Backloaded | Refurbish | 48 | 48 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /51/GC-F-402B | COOLING WATER FILTER |  | 2020-03-07
| MTN-MECH | 2021-11-11 | 15:00 | 2020-05-01 | WDF | 4 | V | 2021-11-12 | 19:00 | 4.Within 2 Months | 2100029445 | 0040 | Emg. Gen. G-810 Low temp. jacket water | Remove heater and pump | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /05/GC-G-810 | EMERGENCY GENERATOR |  | 2020-03-22
| MTN-MECH | 2021-11-13 | 7:00 | 2020-05-01 | WDF | 4 | V | 2021-11-15 | 15:00 | 4.Within 2 Months | 2100029445 | 0050 | Emg. Gen. G-810 Low temp. jacket water | Install new heater and pump | 1 | 6 |  | Hold Step | 8 | 8 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /05/GC-G-810 | EMERGENCY GENERATOR |  | 2020-03-22
| MTN-MECH | 2021-11-15 | 15:00 | 2020-05-01 | WDF | 4 | V | 2021-11-16 | 11:00 | 4.Within 2 Months | 2100029445 | 0060 | Emg. Gen. G-810 Low temp. jacket water | Re-fill cooling water | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /05/GC-G-810 | EMERGENCY GENERATOR |  | 2020-03-22
| MTN-MECH | 2021-11-17 | 15:00 | 2020-05-01 | WDF | 4 | V | 2021-11-18 | 19:00 | 4.Within 2 Months | 2100029445 | 0080 | Emg. Gen. G-810 Low temp. jacket water | Test circulation and heating | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /05/GC-G-810 | EMERGENCY GENERATOR |  | 2020-03-22
| MTN-MECH | 2021-11-08 | 11:00 | 2020-04-01 | WDF | 3 | I | 2021-11-08 | 19:00 | 3.Intermedt 1 Month | 2100030205 | 0020 | Gorm C. New chlorine pump P-0324A for pr | Replace pump P-0324A | 2 | 2 | RCE | PR step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-M-401A | PACKAGE - POTABLE WATER MAKER PROMAC | NOSD | 2020-03-12
| MTN-MECH | 2021-11-09 | 7:00 | 2020-04-01 | WDF | 3 | I | 2021-11-09 | 11:00 | 3.Intermedt 1 Month | 2100030205 | 0030 | Gorm C. New chlorine pump P-0324A for pr | Functional test | 1 | 2 | RCE | PR step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-M-401A | PACKAGE - POTABLE WATER MAKER PROMAC | NOSD | 2020-03-12
| MTN-MECH | 2021-11-08 | 9:00 | 2020-05-03 | WDF | 4 | V | 2021-11-10 | 9:00 | 4.Within 2 Months | 2100030384 | 0020 | Lubeoil leak at P-117E | Replace seals/gaskets. | 2 | 6 |  | GR Offshore | 12 | 12 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117E | CRUDE OIL EXPORT PUMP | NOSD | 2020-03-24
| MTN-MECH | 2021-11-08 | 9:00 | 2020-05-04 | WDF | 4 | V | 2021-11-09 | 9:00 | 4.Within 2 Months | 2100030385 | 0020 | GE-FWH-1502 2"HCV leaking/spindle in hyd | Replace defect 2" hydrant | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /01/GE-FWH-1502 | HOSE REEL WATER | NOSD | 2020-03-25
| MTN-MECH | 2021-11-08 | 10:00 | 2020-04-22 | WDF | 3 | V | 2021-11-09 | 18:00 | 3.Intermedt 1 Month | 2100030394 | 0030 | Oil Change-out P-117C | Changeout GEA-P-117C | 1 | 4 |  |  | 5 | 5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-P-117C | CRUDE OIL TRANSFER SYSTEM | NOSD | 2020-04-02
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-18 | WDF | 7 | V | 2021-11-08 | 19:00 | 7.Within 12 Months | 2100030401 | 0020 | Tyra XCV-38257 MOV styring lånt. | Isolate XCV-38257 | 1 | 6 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /23/GEB-MOV-38257 | MOTOR OPERATED VALVE |  | 2020-07-21
| MTN-MECH | 2021-11-09 | 7:00 | 2021-03-18 | WDF | 7 | V | 2021-11-09 | 15:00 | 7.Within 12 Months | 2100030401 | 0030 | Tyra XCV-38257 MOV styring lånt. | remount parts | 1 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /23/GEB-MOV-38257 | MOTOR OPERATED VALVE |  | 2020-07-21
| MTN-MECH | 2021-11-09 | 15:00 | 2021-03-18 | WDF | 7 | V | 2021-11-10 | 15:00 | 7.Within 12 Months | 2100030401 | 0040 | Tyra XCV-38257 MOV styring lånt. | deisolate XCV-38257 | 1 | 6 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /23/GEB-MOV-38257 | MOTOR OPERATED VALVE |  | 2020-07-21
| MTN-MECH | 2021-11-10 | 12:00 | 2020-05-05 | WDF | 3 | S | 2021-11-13 | 16:00 | 3.Intermedt 1 Month | 2100030939 | 0020 | Seawater filter GC-F-402C change brushin | Changeout Seawater filter GC-F-402C brus | 2 | 8 | OTL/+2400106126 | (4)After/2100029442 | 20 | 20 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER |  | 2020-04-15
| MTN-MECH | 2021-11-08 | 11:00 | 2020-06-02 | WDF | 4 | S | 2021-11-10 | 11:00 | 4.Within 2 Months | 2100030942 | 0020 | GC-P-901B Loss of vacum sewage plant | Changeout GC-P-901B | 2 | 7 |  |  | 12 | 12 | 0 | APPR SMAT RDBL | APPR OPND | REL PPRT PRC SETC GMPS MANC | GO /C /82/GC-P-901B | MACERATING / VACUUM PUMP | NOSD | 2020-04-23
| MTN-MECH | 2021-11-08 | 7:00 | 2020-08-15 | WDF | 5 | S | 2021-11-08 | 15:00 | 5.Within 4 Months | 2100031373 | 0010 | Seized 2" drain/Vlv on GC-F-402C | Prepare permit - Mech | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER | NOSD | 2020-05-17
| MTN-MECH | 2021-11-08 | 7:00 | 2020-08-15 | WDF | 5 | S | 2021-11-08 | 11:00 | 5.Within 4 Months | 2100031373 | 0020 | Seized 2" drain/Vlv on GC-F-402C | Prepare Tools/Matr | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER | NOSD | 2020-05-17
| MTN-MECH | 2021-11-09 | 9:00 | 2020-08-15 | WDF | 5 | S | 2021-11-09 | 17:00 | 5.Within 4 Months | 2100031373 | 0040 | Seized 2" drain/Vlv on GC-F-402C | Replace 2" Ball Vlv | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER | NOSD | 2020-05-17
| MTN-MECH | 2021-11-08 | 7:00 | 2020-08-15 | WDF | 5 | S | 2021-11-08 | 15:00 | 5.Within 4 Months | 2100031373 | 0060 | Seized 2" drain/Vlv on GC-F-402C | Troubleshoot old valve condition | 1 | 7 |  | Hold Step | 2 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER | NOSD | 2020-05-17
| MTN-MECH | 2021-11-08 | 7:00 | 2020-06-25 | WDF | 5 | S | 2021-11-08 | 15:00 | 5.Within 4 Months | 2100031549 | 0010 | Well-N40B Manifold HCV-30111 Gearbox def | Prepare permit - Mech | 1 | 7 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /10/GOFA-HCV-30111 | HCV LP MANIFOLD TO GFN - 40 | NOSD | 2020-03-27
| MTN-MECH | 2021-11-09 | 11:00 | 2020-06-25 | WDF | 5 | S | 2021-11-11 | 11:00 | 5.Within 4 Months | 2100031549 | 0030 | Well-N40B Manifold HCV-30111 Gearbox def | Gearbox troubleshooting | 1 | 7 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /10/GOFA-HCV-30111 | HCV LP MANIFOLD TO GFN - 40 | NOSD | 2020-03-27
| MTN-MECH | 2021-11-10 | 11:00 | 2020-12-18 | WDF | 6 | S | 2021-11-12 | 19:00 | 6.Within 8 Months | 2100031610 | 0030 | GC-P-902 Sewage plant, Pump need to be c | Changeout GC-P-902 | 1 | 7 |  | Hold Step | 8 | 8 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /82/GC-P-902 | DOSING PUMP | NOSD | 2020-07-21
| MTN-MECH | 2021-11-08 | 9:00 | 2020-09-23 | WDF | 5 | I | 2021-11-10 | 9:00 | 5.Within 4 Months | 2100032886 | 0050 | Hyd. filtration pump cannot run | Install GB-P-1309 | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /B /07/GB-P-1309 | FILTRATION PUMP | NOSD | 2020-06-25
| MTN-MECH | 2021-11-10 | 11:00 | 2020-09-25 | WDF | 5 | I | 2021-11-12 | 15:00 | 5.Within 4 Months | 2100032963 | 0030 | Exchange Bio pump - P-121 | Exchange P-121 | 2 | 6 |  |  | 14 | 20 | 6 | APPR SMAT RDBL | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /E /75/GEA-P-121 | BIOCIDE INJECTION SYSTEM |  | 2020-06-27
| MTN-MECH | 2021-11-13 | 7:00 | 2020-09-25 | WDF | 5 | I | 2021-11-13 | 15:00 | 5.Within 4 Months | 2100032963 | 0060 | Exchange Bio pump - P-121 | Test P-121 | 1 | 6 |  |  | 2 | 2 | 0 | APPR SMAT RDBL | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /E /75/GEA-P-121 | BIOCIDE INJECTION SYSTEM |  | 2020-06-27
| MTN-MECH | 2021-11-08 | 13:00 | 2021-01-24 | WDF | 6 | S | 2021-11-09 | 9:00 | 6.Within 8 Months | 2100033191 | 0020 | CJE045 Replace HCV upstream GEA-PSV-1542 | Replace HCV upstream GEA-PSV-1542 | 2 | 6 |  | Hold Step | 4 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /75/GEA-PSV-1542 | PRESSURE RELIEF VALVE | NOSD | 2020-08-27
| MTN-MECH | 2021-11-09 | 7:00 | 2021-10-12 | WDF | 8 | V | 2021-11-10 | 19:00 | 8.Longer than 1 Year | 2100034282 | 0040 | GBN-31 choke to be taken off | Remove choke, and put blind on | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /B /55/GB-CVA-1304J | MANUAL OPERATED CHOKE VALVE | NOSD | 2020-12-16
| MTN-MECH | 2021-11-08 | 7:00 | 2020-10-22 | WDF | 5 | I | 2021-11-08 | 11:00 | 5.Within 4 Months | 2100034334 | 0020 | closedrain gofa-P-5002B periodisk leak | Isolate closed drain pump GOFA-P-5002B | 1 | 6 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /28/GOFA-P-5002B | PUMP | NOSD | 2020-07-24
| MTN-MECH | 2021-11-08 | 11:00 | 2020-10-22 | WDF | 5 | I | 2021-11-10 | 11:00 | 5.Within 4 Months | 2100034334 | 0030 | closedrain gofa-P-5002B periodisk leak | Change mechanical seal GOFA-P-50002B | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /28/GOFA-P-5002B | PUMP | NOSD | 2020-07-24
| MTN-MECH | 2021-11-10 | 11:00 | 2020-10-22 | WDF | 5 | I | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100034334 | 0040 | closedrain gofa-P-5002B periodisk leak | De-isolate closed drain pump GOFA-P-5002 | 1 | 6 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /28/GOFA-P-5002B | PUMP | NOSD | 2020-07-24
| MTN-MECH | 2021-11-08 | 11:00 | 2020-07-17 | WDF | 4 | V | 2021-11-10 | 11:00 | 4.Within 2 Months | 2100035513 | 0060 | Diesel Fuel PCV-1002 is not operating | replace PCV, and test | 1 | 6 |  |  | 6 | 6 | 0 | APPR APOG SMAT RFRZ | INIT OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /71/GC-PCV-1002 | DIESEL OIL FROM P-801A&B | NE | 2020-07-12
| MTN-MECH | 2021-11-08 | 7:00 | 2020-11-12 | WDF | 5 | S | 2021-11-09 | 11:00 | 5.Within 4 Months | 2100035519 | 0020 | Replace vacuum pump on sewage unit. | Receive and store spare vacuum pump | 1 | 7 |  | Hold/CMAT | 4 | 4 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82/GC-P-901B | MACERATING / VACUUM PUMP | NOSD | 2020-08-14
| MTN-MECH | 2021-11-08 | 11:00 | 2020-12-15 | WDF | 5 | V | 2021-11-09 | 15:00 | 5.Within 4 Months | 2100036946 | 0020 | wellpanel FP-3103 hydraulic skuffe GFN49 | re-tighten fitting or send drawer home | 1 | 6 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /07/GOFB-FP-3103 | WELLHEAD HYDRAULIC SHUTDOWN PANEL |  | 2020-09-16
| MTN-MECH | 2021-11-08 | 10:00 | 2020-10-24 | WDF | 4 | V | 2021-11-10 | 10:00 | 4.Within 2 Months | 2100037353 | 0030 | GC-C-901C Olie i luftfiltre, filter has | Changeout filter/dessicant | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /07/GC-C-901C | SCREW COMPR. FOR INSTR AND UTILITY AIR | NOSD | 2020-09-14
| MTN-MECH | 2021-12-31 | 13:38 | 2020-09-27 | WDF | 3 | I | 2022-01-03 | 9:38 | 3.Intermedt 1 Month | 2100038609 | 0020 | GC-P-0288B Scale Injection pumpe stuck, | Changeout GC-P-0288B Injection pumpe | 1 | 4 | SR/OTL kræver SD? | Shipment | 8 | 8 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /75/GC-P-0288B | ANTI-FOAM PUMP | NOSD | 2020-09-22
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-15 | WDF | 7 | I | 2021-11-08 | 15:00 | 7.Within 12 Months | 2100038831 | 0010 | Defect Earth Boss on GC-FT-0335B | Prepare Permit/Tools/Matr | 1 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /85/GC-FT-0335B | POTABLE WATER MAKER MEDIA FILTER | NOSD | 2021-01-18
| MTN-MECH | 2021-11-08 | 15:00 | 2021-09-15 | WDF | 7 | I | 2021-11-09 | 19:00 | 7.Within 12 Months | 2100038831 | 0020 | Defect Earth Boss on GC-FT-0335B | Earth Boss repair | 1 | 6 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /85/GC-FT-0335B | POTABLE WATER MAKER MEDIA FILTER | NOSD | 2021-01-18
| MTN-MECH | 2021-11-10 | 7:00 | 2021-09-15 | WDF | 7 | I | 2021-11-10 | 11:00 | 7.Within 12 Months | 2100038831 | 0030 | Defect Earth Boss on GC-FT-0335B | Housekeeping | 1 | 6 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /85/GC-FT-0335B | POTABLE WATER MAKER MEDIA FILTER | NOSD | 2021-01-18
| MTN-MECH | 2021-11-08 | 13:00 | 2021-09-17 | WDF | 7 | I | 2021-11-09 | 17:00 | 7.Within 12 Months | 2100038833 | 0030 | GOF - Findings on chemical system. -Hose | Changeout HCV f/GOFA-A-3902/Hose no 813 | 1 | 6 |  | PO Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-01-20
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-17 | WDF | 7 | I | 2021-11-08 | 19:00 | 7.Within 12 Months | 2100038833 | 0060 | GOF - Findings on chemical system. -Hose | changeout hose 823 Demulsifier Chemical | 1 | 6 |  | PO Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-01-20
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-17 | WDF | 7 | I | 2021-11-08 | 19:00 | 7.Within 12 Months | 2100038833 | 0090 | GOF - Findings on chemical system. -Hose | changeout hose 812 Scale inhibitor Delu | 1 | 6 |  | PO Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-01-20
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-17 | WDF | 7 | I | 2021-11-08 | 19:00 | 7.Within 12 Months | 2100038833 | 0120 | GOF - Findings on chemical system. -Hose | changeout hose 811 Scale inhibitor Chem | 1 | 6 |  | PO Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-01-20
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-17 | WDF | 7 | I | 2021-11-08 | 19:00 | 7.Within 12 Months | 2100038833 | 0150 | GOF - Findings on chemical system. -Hose | changeout hose 808 Biocide Deluge | 1 | 6 |  | PO Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-01-20
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-17 | WDF | 7 | I | 2021-11-08 | 15:00 | 7.Within 12 Months | 2100038833 | 0180 | GOF - Findings on chemical system. -Hose | changeout hose 787 Oxygen Scavenger Chem | 1 | 6 |  | PO Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-01-20
| MTN-MECH | 2021-11-08 | 10:00 | 2021-02-10 | WDF | 5 | I | 2021-11-10 | 18:00 | 5.Within 4 Months | 2100040008 | 0030 | GOFA-P-3910 defekt pumpe/stroke changeou | Changeout GOFA-P-3910 | 1 | 6 | GR onshore 290921 | GR Onshore 210621 | 8 | 8 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-P-3910 | CATALYST PUMP | NOSD | 2020-11-12
| MTN-MECH | 2021-11-09 | 11:00 | 2022-02-14 | WDF | 8 | S | 2021-11-19 | 11:00 | 8.Longer than 1 Year | 2100040606 | 0030 | Replace pump unit on aviation fuel skid | Exchange heli fuel pump unit | 1 | 7 |  | Hold Step | 30 | 30 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-04-20
| MTN-MECH | 2021-11-09 | 9:00 | 2021-01-05 | WDF | 4 | S | 2021-11-11 | 9:00 | 4.Within 2 Months | 2100041353 | 0040 | GFN-38 Internal leaking HCV manifold | Changeout valve | 1 | 7 |  | PO Step | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /10/GOFB-HCV-30083 | SOUR MANIFOLD TO GFN-38 | NE | 2020-11-26
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-15 | WDF | 4 | I | 2021-11-08 | 15:00 | 4.Within 2 Months | 2100041600 | 0010 | GC-PCV-0395 Valve is blocked | Prepare Permit/Tools/Matr | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /05/GC-PCV-0395 | G-810/G-811 FIREWATER | NOSD | 2020-12-06
| MTN-MECH | 2021-11-08 | 15:00 | 2021-01-15 | WDF | 4 | I | 2021-11-09 | 11:00 | 4.Within 2 Months | 2100041600 | 0030 | GC-PCV-0395 Valve is blocked | Replace PCV-0935 | 2 | 6 |  | Hold Step | 4 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /05/GC-PCV-0395 | G-810/G-811 FIREWATER | NOSD | 2020-12-06
| MTN-MECH | 2021-11-09 | 15:00 | 2021-01-15 | WDF | 4 | I | 2021-11-09 | 19:00 | 4.Within 2 Months | 2100041600 | 0050 | GC-PCV-0395 Valve is blocked | Housekeeping | 1 | 6 |  | Hold Step | 1 | 1 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /05/GC-PCV-0395 | G-810/G-811 FIREWATER | NOSD | 2020-12-06
| MTN-MECH | 2021-11-08 | 15:00 | 2021-03-18 | WDF | 5 | S | 2021-11-11 | 19:00 | 5.Within 4 Months | 2100041837 | 0030 | Change filter Fuel Nozzle heli fuel | Exchange filter in fuel nozzle | 1 | 7 |  | Hold Step | 10 | 10 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-18
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-18 | WDF | 4 | S | 2021-11-10 | 15:00 | 4.Within 2 Months | 2100042027 | 0020 | "No Smoking" signs to be installed on th | Install "No Smoking" signs | 1 | 7 |  | Hold Step | 8 | 8 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-09
| MTN-MECH | 2021-11-08 | 15:00 | 2021-01-18 | WDF | 4 | S | 2021-11-15 | 11:00 | 4.Within 2 Months | 2100042028 | 0030 | Exchange of aviation fuel hose | Exchange fuel hose | 2 | 7 |  | Hold Step | 40 | 40 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-09
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-18 | WDF | 4 | S | 2021-11-09 | 11:00 | 4.Within 2 Months | 2100042030 | 0010 | Grease nipple to be removed from swivel | Removal of grease nipple | 1 | 7 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-09
| MTN-MECH | 2021-11-09 | 11:00 | 2021-01-18 | WDF | 4 | S | 2021-11-10 | 15:00 | 4.Within 2 Months | 2100042030 | 0020 | Grease nipple to be removed from swivel | Plugg-off greasing point | 1 | 7 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-09
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-23 | WDF | 4 | I | 2021-11-08 | 7:24 | 4.Within 2 Months | 2100042081 | 0010 | Order new valve due to Blocked flow | Order new valve due to Blocked flow | 1 | 8 | SR-Tier2/Awating Mat | (6) | 0.1 | 0.1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /27/GOFA-LCV-50239B | LEVEL CONTROL VENTIL |  | 2020-12-14
| MTN-MECH | 2021-11-09 | 13:00 | 2021-03-10 | WDF | 5 |  | 2021-11-11 | 13:00 | 5.Within 4 Months | 2100042082 | 0030 | WI Weep from valve drain plugs | Changeout 2 pcs valves | 1 | 7 |  | Hold Step | 6 | 6 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /F /55/GOF-4-WI-035-0405-FC-U | 4 INJECTION WATER LINE |  | 2020-12-10
| MTN-MECH | 2021-11-08 | 7:00 | 2021-06-23 | WDF | 6 | S | 2021-11-08 | 11:00 | 6.Within 8 Months | 2100042083 | 0010 | GOFA-HOSO-573703 Fuel Nozzle leaky | Isolate line at ball valve | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /71/GOFA-HOSU-573703 | DIESEL HOSE REEL |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-06-23 | WDF | 6 | S | 2021-11-08 | 19:00 | 6.Within 8 Months | 2100042083 | 0020 | GOFA-HOSO-573703 Fuel Nozzle leaky | Replace fuel nozzle | 1 | 7 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /71/GOFA-HOSU-573703 | DIESEL HOSE REEL |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 15:00 | 2021-06-23 | WDF | 6 | S | 2021-11-08 | 19:00 | 6.Within 8 Months | 2100042083 | 0030 | GOFA-HOSO-573703 Fuel Nozzle leaky | De-isolate line @ball valve & leak check | 1 | 7 |  | Hold Step | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /71/GOFA-HOSU-573703 | DIESEL HOSE REEL |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 15:00 | 2021-01-18 | WDF | 4 | S | 2021-11-11 | 19:00 | 4.Within 2 Months | 2100042181 | 0030 | Correct type of overwing nozzle | Exchange overving nozzle | 2 | 7 |  | Hold Step | 20 | 20 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-09
| MTN-MECH | 2021-11-12 | 7:00 | 2021-01-18 | WDF | 4 | S | 2021-11-13 | 11:00 | 4.Within 2 Months | 2100042181 | 0040 | Correct type of overwing nozzle | De-isolate GC-P-802 | 1 | 7 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2020-12-09
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-07 | WDF | 6 | V | 2021-11-11 | 19:00 | 6.Within 8 Months | 2100042901 | 0010 | GC-XCV-1111 Install brace/frame on relea | Fabricate & Install brace/frame on relea | 1 | 6 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-XCV-1111 | DELUGE VALVE CRANE T-804A PEDESTAL | NOSD | 2021-03-10
| MTN-MECH | 2021-11-08 | 17:00 | 2021-02-17 | WDF | 4 | V | 2021-11-09 | 17:00 | 4.Within 2 Months | 2100043627 | 0030 | Air leak from actuator esdv-12740 | Changeout actuator | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /37/GA-ESDV-12740 | EMERGENCY SHUTDOWN VALVE | NE | 2021-01-08
| MTN-MECH | 2021-11-11 | 7:00 | 2021-02-08 | WDF | 3 | V | 2021-11-11 | 7:00 | 3.Intermedt 1 Month | 2100044432 | 0020 | GBN-43 Choke - Runs badly | remove end cover, clean an lube. | 1 | 2 |  |  | 0 | 4 | 12 | APPR AWSC RDBL | APPR OPND | REL PPRT PCNF PRC SETC MANC | GO /B /10/GB-CVA-1304F | CHOKE VALVE |  | 2021-01-19
| MTN-MECH | 2021-11-11 | 12:36 | 2021-02-08 | WDF | 3 | V | 2021-11-12 | 8:36 | 3.Intermedt 1 Month | 2100044432 | 0040 | GBN-43 Choke - Runs badly | test operation | 1 | 2 |  |  | 2 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL PPRT PCNF PRC SETC MANC | GO /B /10/GB-CVA-1304F | CHOKE VALVE |  | 2021-01-19
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-15 | WDF | 4 | V | 2021-11-09 | 19:00 | 4.Within 2 Months | 2100044702 | 0010 | Repl boat stop SB front GC-M-703 (LB3) | Repl boat stop SB front GC-M-703 (LB3) | 2 | 6 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /02/GC-M-703 | ESCAPE CAPSULE NO 3 | NOSD | 2021-02-03
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-15 | WDF | 4 | V | 2021-11-09 | 19:00 | 4.Within 2 Months | 2100044703 | 0010 | Repl boat stops/holders GC-M-704 (LB4) | Repl boat stops/holders GC-M-704 (LB4) | 2 | 6 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /02/GC-M-704 | ESCAPE CAPSULE NO 4 | NOSD | 2021-02-03
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-25 | WDF | 3 | S | 2021-11-22 | 9:00 | 3.Intermedt 1 Month | 2100044832 | 0010 | Leakage on seawage vaccum system | Leakage on seawage vaccum system | 2 | 8 | No planning General job | No planning General job | 85 | 200 | 115 | APPR APOG | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /82/GC-M-900 | SEWAGE TREATMENT PLANT | NOSD | 2021-01-20
| MTN-MECH | 2021-12-26 | 7:06 | 2021-05-20 | WDF | 5 | I | 2021-12-27 | 7:06 | 5.Within 4 Months | 2100044957 | 0030 | PCV-0542 is leaking by piston | Changeout valve. | 1 | 2 |  | GR Onshore 251121 | 3 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /71/GC-PCV-0542 | FUEL GAS CONTROL VALVE | NOSD | 2021-02-19
| MTN-MECH | 2021-11-14 | 9:00 | 2021-05-15 | WDF | 5 | V | 2021-11-18 | 9:00 | 5.Within 4 Months | 2100044958 | 0040 | Replace Coriolis meter GOFB-FE-36224 | Replace Coriolis meter GOF-FT-36224 | 1 | 6 |  | Hold Step | 12 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /23/GOFB-FE-36224 | EXPORT OIL MEASUREMENT (METERING) |  | 2021-02-14
| MTN-MECH | 2021-11-08 | 7:00 | 2021-07-28 | WDF | 6 |  | 2021-11-09 | 15:00 | 6.Within 8 Months | 2100045320 | 0010 | Damaged gearbox | mount new gearbox | 1 | 7 |  | Hold Step | 5 | 5 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /B /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS |  | 2021-02-28
| MTN-MECH | 2021-11-09 | 9:00 | 2021-03-14 | WDF | 3 | V | 2021-11-10 | 13:00 | 3.Intermedt 1 Month | 2100046088 | 0030 | ESDV-01189B - not full closure at trip | Changeout ESDV | 1 | 4 |  | Hold Step | 4 | 4 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /31/GC-ESDV-01189B | EMERGENCY SHUTDOWN VALVE | NE | 2021-02-22
| MTN-MECH | 2021-11-08 | 7:00 | 2021-07-01 | WDF | 5 | S | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100047034 | 0010 | Defect gear | Defect gear, changeout | 1 | 7 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /21/GEB-HCV-36234 | HAND CONTROL VALVE | NOSD | 2021-04-02
| MTN-MECH | 2021-11-08 | 7:00 | 2021-07-01 | WDF | 5 | S | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100047035 | 0010 | Defekt gear. | Defect gear, changeout | 1 | 7 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /21/GEB-HCV-36235 | HAND CONTROL VALVE | NOSD | 2021-04-02
| MTN-MECH | 2021-11-08 | 17:00 | 2021-07-15 | WDF | 5 | V | 2021-11-10 | 17:00 | 5.Within 4 Months | 2100047676 | 0030 | V-3411 PCV-34225-1 int. leaking | Changeout trim | 1 | 6 |  | GR Onshore 280921 | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /20/GOFB-PCV-34225_1 | PRES. CTRL IN GAS DISCH FROM LP SEP. | NOSD | 2021-04-16
| MTN-MECH | 2021-11-08 | 11:00 | 2021-07-21 | WDF | 5 | V | 2021-11-10 | 11:00 | 5.Within 4 Months | 2100048013 | 0020 | FCV-1503 stock open | changeout actuator and positioner | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-FCV-1504 | CRUDE OIL TRANSFER SYSTEM | NOSD | 2021-04-22
| MTN-MECH | 2021-11-08 | 11:00 | 2021-07-21 | WDF | 5 | V | 2021-11-10 | 11:00 | 5.Within 4 Months | 2100048014 | 0020 | FCV-1504 stock open | changeout actuator and positioner | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-FCV-1504 | CRUDE OIL TRANSFER SYSTEM | NOSD | 2021-04-22
| MTN-MECH | 2021-11-08 | 11:00 | 2021-07-21 | WDF | 5 | V | 2021-11-10 | 11:00 | 5.Within 4 Months | 2100048015 | 0020 | FCV-1507 is stock | changeout actuator and positioner | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-FCV-1507 | CRUDE OIL TRANSFER SYSTEM | NOSD | 2021-04-22
| MTN-MECH | 2021-11-08 | 10:00 | 2021-04-20 | WDF | 3 | V | 2021-11-09 | 18:00 | 3.Intermedt 1 Month | 2100048090 | 0030 | GEA-A-5401 compressor GOE A-5401 trips a | Investigation/repair | 1 | 6 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /07/GEA-A-5401 | SCREW COMPRESSOR FOR INSTRUMENT AIR | NOSD | 2021-03-31
| MTN-MECH | 2021-11-08 | 7:00 | 2021-05-25 | WDF | 4 | V | 2021-11-08 | 19:00 | 4.Within 2 Months | 2100048240 | 0010 | disasembvle and clean Flame arrestors. | Prepare permit etc | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-MECH | 2021-11-12 | 15:00 | 2021-05-25 | WDF | 4 | V | 2021-11-13 | 19:00 | 4.Within 2 Months | 2100048240 | 0040 | disasembvle and clean Flame arrestors. | Disconnect and clean GA-FLA-302 | 2 | 6 |  | Hold Step | 8 | 8 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-MECH | 2021-11-14 | 7:00 | 2021-05-25 | WDF | 4 | V | 2021-11-14 | 15:00 | 4.Within 2 Months | 2100048240 | 0050 | disasembvle and clean Flame arrestors. | Mount GA-FLA-302 | 2 | 6 |  | Hold Step | 4 | 4 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-MECH | 2021-11-14 | 15:00 | 2021-05-25 | WDF | 4 | V | 2021-11-15 | 19:00 | 4.Within 2 Months | 2100048240 | 0060 | disasembvle and clean Flame arrestors. | Disconnect and clean GB-FLA-303 | 2 | 6 |  | Hold Step | 8 | 8 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-MECH | 2021-11-16 | 7:00 | 2021-05-25 | WDF | 4 | V | 2021-11-16 | 15:00 | 4.Within 2 Months | 2100048240 | 0070 | disasembvle and clean Flame arrestors. | Mount GB-FLA-303 | 2 | 6 |  | Hold Step | 4 | 4 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-MECH | 2021-11-09 | 11:00 | 2021-08-06 | WDF | 5 | I | 2021-11-20 | 19:00 | 5.Within 4 Months | 2100048630 | 0030 | Biocide pump eksternal leak | Exchange GOFA-P-3906 | 1 | 6 |  | Refurbish | 35 | 35 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-P-3906 | BIOCIDE PUMP | NOSD | 2021-05-08
| MTN-MECH | 2021-11-08 | 10:00 | 2021-05-17 | WDF | 3 | I | 2021-11-08 | 18:00 | 3.Intermedt 1 Month | 2100049180 | 0030 | GC-F-901A Instrument air pre filters blo | Changeout Instrument air pre filters | 1 | 4 |  | Hold Step | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-F-901A | INSTRUMENT AIR PRE-FILTER | NOSD | 2021-04-27
| MTN-MECH | 2021-11-08 | 13:00 | 2021-06-21 | WDF | 4 | V | 2021-11-09 | 17:00 | 4.Within 2 Months | 2100049283 | 0020 | Valve stuck at V-3403 | changeout HCV | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /11/GOFD-V-3403 | SOUR TEST SEPARATOR | NE | 2021-05-12
| MTN-MECH | 2021-11-14 | 11:00 | 2021-12-24 | WDF | 6 | S | 2021-11-15 | 15:00 | 6.Within 8 Months | 2100049528 | 0020 | closed drain HCV broken spindle | changeout valve | 1 | 7 |  | GR Onshore 071021 | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /10/GOFB-HCV-504805 | HAND CONTROL VALVE | NOSD | 2021-07-27
| MTN-MECH | 2021-11-08 | 10:00 | 2021-07-16 | WDF | 4 | I | 2021-11-08 | 18:00 | 4.Within 2 Months | 2100050342 | 0030 | GOFA-FT-5304 Defekt AIR VENT FILTER CIRC | Changeout filter GOFA-FT-5304 | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /76/GOFA-FT-5304 | AIR VENT FILTER | NOSD | 2021-06-06
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-05 | WDF | 4 | V | 2021-11-08 | 15:00 | 4.Within 2 Months | 2100051264 | 0010 | Findings from 1Y PPM GOFA-P-0301 | Prepare permit/tools/matr | 1 | 6 |  | Hold Step | 2 | 2 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /01/GOFA-P-0301 | FIREWATER PUMP | NOSD | 2021-06-26
| MTN-MECH | 2021-11-09 | 9:00 | 2021-08-05 | WDF | 4 | V | 2021-11-11 | 9:00 | 4.Within 2 Months | 2100051264 | 0030 | Findings from 1Y PPM GOFA-P-0301 | Rectify PM findings | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /01/GOFA-P-0301 | FIREWATER PUMP | NOSD | 2021-06-26
| MTN-MECH | 2021-11-11 | 15:00 | 2021-08-05 | WDF | 4 | V | 2021-11-11 | 19:00 | 4.Within 2 Months | 2100051264 | 0050 | Findings from 1Y PPM GOFA-P-0301 | Housekeeping | 1 | 6 |  | Hold Step | 1 | 1 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /01/GOFA-P-0301 | FIREWATER PUMP | NOSD | 2021-06-26
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-21 | WDF | 5 | V | 2021-11-09 | 11:00 | 5.Within 4 Months | 2100051792 | 0030 | ESDV-36920 cannot open | Mount modifired adatop and spacer | 1 | 6 |  |  | 4 | 4 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC MANC | GO /E /26/GEA-ESDV-36920 | EMERGENCY SHUTDOWN VALVE | NOSD | 2021-07-23
| MTN-MECH | 2021-11-09 | 10:08 | 2021-10-21 | WDF | 5 | V | 2021-11-10 | 10:08 | 5.Within 4 Months | 2100051792 | 0040 | ESDV-36920 cannot open | mount gearbox. | 1 | 6 |  |  | 3 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC MANC | GO /E /26/GEA-ESDV-36920 | EMERGENCY SHUTDOWN VALVE | NOSD | 2021-07-23
| MTN-MECH | 2021-11-09 | 17:00 | 2021-10-26 | WDF | 5 | V | 2021-11-11 | 13:00 | 5.Within 4 Months | 2100052130 | 0040 | XCV-0509 on C-202A Internal Leaking | Changeout valve | 1 | 6 |  | Hold Step | 5 | 5 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /32/GC-XCV-0509 | IP GAS COMPR. | NE | 2021-07-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-25 | WDF | 5 | I | 2021-11-11 | 11:00 | 5.Within 4 Months | 2100052181 | 0020 | Temperary OR-13 string seep. | Linewalk to locate all leakages | 1 | 6 |  |  | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3905 | SODIUM HYPOCHLORITE PUMP, 50 L/HR | NOSD | 2021-07-27
| MTN-MECH | 2021-11-19 | 15:00 | 2021-10-25 | WDF | 5 | I | 2021-11-22 | 19:00 | 5.Within 4 Months | 2100052181 | 0050 | Temperary OR-13 string seep. | Flushing of system | 1 | 6 |  |  | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3905 | SODIUM HYPOCHLORITE PUMP, 50 L/HR | NOSD | 2021-07-27
| MTN-MECH | 2021-11-23 | 7:00 | 2021-10-25 | WDF | 5 | I | 2021-11-29 | 15:00 | 5.Within 4 Months | 2100052181 | 0060 | Temperary OR-13 string seep. | Repair of leakages | 1 | 6 |  |  | 20 | 20 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3905 | SODIUM HYPOCHLORITE PUMP, 50 L/HR | NOSD | 2021-07-27
| MTN-MECH | 2021-12-01 | 13:14 | 2021-10-30 | WDF | 5 | S | 2021-12-02 | 17:14 | 5.Within 4 Months | 2100052326 | 0020 | severly corroded valve | Changeout valve | 1 | 7 |  |  | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /B /28/GB-HCV-13790 | HAND CONTROL VALVE | NE | 2021-08-01
| MTN-MECH | 2021-12-01 | 14:16 | 2021-11-02 | WDF | 5 | S | 2021-12-02 | 18:16 | 5.Within 4 Months | 2100052449 | 0020 | badly corroded valve 4" FG system | Changeout valve | 1 | 7 |  |  | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /E /70/GEB-HCV-36233 | HAND CONTROL VALVE | NE | 2021-08-04
| MTN-MECH | 2021-12-02 | 7:09 | 2021-10-31 | WDF | 5 | S | 2021-12-03 | 11:09 | 5.Within 4 Months | 2100052450 | 0020 | badly corroded valve 2" FG system | Changeout valve | 1 | 7 |  |  | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /E /70/GEB-HCV-57045 | HAND CONTROL VALVE | NE | 2021-08-02
| MTN-MECH | 2021-11-08 | 11:00 | 2021-11-02 | WDF | 5 | V | 2021-11-09 | 15:00 | 5.Within 4 Months | 2100052451 | 0020 | badly corroded valve 2" FG system | Changeout valve | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /21/GEB-PCV-36087B | PRESSURE CONTROL VALVE | NE | 2021-08-04
| MTN-MECH | 2021-12-06 | 11:19 | 2022-03-10 | WDF | 6 | S | 2021-12-06 | 17:19 | 6.Within 8 Months | 2100052868 | 0020 | FW valves missing handle | Prepare matr/tools/permit | 2 | 7 |  | GR Onshore 291021 | 3 | 3 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-MECH | 2021-12-07 | 17:19 | 2022-03-10 | WDF | 6 | S | 2021-12-08 | 17:19 | 6.Within 8 Months | 2100052868 | 0050 | FW valves missing handle | Replace Butterfly 4"Vlv 09735 | 2 | 7 |  | GR Onshore 291021 | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-MECH | 2021-12-09 | 11:19 | 2022-03-10 | WDF | 6 | S | 2021-12-09 | 13:19 | 6.Within 8 Months | 2100052868 | 0080 | FW valves missing handle | Housekeeping | 2 | 7 |  | GR Onshore 291021 | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-MECH | 2021-11-08 | 12:43 | 2022-03-10 | WDF | 6 | S | 2021-11-08 | 18:43 | 6.Within 8 Months | 2100052869 | 0020 | FW valve handle missing on GEA-HCV-03047 | Prepare matr/tools/permit | 2 | 7 |  |  | 3 | 3 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /01/GEA-HCV-03047 | LO - HCV FOR DELUGE | NOSD | 2021-10-11
| MTN-MECH | 2021-11-09 | 18:43 | 2022-03-10 | WDF | 6 | S | 2021-11-10 | 18:43 | 6.Within 8 Months | 2100052869 | 0050 | FW valve handle missing on GEA-HCV-03047 | Replace 8" valve | 2 | 7 |  |  | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /01/GEA-HCV-03047 | LO - HCV FOR DELUGE | NOSD | 2021-10-11
| MTN-MECH | 2021-11-11 | 8:43 | 2022-03-10 | WDF | 6 | S | 2021-11-11 | 12:43 | 6.Within 8 Months | 2100052869 | 0070 | FW valve handle missing on GEA-HCV-03047 | Housekeeping | 2 | 7 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /01/GEA-HCV-03047 | LO - HCV FOR DELUGE | NOSD | 2021-10-11
| MTN-MECH | 2021-12-03 | 7:50 | 2021-07-22 | WDF | 1 | V | 2021-12-05 | 7:50 | 1.Emergency 2 Days | 2100053052 | 0040 | Foam ejectors for helideck not working | Prepare matr/tools/permit | 2 | 1 |  |  | 12 | 12 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-05 | 15:50 | 2021-07-22 | WDF | 1 | V | 2021-12-08 | 11:50 | 1.Emergency 2 Days | 2100053052 | 0060 | Foam ejectors for helideck not working | Modify Foam Injector P-408 SYS | 2 | 1 |  |  | 16 | 16 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-08 | 11:50 | 2021-07-22 | WDF | 1 | V | 2021-12-09 | 11:50 | 1.Emergency 2 Days | 2100053052 | 0070 | Foam ejectors for helideck not working | Production Deisolate w leak/test | 1 | 1 |  |  | 3 | 3 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-09 | 15:50 | 2021-07-22 | WDF | 1 | V | 2021-12-11 | 7:50 | 1.Emergency 2 Days | 2100053052 | 0090 | Foam ejectors for helideck not working | Prod. Isolation/Permit P-409 SYS | 1 | 1 |  |  | 4 | 4 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-11 | 7:50 | 2021-07-22 | WDF | 1 | V | 2021-12-13 | 15:50 | 1.Emergency 2 Days | 2100053052 | 0100 | Foam ejectors for helideck not working | Modify Foam Injector P-409 SYS | 2 | 1 |  |  | 16 | 16 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-13 | 15:50 | 2021-07-22 | WDF | 1 | V | 2021-12-14 | 15:50 | 1.Emergency 2 Days | 2100053052 | 0110 | Foam ejectors for helideck not working | Production Deisolate w leak/test | 1 | 1 |  |  | 3 | 3 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-14 | 15:50 | 2021-07-22 | WDF | 1 | V | 2021-12-15 | 11:50 | 1.Emergency 2 Days | 2100053052 | 0120 | Foam ejectors for helideck not working | Function Test P-408 SYS | 2 | 1 |  |  | 4 | 4 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-12-15 | 11:50 | 2021-07-22 | WDF | 1 | V | 2021-12-16 | 11:50 | 1.Emergency 2 Days | 2100053052 | 0130 | Foam ejectors for helideck not working | Housekeeping | 2 | 1 |  |  | 6 | 6 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PPRT PRC SETC MANC | GO /C /01/GC-P-409 | FIREWATER BOOSTER PUMP | NOSD | 2021-07-20
| MTN-MECH | 2021-11-22 | 8:44 | 2021-10-08 | WDF | 4 | V | 2021-11-22 | 12:44 | 4.Within 2 Months | 2100054632 | 0010 | GA-XCV-1225 found internal leaking | Prepare matr/tools/permit | 2 | 6 |  |  | 2 | 2 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /A /01/GA-XCV-1225 | DELUGE VALVE | NOSD | 2021-08-29
| MTN-MECH | 2021-11-23 | 14:44 | 2021-10-08 | WDF | 4 | V | 2021-11-24 | 18:44 | 4.Within 2 Months | 2100054632 | 0040 | GA-XCV-1225 found internal leaking | Deluge XCV-1225 Replacement | 2 | 6 |  |  | 8 | 8 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /A /01/GA-XCV-1225 | DELUGE VALVE | NOSD | 2021-08-29
| MTN-MECH | 2021-11-25 | 12:44 | 2021-10-08 | WDF | 4 | V | 2021-11-25 | 18:44 | 4.Within 2 Months | 2100054632 | 0060 | GA-XCV-1225 found internal leaking | Deluge Vlv Function Test | 2 | 6 |  |  | 3 | 3 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /A /01/GA-XCV-1225 | DELUGE VALVE | NOSD | 2021-08-29
| MTN-MECH | 2021-11-25 | 18:44 | 2021-10-08 | WDF | 4 | V | 2021-11-26 | 12:44 | 4.Within 2 Months | 2100054632 | 0070 | GA-XCV-1225 found internal leaking | Housekeeping w backload | 2 | 6 |  |  | 3 | 3 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /A /01/GA-XCV-1225 | DELUGE VALVE | NOSD | 2021-08-29
| MTN-MECH | 2021-11-10 | 10:22 | 2021-09-23 | WDF | 3 | V | 2021-11-12 | 10:22 | 3.Intermedt 1 Month | 2100054714 | 0040 | Faulty firedamper GC-SOD-380 | Assist MTN-ELEC | 1 | 4 |  |  | 6 | 6 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/GC-SOD-0380 | FIRE DAMPER EXHAUST AIR LOW. LEV. | NOSD | 2021-09-03
| MTN-MECH | 2021-11-22 | 9:04 | 2022-04-21 | WDF | 6 | V | 2021-11-23 | 9:04 | 6.Within 8 Months | 2100054717 | 0010 | GB-XCV-1321 found with wrong gasket | Prepare matr/tools/permit | 1 | 6 |  |  | 3 | 3 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /B /01/GB-XCV-1321 | DELUGE VALVE | NOSD | 2021-11-22
| MTN-MECH | 2021-11-23 | 15:04 | 2022-04-21 | WDF | 6 | V | 2021-11-24 | 11:04 | 6.Within 8 Months | 2100054717 | 0040 | GB-XCV-1321 found with wrong gasket | Replace GSKT/Deluge Vlv XCV-1321 | 2 | 6 |  |  | 4 | 4 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /B /01/GB-XCV-1321 | DELUGE VALVE | NOSD | 2021-11-22
| MTN-MECH | 2021-11-24 | 13:04 | 2022-04-21 | WDF | 6 | V | 2021-11-24 | 17:04 | 6.Within 8 Months | 2100054717 | 0060 | GB-XCV-1321 found with wrong gasket | Housekeeping | 1 | 6 |  |  | 1 | 1 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /B /01/GB-XCV-1321 | DELUGE VALVE | NOSD | 2021-11-22
| MTN-MECH | 2021-11-22 | 9:04 | 2022-04-21 | WDF | 6 | V | 2021-11-23 | 9:04 | 6.Within 8 Months | 2100054718 | 0010 | GB-XCV-1322 found with wrong gasket | Prepare matr/tools/permit | 1 | 6 |  |  | 3 | 3 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /B /01/GB-XCV-1322 | DELUGE VALVE | NOSD | 2021-11-22
| MTN-MECH | 2021-11-23 | 15:04 | 2022-04-21 | WDF | 6 | V | 2021-11-24 | 11:04 | 6.Within 8 Months | 2100054718 | 0040 | GB-XCV-1322 found with wrong gasket | Replace GSKT/Deluge Vlv XCV-1322 | 2 | 6 |  |  | 4 | 4 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /B /01/GB-XCV-1322 | DELUGE VALVE | NOSD | 2021-11-22
| MTN-MECH | 2021-11-24 | 13:04 | 2022-04-21 | WDF | 6 | V | 2021-11-24 | 17:04 | 6.Within 8 Months | 2100054718 | 0060 | GB-XCV-1322 found with wrong gasket | Housekeeping | 1 | 6 |  |  | 1 | 1 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MACM | GO /B /01/GB-XCV-1322 | DELUGE VALVE | NOSD | 2021-11-22
| MTN-MECH | 2021-11-08 | 13:00 | 2021-12-28 | WDF | 5 | V | 2021-11-12 | 13:00 | 5.Within 4 Months | 2100055030 | 0030 | Clean Gorm E fast loop BS&W meter | Dismantel meter | 1 | 6 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GE-AE-2901 | SENSOR FOR AT-2901 (METERING) |  | 2021-09-29
| MTN-MECH | 2021-11-08 | 7:00 | 2020-01-21 | WPM | C | S | 2021-11-18 | 15:00 | Business Critical | 2400049931 | 0010 | 1Y SALTVANDSSERVICEFILTRE GC-F-401A/B | 1Y SALTVANDSSERVICEFILTRE GC-F-401A/B | 1 | 5 |  | Hold Step | 32 | 32 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /77/GC-F-401A | SERVICE WATER FILTER | NOSD | 2019-11-28
| MTN-MECH | 2021-11-08 | 7:00 | 2020-01-21 | WPM | C | V | 2021-11-15 | 11:00 | Business Critical | 2400049946 | 0010 | 1Y IRON FILTER FEED PUMPER, GORM C | 1Y IRON FILTER FEED PUMPER, GORM C | 1 | 5 |  |  | 22 | 22 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NE | 2019-11-30
| MTN-MECH | 2021-11-08 | 7:00 | 2020-01-15 | WPM | C | V | 2021-11-13 | 17:00 | Business Critical | 2400049973 | 0010 | 1Y FIRED HEATER | Fired heater | 1 | 5 |  |  | 17.5 | 17.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /72 | HOT WATER GENERATION AND DISTRIBUTION | NE | 2019-11-22
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-01 | WPM | D | I | 2021-11-08 | 15:00 | Non Critical | 2400050051 | 0010 | CMAT:1Y ENWAMATIC FILTER | 1Y ENWAMATIC FILTER | 1 | 5 |  | Hold/CMAT | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /51 | FILTRATION (MAIN AND PRELIMINARY) | NOSD | 2019-11-22
| MTN-MECH | 2021-11-08 | 7:00 | 2019-12-17 | WPM | D | V | 2021-11-11 | 19:00 | Non Critical | 2400050145 | 0010 | 3M GORM LUB. AND INSP. PLAN | Condition insp round for pumps/motors | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27 | OILY WATER PROCESSING | NE | 2019-11-24
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-16 | WPM | D | V | 2021-11-08 | 15:00 | Non Critical | 2400050194 | 0010 | 6M DRAIN CLEANING CONDENSERS | TOP UP OF WATER TRAP | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27 | OILY WATER PROCESSING | NE | 2020-01-09
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-26 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400050277 | 0010 | 5Y BREATHING AIR STATION GA-A-1210 | BREATHING AIR SYSTEM INSPECTION,, | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MANC | GO /A /02/GA-A-1210 | PRESSURE REDUCTION STATION | NOSD | 2019-12-23
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-23 | WPM | C | I | 2021-11-12 | 15:00 | Business Critical | 2400050402 | 0010 | 1Y BRISCO SSSV CONTROL PANEL - GOB | Registration of working hours | 1 | 5 |  | Hold Step | 14 | 14 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /B /07/GB-FP-1377 | HYDRAULIC BOOSTER PANEL | NOSD | 2020-01-27
| MTN-MECH | 2021-11-08 | 11:00 | 2020-02-22 | WPM | C | V | 2021-11-10 | 19:00 | Business Critical | 2400050448 | 0020 | 2Y GC-A-0294 OIL EXPORT - METERING | Demontering og montering af meteret | 1 | 5 |  |  | 8 | 8 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /26/GC-A-0294 | PACKAGE EQUIPMENT SKID | NOSD | 2020-01-14
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-22 | WPM | C | V | 2021-11-24 | 15:00 | Business Critical | 2400050496 | 0010 | 2Y CRUDE OIL PUMP A-117E, CALENDAR PM | Transmitter, Kalibrer | 1 | 5 |  | Hold Step | 50 | 50 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117E | CRUDE OIL EXPORT PUMP | NE | 2019-12-05
| MTN-MECH | 2021-11-08 | 7:00 | 2019-10-19 | WPM | C | V | 2021-11-10 | 13:00 | Business Critical | 2400050512 | 0010 | 1Y RENSNING AF DRÆNSYSTEM | P&ID REF: GOFA-05-01014-0001, REV.19 | 1 | 5 |  |  | 7.5 | 7.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /27 | OILY WATER PROCESSING | NOSD | 2019-08-30
| MTN-MECH | 2021-11-08 | 7:00 | 2019-10-24 | WPM | C | V | 2021-11-13 | 19:00 | Business Critical | 2400050513 | 0010 | 1Y RENSNING AF DRÆNSYSTEM | P&ID REF: GOCY-05-01057-0001, REV.24 | 1 | 5 |  |  | 18 | 18 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27 | OILY WATER PROCESSING | NE | 2019-08-30
| MTN-MECH | 2021-11-08 | 7:00 | 2020-01-17 | WPM | C | I | 2021-11-08 | 17:00 | Business Critical | 2400050542 | 0010 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-3910 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-3910 | 1 | 5 | await 2100025740 |  | 2.5 | 2.5 | 0 | APPR | APPR OPND | REL PRT PCNF PRC SETC MANC NMAT | GO /F /75/GOFA-P-3910 | CATALYST PUMP | NE | 2019-12-24
| MTN-MECH | 2021-11-08 | 7:00 | 2020-02-12 | WPM | C | V | 2021-11-08 | 17:00 | Business Critical | 2400050703 | 0010 | CHEMICAL INJECTION RACKS, GORM F | DER LAVES EN WORK PERMIT FOR AT UDFØ | 1 | 5 |  |  | 2.5 | 2.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | NE | 2019-12-26
| MTN-MECH | 2021-11-08 | 7:00 | 2019-10-07 | WPM | C | V | 2021-11-16 | 11:00 | Business Critical | 2400050786 | 0010 | PLUG VALVES IN OIL/GAS SYSTEMS | Maintenance procedure | 1 | 5 |  |  | 25 | 25 | 0 | APPR PROK RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2019-08-18
| MTN-MECH | 2021-11-08 | 7:00 | 2019-11-16 | WPM | D |  | 2021-11-09 | 11:00 | Non Critical | 2400050935 | 0010 | SMAT:AIR FILTER, SMOKE CABINS GOE | UDSKIFTNING AF FILTRE FOR RYGEKABINE | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /82 | LIVING AND WELFARE QTRS | NOSD | 2019-10-23
| MTN-MECH | 2021-11-08 | 7:00 | 2019-11-03 | WPM | C | V | 2021-11-19 | 19:00 | Business Critical | 2400051052 | 0010 | 6M GAS TURBINE PT-3501/P-3501 | Before the task can be started, the ppm | 1 | 5 |  | Hold Step | 36 | 36 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NE | 2019-10-01
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-12 | WPM | C | I | 2021-11-09 | 19:00 | Business Critical | 2400051264 | 0010 | 1Y GOF DIESEL HOSE REELS | 19.03.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR | APPR OPND | REL PRC SETC MANC NMAT | GO /F /71/DIESEL-HOSES | DIESEL HOSES | NE | 2020-04-17
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-26 | WPM | C | I | 2021-11-09 | 19:00 | Business Critical | 2400051265 | 0010 | 1Y GOC DIESEL HOSE REELS | 19.03.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/DIESEL-HOSES | DIESEL HOSES | NE | 2020-05-01
| MTN-MECH | 2021-11-08 | 7:00 | 2020-07-17 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400051316 | 0010 | 2 Y STAIRS GORM A | 2 Y STAIRS GORM A | 1 | 5 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /A /86 | STRUCTURES/MOORING/BALLAST | NOSD | 2020-03-28
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-30 | WPM | C | I | 2021-11-08 | 15:00 | Business Critical | 2400051329 | 0010 | 1Y VAND & GLYCOLEKS KØLEVANDS TANK T-403 | Registration of working hours | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /51 | FILTRATION (MAIN AND PRELIMINARY) | NE | 2020-04-13
| MTN-MECH | 2021-11-08 | 7:00 | 2020-06-14 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400051334 | 0010 | 1Y BREATHING AIR STATION A-5405/5415 | BREATHING AIR PRESS REDUCTION SYSTEM, TY | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR CMAT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2020-05-20
| MTN-MECH | 2021-11-08 | 7:00 | 2020-06-27 | WPM | B | V | 2021-11-23 | 19:00 | Safety & Env.Related | 2400051345 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117E | Instrument ventiler - generelt | 1 | 5 |  | Hold Step | 48 | 48 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117E | CRUDE OIL EXPORT PUMP | NE | 2020-05-23
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-19 | WPM | D | V | 2021-11-10 | 11:00 | Non Critical | 2400051363 | 0010 | 1YA BREATHING AIR COMPRESSOR GC-A-5401/5 | 1YA BREATHING AIR COMPRESSOR GC-A-5401/5 | 1 | 5 |  | Hold Step | 7 | 7 | 0 | APPR PMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /02/GC-A-5401 | BREATHING AIR COMPRESSOR | NOSD | 2020-03-09
| MTN-MECH | 2021-11-08 | 11:00 | 2020-04-28 | WPM | C | V | 2021-11-10 | 19:00 | Business Critical | 2400051596 | 0020 | 3Y RFA SEP. GC-V-104 - METERING | De-montering og montering af meteret | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /11/GC-V-104 | ROLF SEPARATOR | NOSD | 2020-03-18
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-30 | WPM | C | V | 2021-11-11 | 17:00 | Business Critical | 2400051673 | 0010 | 1YA WATER CLARIFIER INJECTION GOF-P-3911 | 1YA WATER CLARIFIER INJECTION GOF-P-3911 | 1 | 5 |  |  | 11.5 | 11.5 | 0 | APPR | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFB-A-3904 | WATER CLARIFIER PUMP SKID | NE | 2020-05-03
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-15 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400051694 | 0010 | MEXEL INJECTION RACKS, GORM C | DER LAVES EN WORK PERMIT FOR AT UDFØ | 1 | 5 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | NE | 2020-03-27
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-26 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400051706 | 0010 | 1Y SIKKERHEDSDRÆN | GOF-53A01 PM-Code: | 1 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /28 | CLOSED DRAINS/OPEN DRAINS | NE | 2020-04-07
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-10 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400051733 | 0010 | 1Y MANUAL OPERATED BLOCK VALVES SYS. 36 | GOC-36Z02 PM-Code: | 1 | 5 |  |  | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /23 | TRANSFER | NE | 2020-03-22
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-12 | WPM | B | V | 2021-11-20 | 11:00 | Safety & Env.Related | 2400051953 | 0010 | 1Y BOOSTER PUMPER GC-P-101A/B/C/D MODUL2 | 1Y BOOSTER PUMPER GC-P-101A/B/C/D MODUL2 | 1 | 5 | /ptw-270720/271013 |  | 37 | 37 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC MANC NMAT | GO /C /23/GC-P-101A | CRUDE OIL BUSTER PUMP | NE | 2020-04-09
| MTN-MECH | 2021-11-08 | 7:00 | 2020-06-28 | WPM | C | I | 2021-11-10 | 11:00 | Business Critical | 2400051969 | 0010 | 2Y INST. & UTILITY AIR DRYER. GC-X-0986 | 2Y, AIR DRYER, GC-X-0986 | 1 | 5 |  | Hold Step | 7 | 7 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /07/GC-X-0986 | AIR DRYER PACKAGE | NE | 2020-04-16
| MTN-MECH | 2021-11-08 | 9:00 | 2020-05-09 | WPM | C | V | 2021-11-10 | 9:00 | Business Critical | 2400052002 | 0020 | 1Y GOFA-FT-35979 - PW METERING | De-montering og montering af meteret | 1 | 5 | SR | Pick/Pack/Myndighedskrav | 6 | 6 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NE | 2020-03-22
| MTN-MECH | 2021-11-08 | 7:00 | 2020-05-08 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400052042 | 0010 | 1Y BRISCO SSSV CONTROL PANEL - GOA | Registration of working hours | 1 | 5 |  | Hold Step | 13 | 13 | 0 | APPR PMAT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /07/GA-FP-1207 | EXTENSION FOR BRISCO PANEL BOOSTER PANEL | NOSD | 2020-04-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-04-01 | WPM | C | I | 2021-11-14 | 15:00 | Business Critical | 2400052217 | 0010 | 3M INJECTION VANDFILTER FT-3505 | Instrument ventiler - generelt | 1 | 5 |  | Hold Step | 20 | 20 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /F /54/GOFB-FT-3505 | DUAL MEDIA FILTER NR. 5 | NE | 2020-03-03
| MTN-MECH | 2021-11-08 | 7:00 | 2020-03-31 | WPM | C | I | 2021-11-12 | 17:00 | Business Critical | 2400052228 | 0010 | 1YA WATERCLARIFIER GC-P-1122A-D, GC-P-11 | Instrument ventiler - generelt | 1 | 5 |  |  | 14.5 | 14.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-P-1122A | WTR CLARIFICATION INJ. PUMP FOR GC-V-101 | NE | 2020-03-03
| MTN-MECH | 2021-11-08 | 7:00 | 2020-03-22 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400052285 | 0010 | CMAT:1Y BREATHING AIR STATION GB-A-5418 | BREATHING AIR SYSTEM INSPECTION,, | 1 | 5 |  | Hold/CMAT | 10 | 10 | 0 | APPR | APPR OPND | REL PRC SETC MANC | GO /B /02/GB-A-5418 | PRESSURE REDUCTION STATION | NOSD | 2020-02-26
| MTN-MECH | 2021-11-08 | 7:00 | 2020-03-19 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400052669 | 0010 | 1Y SMØRING/TILSTAND AF KONTROLVENTILER | GOC-44Z03 PM-Code: | 2 | 5 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /31 | GAS COMPRESSION | NOSD | 2020-01-30
| MTN-MECH | 2021-11-08 | 7:00 | 2020-04-24 | WPM | C | I | 2021-11-10 | 11:00 | Business Critical | 2400052735 | 0010 | 1Y COOLING WATER PUMPS P-5305A/B, LEVEL | Registration of working hours | 1 | 5 |  |  | 7 | 7 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /76/GOFA-E-5303 | CIRC. OIL TANK HEATER | NE | 2020-03-05
| MTN-MECH | 2021-11-08 | 7:00 | 2020-04-21 | WPM | A |  | 2021-11-09 | 11:00 | Assurance | 2400052743 | 0010 | 3Y KØLEVANDSFILTRE GC-F-402A/B/C | Registration of working hours | 1 | 5 |  | Hold Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /76 | COOLING WATER | NE | 2020-03-12
| MTN-MECH | 2021-11-08 | 7:00 | 2020-04-14 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400052746 | 0010 | 1Y LOW PRESSURE BREATHING AIR MANIFOLDS | Breathing air manifold | 1 | 5 |  | Hold Step | 13 | 13 | 0 | APPR PMAT | APPR OPND | REL PRC SETC GMPS MANC | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2020-03-19
| MTN-MECH | 2021-11-08 | 7:00 | 2020-04-10 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400052780 | 0010 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-4604 | 1YA KEMIKALIE INJECTION PUMPE GOF-P-4604 | 1 | 5 |  |  | 4 | 4 | 0 | APPR | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFB-A-3903 | H2S SCAV. INJECTION PUMP SKID | NE | 2020-03-16
| MTN-MECH | 2021-11-08 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400052952 | 0010 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Transmitter, calibrer | 1 | 5 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-08 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400052952 | 0040 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Pumpe<(>,<)> Funktions test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-08 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400052952 | 0050 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Pumpe, inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-08 | 15:00 | 2020-06-27 | WPM | C | V | 2021-11-08 | 17:00 | Business Critical | 2400052952 | 0070 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Push button, Rengør mekanisk | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-08 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400052952 | 0100 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Push button, Funktions test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-09 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-09 | 9:00 | Business Critical | 2400052952 | 0130 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Tank, Sampling Olie | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-09 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400052952 | 0140 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Tank<(>,<)> Inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-09 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-09 | 13:00 | Business Critical | 2400052952 | 0150 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Tank, Inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-09 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-10 | 9:00 | Business Critical | 2400052952 | 0160 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | TANK, OLIE SKIFT | 1 | 5 |  | PO Step | 2 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-10 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-10 | 17:00 | Business Critical | 2400052952 | 0170 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Switch<(>,<)> Juster SP | 1 | 5 |  | PO Step | 2 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-10 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-10 | 19:00 | Business Critical | 2400052952 | 0200 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Motor, Rengør | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-11 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-11 | 9:00 | Business Critical | 2400052952 | 0210 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Køler, rengør | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-11 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400052952 | 0220 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Køler, inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-11 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-11 | 13:00 | Business Critical | 2400052952 | 0230 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Køler<(>,<)> Inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-11 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-11 | 15:00 | Business Critical | 2400052952 | 0240 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Aktuator, Funktions test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-11 | 15:00 | 2020-06-27 | WPM | C | V | 2021-11-11 | 17:00 | Business Critical | 2400052952 | 0250 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Switch, funktions test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-11 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400052952 | 0260 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Skueglas, Inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-12 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400052952 | 0270 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Ventil, Juster SP | 1 | 5 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-12 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-12 | 13:00 | Business Critical | 2400052952 | 0280 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Ventil<(>,<)> Funktions test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-12 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-12 | 15:00 | Business Critical | 2400052952 | 0290 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Aktuator, Inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-12 | 15:00 | 2020-06-27 | WPM | C | V | 2021-11-12 | 19:00 | Business Critical | 2400052952 | 0300 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Ventil, Funktions test | 1 | 5 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-13 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-13 | 11:00 | Business Critical | 2400052952 | 0310 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Regulator, Juster SP | 1 | 5 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-13 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-13 | 15:00 | Business Critical | 2400052952 | 0330 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Regulator, Leak test | 1 | 5 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-13 | 15:00 | 2020-06-27 | WPM | C | V | 2021-11-13 | 19:00 | Business Critical | 2400052952 | 0350 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Konverter, Rengør | 1 | 5 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-14 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-14 | 9:00 | Business Critical | 2400052952 | 0360 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Konverter, Kalibrer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-14 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-14 | 11:00 | Business Critical | 2400052952 | 0370 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Ventil, Funktions test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-14 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-14 | 13:00 | Business Critical | 2400052952 | 0380 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Aktuator, Leak test | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-14 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-14 | 15:00 | Business Critical | 2400052952 | 0390 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Transmitter, Kalibrer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-14 | 15:00 | 2020-06-27 | WPM | C | V | 2021-11-14 | 17:00 | Business Critical | 2400052952 | 0400 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Filter, udskift | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-14 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400052952 | 0410 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Filter, Inspicer | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-15 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-15 | 9:00 | Business Critical | 2400052952 | 0420 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | FILTER, INSPICER | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-15 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-19 | 9:00 | Business Critical | 2400052952 | 0430 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Seal, Udskift | 2 | 5 |  | PO Step | 24 | 24 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-19 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-21 | 17:00 | Business Critical | 2400052952 | 0440 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | CL, Rengør | 1 | 5 |  | PO Step | 8 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-21 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-21 | 19:00 | Business Critical | 2400052952 | 0450 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Seal, IR måling | 1 | 5 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-22 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-22 | 9:00 | Business Critical | 2400052952 | 0460 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Leje<(>,<)> Inspicer | 1 | 3 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-22 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-22 | 13:00 | Business Critical | 2400052952 | 0470 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Pumpe, Data opsamling | 1 | 3 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-22 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-22 | 17:00 | Business Critical | 2400052952 | 0480 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Motor, Data opsamling | 1 | 3 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-22 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-22 | 19:00 | Business Critical | 2400052952 | 0490 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | LEJE, SMØRING | 1 | 3 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-23 | 7:00 | 2020-06-27 | WPM | C | V | 2021-11-23 | 9:00 | Business Critical | 2400052952 | 0500 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Switch, Rengør | 1 | 3 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-23 | 9:00 | 2020-06-27 | WPM | C | V | 2021-11-23 | 11:00 | Business Critical | 2400052952 | 0520 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Switch, Funktions test | 1 | 3 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-23 | 11:00 | 2020-06-27 | WPM | C | V | 2021-11-23 | 13:00 | Business Critical | 2400052952 | 0540 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | HEATER, MODSTANDSTJEK | 1 | 3 |  | PO Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-23 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-23 | 17:00 | Business Critical | 2400052952 | 0550 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Heater, isolations test | 1 | 3 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-23 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-24 | 13:00 | Business Critical | 2400052952 | 0560 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Switch<(>,<)> Udskift | 1 | 3 |  | PO Step | 2 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-24 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-24 | 17:00 | Business Critical | 2400052952 | 0580 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Switch<(>,<)> Juster SP | 1 | 3 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-24 | 17:00 | 2020-06-27 | WPM | C | V | 2021-11-25 | 13:00 | Business Critical | 2400052952 | 0600 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Pumpe, Udskift | 1 | 3 |  | PO Step | 2 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-25 | 13:00 | 2020-06-27 | WPM | C | V | 2021-11-25 | 17:00 | Business Critical | 2400052952 | 0610 | 6 Y CRUDE OIL PUMP A-117B, CALENDAR PM | Transmitter, Kalibrer | 1 | 3 |  | PO Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM | NE | 2020-01-17
| MTN-MECH | 2021-11-08 | 7:00 | 2020-04-01 | WPM | C |  | 2021-11-08 | 19:00 | Business Critical | 2400053084 | 0010 | 6M SLANGER FOR HØJTRYKSRENSER | 1. Placering af slangeruller for hø | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /72 | HOT WATER GENERATION AND DISTRIBUTION | NOSD | 2020-03-06
| MTN-MECH | 2021-11-08 | 7:00 | 2018-08-21 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400053269 | 0010 | SMAT:1Y COOLING WATER PUMP, P-5302. | 1Y COOLING WATER PUMP, P-5302. | 1 | 5 | After 2100025573 | Await 2100042857 + 2100025573 | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC | GO /F /76 | COOLING WATER | NE | 2018-07-02
| MTN-MECH | 2021-11-08 | 7:00 | 2018-09-25 | WPM | C | I | 2021-11-09 | 11:00 | Business Critical | 2400053290 | 0010 | SMAT:1YA SCALE INH P-3902A/B/C&P-3915A/B | 28.05.2013 | 1 | 5 |  |  | 4 | 4 | 0 | APPR PROK RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2018-08-31
| MTN-MECH | 2021-11-08 | 7:00 | 2018-04-21 | WPM | C |  | 2021-11-09 | 13:00 | Business Critical | 2400053328 | 0010 | SMAT:KØLEVANDSFILTRE GC-F-402A/B/C | 1. KONTROLLER FILTRENE FOR UDVENDIGE S | 1 | 5 |  |  | 4.5 | 4.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /C /76 | COOLING WATER | NOSD | 2018-03-25
| MTN-MECH | 2021-11-08 | 7:00 | 2019-02-13 | WPM | D | V | 2021-11-23 | 9:00 | Non Critical | 2400053859 | 0010 | DØRE/SKYDEDØRE, GORM C | 1. DØRE | 1 | 5 | CARETEAKER |  | 45.5 | 60 | 14.5 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /86 | STRUCTURES/MOORING/BALLAST | NOSD | 2018-12-03
| MTN-MECH | 2021-11-26 | 7:00 | 2019-02-13 | WPM | D | V | 2021-12-09 | 11:00 | Non Critical | 2400053859 | 0020 | DØRE/SKYDEDØRE, GORM C | NOT: 100610115 | 1 | 5 |  |  | 40 | 40 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /86 | STRUCTURES/MOORING/BALLAST | NOSD | 2018-12-03
| MTN-MECH | 2021-11-08 | 7:00 | 2019-11-12 | WPM | D | V | 2021-11-11 | 11:00 | Non Critical | 2400053861 | 0040 | 6M GLYCOL DEHYDRATION PACKAGE, GC-P-501A | GLYKOL-CIRKULATIONSPUMPE | 1 | 5 |  |  | 10 | 10 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /30 | DEHYDRATION/SWEETENING | NOSD | 2019-02-28
| MTN-MECH | 2021-11-08 | 7:00 | 2018-02-13 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400055125 | 0020 | SMAT:WIRELINE OVERRIDE PANELER, GA/GB. | Demount and backload GOA panel FP-1305 | 2 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2017-06-10
| MTN-MECH | 2021-11-08 | 11:00 | 2018-02-13 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400055125 | 0030 | SMAT:WIRELINE OVERRIDE PANELER, GA/GB. | Install refurbed panel GOA FP-1305 | 2 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2017-06-10
| MTN-MECH | 2021-11-08 | 15:00 | 2018-02-13 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400055125 | 0040 | SMAT:WIRELINE OVERRIDE PANELER, GA/GB. | Demount and Backload GOB panel FP | 2 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2017-06-10
| MTN-MECH | 2021-11-09 | 7:00 | 2018-02-13 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400055125 | 0050 | SMAT:WIRELINE OVERRIDE PANELER, GA/GB. | Install refurbed panel GOB | 2 | 5 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC | GO /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD | 2017-06-10
| MTN-MECH | 2021-11-08 | 7:00 | 2020-10-02 | WPM | C | S | 2021-11-12 | 19:00 | Business Critical | 2400064300 | 0010 | 1Y PLUG VALVES IN OIL/GAS GOF | TILSTAND OG SMØRING AF PLUGVENTILER. | 1 | 5 |  |  | 15 | 15 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /10/GOFB-HCV-30028 | HAND CONTROL VALVE | NOSD | 2020-07-20
| MTN-MECH | 2021-11-08 | 7:00 | 2020-09-04 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400064563 | 0010 | 2Y HANDRAIL GORM A(GOC-64I02) | 31.03.2012 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /A /86/STRUCTURAL-ABOVE-WATER | STRUCTURE ABOVE WATER | NOSD | 2020-04-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-09-04 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400064566 | 0010 | 2Y HANDRAIL GORM B(GOC-64I03) | 31.03.2012 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /B /86/STRUCTURAL-ABOVE-WATER | STRUCTURE ABOVE WATER | NOSD | 2020-04-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-09-04 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400064567 | 0010 | 2Y - HANDRAIL, GORM GOC,GOD+ BR. GOC-GOD | 31.03.2012 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /86/STRUCTURAL-ABOVE-WATER | STRUCTURE ABOVE WATER | NOSD | 2020-04-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-09-04 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400064568 | 0010 | 2Y - HANDRAIL, GORM GOF, BR. GOF-GOB | 31.03.2012 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /86/STRUCTURAL-ABOVE-WATER | STRUCTURE ABOVE WATER | NOSD | 2020-04-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-09-04 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400064569 | 0010 | 2Y - HANDRAIL GORM GOE+ BR. GOE-GOC | 31.03.2012 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /86/STRUCTURAL-ABOVE-WATER | STRUCTURE ABOVE WATER | NOSD | 2020-04-11
| MTN-MECH | 2021-12-25 | 15:00 | 2020-12-17 | WPM | C | V | 2022-01-06 | 15:00 | Business Critical | 2400065219 | 0020 | 4Y FW PUMP ANODE SKIFT GC-P-402B | UDSKIFTNING AF ANODER PÅ FIREWATER PUMPE | 2 | 5 | COP/to be cancelled | Hold Step | 72 | 72 | 0 | APPR PMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /01/GC-P-402B | FIREWATER PUMP | NOSD | 2020-06-05
| MTN-MECH | 2021-11-10 | 7:00 | 2020-09-03 | WPM | C | V | 2021-11-10 | 8:36 | Business Critical | 2400065313 | 0010 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TRANSMITTER, KALIBRER | 0 | 5 |  | Hold Step | 0.4 | 0.4 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-10 | 8:36 | 2020-09-03 | WPM | C | V | 2021-11-10 | 10:36 | Business Critical | 2400065313 | 0060 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SMØREOILE, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-10 | 10:36 | 2020-09-03 | WPM | C | V | 2021-11-10 | 12:36 | Business Critical | 2400065313 | 0070 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | MOTOR, SAMPLING OLIE | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-10 | 12:36 | 2020-09-03 | WPM | C | V | 2021-11-10 | 14:36 | Business Critical | 2400065313 | 0090 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | FILTER, UDSKIFT | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-10 | 14:36 | 2020-09-03 | WPM | C | V | 2021-11-10 | 16:36 | Business Critical | 2400065313 | 0100 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | FILTER, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-10 | 16:36 | 2020-09-03 | WPM | C | V | 2021-11-10 | 17:48 | Business Critical | 2400065313 | 0120 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TRANSMITTER, CALIBRER | 0 | 5 |  | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-10 | 17:48 | 2020-09-03 | WPM | C | V | 2021-11-11 | 7:48 | Business Critical | 2400065313 | 0150 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 7:48 | 2020-09-03 | WPM | C | V | 2021-11-11 | 9:48 | Business Critical | 2400065313 | 0160 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | PUMPE, INSPICER | 0 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 9:48 | 2020-09-03 | WPM | C | V | 2021-11-11 | 10:36 | Business Critical | 2400065313 | 0180 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | PUSH BUTTON, FUNKTIONS TEST | 0 | 5 |  | Hold Step | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 10:36 | 2020-09-03 | WPM | C | V | 2021-11-11 | 11:24 | Business Critical | 2400065313 | 0210 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | PUSH BUTTON, RENGØR MEKANISK | 0 | 5 |  | Hold Step | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 11:24 | 2020-09-03 | WPM | C | V | 2021-11-11 | 13:24 | Business Critical | 2400065313 | 0240 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SKUEGLAS, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 13:24 | 2020-09-03 | WPM | C | V | 2021-11-11 | 15:24 | Business Critical | 2400065313 | 0250 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 15:24 | 2020-09-03 | WPM | C | V | 2021-11-11 | 17:24 | Business Critical | 2400065313 | 0260 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TANK, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-11 | 17:24 | 2020-09-03 | WPM | C | V | 2021-11-12 | 7:24 | Business Critical | 2400065313 | 0270 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TANK, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-12 | 7:24 | 2020-09-03 | WPM | C | V | 2021-11-12 | 15:24 | Business Critical | 2400065313 | 0280 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TANK, OLIE SKIFT | 1 | 5 |  | Hold Step | 2 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-12 | 15:24 | 2020-09-03 | WPM | C | V | 2021-11-12 | 17:24 | Business Critical | 2400065313 | 0290 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | KØLER, RENGØR | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-12 | 17:24 | 2020-09-03 | WPM | C | V | 2021-11-13 | 7:24 | Business Critical | 2400065313 | 0300 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | KØLER, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-13 | 7:24 | 2020-09-03 | WPM | C | V | 2021-11-13 | 9:24 | Business Critical | 2400065313 | 0310 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | KØLER, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-13 | 9:24 | 2020-09-03 | WPM | C | V | 2021-11-13 | 13:24 | Business Critical | 2400065313 | 0320 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | VENTIL, JUSTER SP | 1 | 5 |  | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-13 | 13:24 | 2020-09-03 | WPM | C | V | 2021-11-13 | 15:24 | Business Critical | 2400065313 | 0330 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-13 | 15:24 | 2020-09-03 | WPM | C | V | 2021-11-13 | 17:24 | Business Critical | 2400065313 | 0340 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | AKTUATOR, FUNKTIONS TEST | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-14 | 7:24 | 2020-09-03 | WPM | C | V | 2021-11-14 | 9:24 | Business Critical | 2400065313 | 0360 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | AKTUATOR, LEAK TEST | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-14 | 9:24 | 2020-09-03 | WPM | C | V | 2021-11-14 | 11:24 | Business Critical | 2400065313 | 0370 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | AKTUATOR, INSPICER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-14 | 11:24 | 2020-09-03 | WPM | C | V | 2021-11-14 | 15:24 | Business Critical | 2400065313 | 0380 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-14 | 15:24 | 2020-09-03 | WPM | C | V | 2021-11-14 | 17:24 | Business Critical | 2400065313 | 0390 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | TRANSMITTER, KALIBRER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-14 | 17:24 | 2020-09-03 | WPM | C | V | 2021-11-15 | 7:24 | Business Critical | 2400065313 | 0400 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | REGULATOR, JUSTER SP | 0 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-15 | 7:24 | 2020-09-03 | WPM | C | V | 2021-11-15 | 9:24 | Business Critical | 2400065313 | 0420 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | REGULATOR, LEAK TEST | 0 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-15 | 9:24 | 2020-09-03 | WPM | C | V | 2021-11-15 | 13:24 | Business Critical | 2400065313 | 0440 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | KONVERTER, RENGØR | 1 | 5 |  | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-15 | 13:24 | 2020-09-03 | WPM | C | V | 2021-11-15 | 15:24 | Business Critical | 2400065313 | 0450 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | KONVERTER, KALIBRER | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-15 | 15:24 | 2020-09-03 | WPM | C | V | 2021-11-16 | 7:24 | Business Critical | 2400065313 | 0460 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-16 | 7:24 | 2020-09-03 | WPM | C | V | 2021-11-16 | 9:24 | Business Critical | 2400065313 | 0470 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-16 | 9:24 | 2020-09-03 | WPM | C | V | 2021-11-18 | 17:24 | Business Critical | 2400065313 | 0480 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | CL, RENGØR | 1 | 5 |  | Hold Step | 8 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-18 | 17:24 | 2020-09-03 | WPM | C | V | 2021-11-18 | 18:36 | Business Critical | 2400065313 | 0490 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SWITCH, RENGØR | 0 | 5 |  | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-18 | 18:36 | 2020-09-03 | WPM | C | V | 2021-11-19 | 7:48 | Business Critical | 2400065313 | 0510 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SWITCH, FUNKTIONS TEST | 0 | 5 |  | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-19 | 7:48 | 2020-09-03 | WPM | C | V | 2021-11-19 | 9:00 | Business Critical | 2400065313 | 0530 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 |  | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-19 | 9:00 | 2020-09-03 | WPM | C | V | 2021-11-19 | 13:00 | Business Critical | 2400065313 | 0560 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | HEATER, ISOLATIONS TEST | 1 | 5 |  | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-19 | 13:00 | 2020-09-03 | WPM | C | V | 2021-11-19 | 14:12 | Business Critical | 2400065313 | 0580 | 3Y CRUDE OIL PUMP A-117G, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 |  | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-04-04
| MTN-MECH | 2021-11-08 | 7:00 | 2020-07-17 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400065314 | 0010 | 1Y CRUDE PUMP A-117G, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-05-18
| MTN-MECH | 2021-11-08 | 7:00 | 2020-08-21 | WPM | C |  | 2021-11-08 | 19:00 | Business Critical | 2400065431 | 0010 | 1Y OLIE FRA ROLF (TIE IN) VALVE/INST | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /12/INSTRUMENTS | INSTRUMENTS |  | 2020-06-10
| MTN-MECH | 2021-11-08 | 7:00 | 2020-07-25 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400065455 | 0010 | 1Y LIFT GAS S/D PANEL | LIFT GAS S/D PANEL CHECK | 1 | 5 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /B /07/GB-FP-1398 | LIFT GAS S/D PANEL |  | 2020-05-14
| MTN-MECH | 2021-11-08 | 7:00 | 2020-10-09 | WPM | B | V | 2021-11-09 | 11:00 | Safety & Env.Related | 2400065461 | 0010 | 3Y DAGMAR EKSPORT OLIE PUMPER | TL-3YA DAGMAR EKSPORT OLIE PUMPER | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /23/GOFA-P-3601 | CRUDE OIL EXPORT PUMP DAGMAR OIL |  | 2020-06-07
| MTN-MECH | 2021-11-08 | 7:00 | 2020-08-07 | WPM | C | V | 2021-11-22 | 15:00 | Business Critical | 2400065550 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117G | INSTRUMENT VENTILER - GENERELT | 1 | 5 | Dobbel/2400125984 | Hold Step | 44 | 44 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117G | CRUDE OIL TRANSFER SYSTEM |  | 2020-05-18
| MTN-MECH | 2021-11-08 | 7:00 | 2020-07-20 | WPM | B | V | 2021-11-23 | 19:00 | Safety & Env.Related | 2400065584 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117F | INSTRUMENT VENTILER - GENERELT | 1 | 5 | Dobbel/2400125708 | Hold Step | 48 | 48 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /E /25/GEA-P-117F | CRUDE OIL EXPORT PUMP |  | 2020-05-12
| MTN-MECH | 2021-11-08 | 7:00 | 2020-10-14 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400065837 | 0010 | 1Y CHEMICAL INJEC. RACK GA-A-1202, GB-A | TL-1YA CHEMICAL INJEC. RACK GA-A-1202, G | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /A /75/GA-A-1202 | CHEMICAL INJ. RACK | NOSD | 2020-08-02
| MTN-MECH | 2021-11-08 | 7:00 | 2020-10-27 | WPM | D | S | 2021-11-09 | 11:00 | Non Critical | 2400065908 | 0010 | 1Y UTIL/INSTR AIR HOSE REELS | TL-1Y UTIL/INSTR AIR HOSE REELS | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/INST-AIR-HOSEREELS | INST AIR HOSE REELS |  | 2020-07-25
| MTN-MECH | 2021-11-08 | 7:00 | 2020-10-22 | WPM | B | V | 2021-11-23 | 19:00 | Safety & Env.Related | 2400076940 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117C | INSTRUMENT VENTILER - GENERELT | 1 | 5 | Dobbel/2400115934 | Hold Step | 48 | 48 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /E /25/GEA-P-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-09-22
| MTN-MECH | 2021-11-08 | 7:00 | 2020-11-10 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400078623 | 0010 | 1Y CRUDE PUMP A-117C, ASSU CHECK IP-01 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-11-10 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400078624 | 0010 | 1Y CRUDE PUMP A-117C, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-11-28 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400085212 | 0010 | 5Y BREATHING AIR STATION A-5417 | BREATHING AIR SYSTEM INSPECTION,, | 1 | 5 |  | Refurbish | 10 | 10 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2020-08-24
| MTN-MECH | 2021-11-08 | 7:00 | 2020-12-17 | WPM | C | I | 2021-11-09 | 17:00 | Business Critical | 2400087126 | 0010 | 1Y CHEMICAL INJECTION, BIOCIDE - GOE | TL-1YA CHEMICAL INJECTION, BIOCIDE - GOE | 1 | 5 |  |  | 5.5 | 5.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /75/GEA-P-121 | BIOCIDE INJECTION SYSTEM | NOSD | 2020-11-11
| MTN-MECH | 2021-11-08 | 7:00 | 2020-12-20 | WPM | C | V | 2021-11-08 | 8:12 | Business Critical | 2400087216 | 0010 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | TRANSMITTER, CALIBRER | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 8:12 | 2020-12-20 | WPM | C | V | 2021-11-08 | 10:12 | Business Critical | 2400087216 | 0030 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 10:12 | 2020-12-20 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400087216 | 0040 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUSH BUTTON, RENGØR MEKANISK | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 11:00 | 2020-12-20 | WPM | C | V | 2021-11-08 | 11:48 | Business Critical | 2400087216 | 0070 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUSH BUTTON, FUNKTIONS TEST | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 11:48 | 2020-12-20 | WPM | C | V | 2021-11-08 | 13:48 | Business Critical | 2400087216 | 0100 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 13:48 | 2020-12-20 | WPM | C | V | 2021-11-08 | 15:48 | Business Critical | 2400087216 | 0110 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | TANK, INSPICER | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 15:48 | 2020-12-20 | WPM | C | V | 2021-11-08 | 17:48 | Business Critical | 2400087216 | 0120 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | AKTUATOR, FUNKTIONS TEST | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 17:48 | 2020-12-20 | WPM | C | V | 2021-11-09 | 9:48 | Business Critical | 2400087216 | 0130 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | VENTIL, JUSTER SP | 1 | 5 | Dobbel/2400125966 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-09 | 9:48 | 2020-12-20 | WPM | C | V | 2021-11-09 | 11:48 | Business Critical | 2400087216 | 0140 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-09 | 11:48 | 2020-12-20 | WPM | C | V | 2021-11-09 | 13:48 | Business Critical | 2400087216 | 0150 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | AKTUATOR, INSPICER | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-09 | 13:48 | 2020-12-20 | WPM | C | V | 2021-11-09 | 17:48 | Business Critical | 2400087216 | 0160 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 | Dobbel/2400125966 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-09 | 17:48 | 2020-12-20 | WPM | C | V | 2021-11-10 | 9:48 | Business Critical | 2400087216 | 0170 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | KONVERTER, RENGØR | 1 | 5 | Dobbel/2400125966 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 9:48 | 2020-12-20 | WPM | C | V | 2021-11-10 | 11:48 | Business Critical | 2400087216 | 0180 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | KONVERTER, KALIBRER | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 11:48 | 2020-12-20 | WPM | C | V | 2021-11-10 | 13:48 | Business Critical | 2400087216 | 0190 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | TRANSMITTER, KALIBRER | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 13:48 | 2020-12-20 | WPM | C | V | 2021-11-10 | 15:48 | Business Critical | 2400087216 | 0200 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | FILTER, UDSKIFT | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 15:48 | 2020-12-20 | WPM | C | V | 2021-11-13 | 11:48 | Business Critical | 2400087216 | 0220 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | CL, RENGØR | 1 | 5 | Dobbel/2400125966 | Hold Step | 8 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-13 | 11:48 | 2020-12-20 | WPM | C | V | 2021-11-13 | 13:48 | Business Critical | 2400087216 | 0230 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-13 | 13:48 | 2020-12-20 | WPM | C | V | 2021-11-13 | 15:48 | Business Critical | 2400087216 | 0240 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | LEJE, INSPICER | 1 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-13 | 15:48 | 2020-12-20 | WPM | C | V | 2021-11-14 | 7:48 | Business Critical | 2400087216 | 0250 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 | Dobbel/2400125966 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-14 | 7:48 | 2020-12-20 | WPM | C | V | 2021-11-14 | 11:48 | Business Critical | 2400087216 | 0260 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 | Dobbel/2400125966 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-14 | 11:48 | 2020-12-20 | WPM | C | V | 2021-11-14 | 13:00 | Business Critical | 2400087216 | 0280 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | SWITCH, FUNKTIONS TEST | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-14 | 13:00 | 2020-12-20 | WPM | C | V | 2021-11-14 | 15:00 | Business Critical | 2400087216 | 0300 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-14 | 15:00 | 2020-12-20 | WPM | C | V | 2021-11-14 | 17:00 | Business Critical | 2400087216 | 0320 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-14 | 17:00 | 2020-12-20 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400087216 | 0350 | 1Y CRUDE OIL PUMP A-117C, CALENDAR PM | TRANSMITTER, KALIBRER | 0 | 5 | Dobbel/2400125966 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 7:00 | 2020-12-23 | WPM | C | V | 2021-11-27 | 11:00 | Business Critical | 2400087222 | 0010 | 3Y SKJOLD EXPORT PUMPS | TL-3YA SKJOLD EXPORT PUMPS | 1 | 5 |  |  | 58 | 58 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /23/GOFB-P-3611 | TRANSFER OF SKJOLD CRUDE OIL |  | 2020-10-10
| MTN-MECH | 2021-11-08 | 7:00 | 2020-12-26 | WPM | C | I | 2021-11-11 | 19:00 | Business Critical | 2400087392 | 0010 | 1Y DEMULSIFIER INJECTION GOF-P-3913/39 | 09.09.2012 | 1 | 5 |  | Hold Step | 12 | 12 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /75/GOFA-P-3913 | RECIPROCATING PUMP | NOSD | 2020-11-20
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-06 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400089163 | 0010 | 1Y CRUDE PUMP A-117E, ASSU CHECK IP-01 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117E | CRUDE OIL TRANSFER SYSTEM |  | 2020-12-07
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-06 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400089164 | 0010 | 1Y CRUDE PUMP A-117E, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117E | CRUDE OIL TRANSFER SYSTEM |  | 2020-12-07
| MTN-MECH | 2021-11-10 | 7:00 | 2021-01-08 | WPM | C | V | 2021-11-10 | 7:00 | Business Critical | 2400089876 | 0010 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | TRANSMITTER, KALIBRER | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.4 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 7:29 | 2021-01-08 | WPM | C | V | 2021-11-10 | 7:29 | Business Critical | 2400089876 | 0060 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SMØREOILE, INSPICER | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 8:21 | 2021-01-08 | WPM | C | V | 2021-11-10 | 8:21 | Business Critical | 2400089876 | 0070 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | MOTOR, SAMPLING OLIE | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 9:14 | 2021-01-08 | WPM | C | V | 2021-11-10 | 11:14 | Business Critical | 2400089876 | 0090 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | FILTER, UDSKIFT | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0.5 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 10:07 | 2021-01-08 | WPM | C | V | 2021-11-10 | 10:07 | Business Critical | 2400089876 | 0110 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | TRANSMITTER, CALIBRER | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 10:59 | 2021-01-08 | WPM | C | V | 2021-11-10 | 12:59 | Business Critical | 2400089876 | 0130 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0.5 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 11:52 | 2021-01-08 | WPM | C | V | 2021-11-10 | 11:52 | Business Critical | 2400089876 | 0140 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | PUSH BUTTON, FUNKTIONS TEST | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.2 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 11:52 | 2021-01-08 | WPM | C | V | 2021-11-10 | 11:52 | Business Critical | 2400089876 | 0170 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | PUSH BUTTON, RENGØR MEKANISK | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.2 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 11:52 | 2021-01-08 | WPM | C | V | 2021-11-10 | 11:52 | Business Critical | 2400089876 | 0200 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 12:44 | 2021-01-08 | WPM | C | V | 2021-11-10 | 12:44 | Business Critical | 2400089876 | 0210 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | TANK, INSPICER | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 13:35 | 2021-01-08 | WPM | C | V | 2021-11-10 | 13:35 | Business Critical | 2400089876 | 0220 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | VENTIL, JUSTER SP | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 1 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 16:27 | 2021-01-08 | WPM | C | V | 2021-11-10 | 16:27 | Business Critical | 2400089876 | 0230 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-10 | 17:18 | 2021-01-08 | WPM | C | V | 2021-11-10 | 17:18 | Business Critical | 2400089876 | 0240 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | AKTUATOR, FUNKTIONS TEST | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 7:01 | 2021-01-08 | WPM | C | V | 2021-11-11 | 7:01 | Business Critical | 2400089876 | 0260 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | AKTUATOR, LEAK TEST | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 7:52 | 2021-01-08 | WPM | C | V | 2021-11-11 | 7:52 | Business Critical | 2400089876 | 0270 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | AKTUATOR, INSPICER | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 8:44 | 2021-01-08 | WPM | C | V | 2021-11-11 | 8:44 | Business Critical | 2400089876 | 0280 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 1 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 11:34 | 2021-01-08 | WPM | C | V | 2021-11-11 | 11:34 | Business Critical | 2400089876 | 0290 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | TRANSMITTER, KALIBRER | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 12:25 | 2021-01-08 | WPM | C | V | 2021-11-11 | 12:25 | Business Critical | 2400089876 | 0300 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | KONVERTER, RENGØR | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 1 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 15:16 | 2021-01-08 | WPM | C | V | 2021-11-11 | 15:16 | Business Critical | 2400089876 | 0310 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | KONVERTER, KALIBRER | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-11 | 16:07 | 2021-01-08 | WPM | C | V | 2021-11-13 | 16:07 | Business Critical | 2400089876 | 0320 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SEAL, UDSKIFT | 2 | 5 | Dobbel/2400128023 | Pick/Pack | 12 | 24 | 12 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-15 | 14:57 | 2021-01-08 | WPM | C | V | 2021-11-15 | 14:57 | Business Critical | 2400089876 | 0330 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | CL, RENGØR | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 8 | 12 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-18 | 9:47 | 2021-01-08 | WPM | C | V | 2021-11-18 | 9:47 | Business Critical | 2400089876 | 0340 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.5 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-18 | 10:36 | 2021-01-08 | WPM | C | V | 2021-11-18 | 10:36 | Business Critical | 2400089876 | 0350 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 1 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-18 | 13:25 | 2021-01-08 | WPM | C | V | 2021-11-18 | 13:25 | Business Critical | 2400089876 | 0360 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SWITCH, RENGØR | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.3 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-18 | 13:26 | 2021-01-08 | WPM | C | V | 2021-11-18 | 13:26 | Business Critical | 2400089876 | 0380 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SWITCH, FUNKTIONS TEST | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.3 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-18 | 13:27 | 2021-01-08 | WPM | C | V | 2021-11-18 | 13:27 | Business Critical | 2400089876 | 0400 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.3 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-18 | 13:28 | 2021-01-08 | WPM | C | V | 2021-11-18 | 13:28 | Business Critical | 2400089876 | 0420 | 2Y CRUDE OIL PUMP A-117F, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 | Dobbel/2400128023 | Pick/Pack | 0 | 0.3 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2020-11-14
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-10 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400089908 | 0010 | 1Y BREATHING AIR STATION GA-A-1212 | BREATHING AIR SYSTEM INSPECTION,, | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /A /02/GA-A-1212 | PRESSURE REDUCTION STATION | NOSD | 2020-12-05
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-08 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400089938 | 0010 | 1Y BREATHING AIR STATION A-5413 | BREATHING AIR PRESS REDUCTION SYSTEM, TY | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2020-12-03
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-14 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400096752 | 0010 | 1Y SODIUM HYPOCHLORITE INJECTION GOF-P- | TL-1YA SODIUM HYPOCHLORITE INJECTION GOF | 1 | 5 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3905 | SODIUM HYPOCHLORITE PUMP, 50 L/HR |  | 2020-12-09
| MTN-MECH | 2021-11-08 | 7:00 | 2021-01-15 | WPM | C | I | 2021-11-08 | 19:00 | Business Critical | 2400096753 | 0010 | 1Y H2S SCAV. INJEC, GOF-P-3909 | KONTROLRUM ADVISERES OM AT PUMPEN STOPPE | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3909 | H2S SCAVENGER PUMP |  | 2020-12-10
| MTN-MECH | 2021-11-08 | 7:00 | 2021-02-09 | WPM | B | V | 2021-11-08 | 15:00 | Safety & Env.Related | 2400101673 | 0010 | 6M TILSTDSCHK S/D VENTIL, GC-ESDV-09533 | DETTE CHECK, SKAL UDFØRES I SAMRÅD MED C | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-02-21 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400102346 | 0010 | 5Y BREATHING AIR STATION GB-A-5406 | BREATHING AIR SYSTEM INSPECTION,, | 1 | 5 |  | Hold Step | 10 | 10 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /B /02/GB-A-5406 | BOTTLE BANK - BREATHING AIR | NOSD | 2020-11-17
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-01 | WPM | C | I | 2021-11-13 | 13:00 | Business Critical | 2400102985 | 0010 | 1Y ANTIFOAM PUMP SKID, GC-A-0289 | 08.09.2012 | 1 | 5 |  |  | 16.5 | 16.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-A-0289 | ANTIFOAM INJECTION PACKAGE |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-01 | WPM | C | V | 2021-11-08 | 8:12 | Business Critical | 2400103044 | 0010 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | TRANSMITTER, CALIBRER | 0 | 3 | Dobbel/2400117339 | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 8:12 | 2021-03-01 | WPM | C | V | 2021-11-08 | 10:12 | Business Critical | 2400103044 | 0030 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 3 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 10:12 | 2021-03-01 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400103044 | 0040 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | PUSH BUTTON, RENGØR MEKANISK | 0 | 5 | Dobbel/2400117339 | Hold Step | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 11:00 | 2021-03-01 | WPM | C | V | 2021-11-08 | 11:48 | Business Critical | 2400103044 | 0070 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | PUSH BUTTON, FUNKTIONS TEST | 0 | 5 | Dobbel/2400117339 | Hold Step | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 11:48 | 2021-03-01 | WPM | C | V | 2021-11-08 | 13:48 | Business Critical | 2400103044 | 0100 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 13:48 | 2021-03-01 | WPM | C | V | 2021-11-08 | 15:48 | Business Critical | 2400103044 | 0110 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | TANK, INSPICER | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 15:48 | 2021-03-01 | WPM | C | V | 2021-11-08 | 17:48 | Business Critical | 2400103044 | 0120 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | AKTUATOR, FUNKTIONS TEST | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 17:48 | 2021-03-01 | WPM | C | V | 2021-11-09 | 9:48 | Business Critical | 2400103044 | 0130 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | VENTIL, JUSTER SP | 1 | 5 | Dobbel/2400117339 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-09 | 9:48 | 2021-03-01 | WPM | C | V | 2021-11-09 | 11:48 | Business Critical | 2400103044 | 0140 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-09 | 11:48 | 2021-03-01 | WPM | C | V | 2021-11-09 | 13:48 | Business Critical | 2400103044 | 0150 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | AKTUATOR, INSPICER | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-09 | 13:48 | 2021-03-01 | WPM | C | V | 2021-11-09 | 17:48 | Business Critical | 2400103044 | 0160 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 | Dobbel/2400117339 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-09 | 17:48 | 2021-03-01 | WPM | C | V | 2021-11-10 | 9:48 | Business Critical | 2400103044 | 0170 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | KONVERTER, RENGØR | 1 | 5 | Dobbel/2400117339 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-10 | 9:48 | 2021-03-01 | WPM | C | V | 2021-11-10 | 11:48 | Business Critical | 2400103044 | 0180 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | KONVERTER, KALIBRER | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-10 | 11:48 | 2021-03-01 | WPM | C | V | 2021-11-10 | 13:48 | Business Critical | 2400103044 | 0190 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | TRANSMITTER, KALIBRER | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-10 | 13:48 | 2021-03-01 | WPM | C | V | 2021-11-10 | 15:48 | Business Critical | 2400103044 | 0200 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | FILTER, UDSKIFT | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-10 | 15:48 | 2021-03-01 | WPM | C | V | 2021-11-13 | 11:48 | Business Critical | 2400103044 | 0220 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | CL, RENGØR | 1 | 5 | Dobbel/2400117339 | Hold Step | 8 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-13 | 11:48 | 2021-03-01 | WPM | C | V | 2021-11-13 | 13:48 | Business Critical | 2400103044 | 0230 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-13 | 13:48 | 2021-03-01 | WPM | C | V | 2021-11-13 | 15:48 | Business Critical | 2400103044 | 0240 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | LEJE, INSPICER | 1 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-13 | 15:48 | 2021-03-01 | WPM | C | V | 2021-11-14 | 7:48 | Business Critical | 2400103044 | 0250 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 | Dobbel/2400117339 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-14 | 7:48 | 2021-03-01 | WPM | C | V | 2021-11-14 | 11:48 | Business Critical | 2400103044 | 0260 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 | Dobbel/2400117339 | Hold Step | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-14 | 11:48 | 2021-03-01 | WPM | C | V | 2021-11-14 | 13:00 | Business Critical | 2400103044 | 0280 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | SWITCH, FUNKTIONS TEST | 0 | 5 | Dobbel/2400117339 | Hold Step | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-14 | 13:00 | 2021-03-01 | WPM | C | V | 2021-11-14 | 15:00 | Business Critical | 2400103044 | 0300 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-14 | 15:00 | 2021-03-01 | WPM | C | V | 2021-11-14 | 17:00 | Business Critical | 2400103044 | 0320 | 1Y CRUDE OIL PUMP A-117A, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 | Dobbel/2400117339 | Hold Step | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-01-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-03 | WPM | C | V | 2021-11-09 | 11:00 | Business Critical | 2400103073 | 0010 | 1Y CRUDE OIL HEATING | GOF-34A01 PM-CODE: | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /20/INSTRUMENTATION | SEPARATION INSTRUMENTATION | NOSD | 2021-01-26
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-16 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400105581 | 0020 | 3Y SSSV BOOSTER PANEL - GOA | REGISTRATION OF WORKING HOURS | 1 | 5 |  | Hold Step | 21 | 21 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /A /07/GA-FP-1215 | SSSV BOOSTER PANEL N-61/W61 | NOSD | 2021-01-01
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-19 | WPM | C | I | 2021-11-09 | 13:00 | Business Critical | 2400105660 | 0010 | 1Y OXYGEN SCAVENGER INJECTION GOF-P-390 | TL-1YA OXYGEN SCAVENGER INJECTION GOF-P- | 1 | 5 |  |  | 4.5 | 4.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3907 | OXYGEN SCAVENGER PUMP |  | 2021-02-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-02-19 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400105892 | 0010 | 3M FW PUMPS GC-P-401A/B AND P-402A/B | 3M FW PUMPS GC-P-401A/B + 402A/B | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/FW-PUMPS | FIREWATER PUMPS | NOSD | 2021-02-08
| MTN-MECH | 2021-11-08 | 7:00 | 2021-03-27 | WPM | C | S | 2021-11-09 | 11:00 | Business Critical | 2400106126 | 0010 | 6M KØLEVANDSFILTRE GC-F-402A/B/C | REGISTRATION OF WORKING HOURS | 1 | 8 | +2100030939 | (5)After/2100029442 | 4 | 4 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /51/GC-F-402A | COOLING WATER FILTER |  | 2021-03-08
| MTN-MECH | 2021-11-08 | 7:00 | 2021-04-09 | WPM | C | I | 2021-11-08 | 19:00 | Business Critical | 2400108387 | 0010 | 1Y KEMIKALIE INJECTION PUMPE GOF-P-3906 | TL-1YAKEMIKALIE INJECTION PUMPE GOF-P-39 | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /75/GOFA-P-3906 | BIOCIDE PUMP |  | 2021-03-04
| MTN-MECH | 2021-11-08 | 7:00 | 2021-04-11 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400108420 | 0010 | 1Y CRUDE PUMP A-117B, ASSU CHECK IP-01 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-03-12
| MTN-MECH | 2021-11-08 | 7:00 | 2021-04-11 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400108422 | 0010 | 1Y CRUDE PUMP A-117B, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-03-12
| MTN-MECH | 2021-11-08 | 7:00 | 2021-04-13 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400115939 | 0010 | 3Y COOLING WATER PUMP, P-5301 | REGISTRATION OF WORKING HOURS | 1 | 5 |  | Hold Step | 5 | 5 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /76/GOFA-A-5301 | SKID |  | 2021-01-29
| MTN-MECH | 2021-11-08 | 15:00 | 2021-05-02 | WPM | B | S | 2021-11-10 | 19:00 | Safety & Env.Related | 2400116213 | 0020 | 3M AVIATION FUEL DISPENSER - GOC | 6M AVIATION DISPENSER UNIT: | 1 | 5 |  |  | 7 | 7 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-04-22
| MTN-MECH | 2021-11-08 | 7:00 | 2021-05-07 | WPM | B | V | 2021-11-11 | 11:00 | Safety & Env.Related | 2400116474 | 0010 | 1Y AIR COMP GC-C-901A | 1Y AIR COMP. GC-C-901A | 1 | 5 |  | STPO Step | 10 | 10 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /07/GC-C-901A | SCREW COMPR. FOR INSTR AND UTILITY AIR |  | 2021-04-07
| MTN-MECH | 2021-11-08 | 7:00 | 2021-06-11 | WPM | C | I | 2021-11-10 | 17:00 | Business Critical | 2400125701 | 0010 | 3Y H2S SCAVENGER INJECTION | 27.08.2012 | 1 | 5 |  |  | 8.5 | 8.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-A-1096 | H2S SCAVENGER CHEM INJECTION PUMP SKID |  | 2021-03-29
| MTN-MECH | 2021-11-08 | 7:00 | 2021-06-19 | WPM | D | V | 2021-11-08 | 19:00 | Non Critical | 2400125843 | 0010 | 1Y BAUER KOMPRESSOR | TL-YA BAUER KOMPRESSOR | 1 | 8 | Forkert mat/030621 | PO Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PPRT PRC SETC GMPS MANC | GO /E /07/GEB-C-5440 | COMPRESSOR |  | 2021-05-03
| MTN-MECH | 2021-11-08 | 7:00 | 2021-06-21 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400125965 | 0010 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-06-10
| MTN-MECH | 2021-11-08 | 9:00 | 2021-06-21 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400125965 | 0020 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-06-10
| MTN-MECH | 2021-11-08 | 11:00 | 2021-06-21 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400125965 | 0030 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-06-10
| MTN-MECH | 2021-11-08 | 15:00 | 2021-06-21 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400125965 | 0040 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-06-10
| MTN-MECH | 2021-11-08 | 7:00 | 2021-06-26 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400126182 | 0010 | 1Y CRUDE PUMP A-117A, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-05-27
| MTN-MECH | 2021-11-08 | 7:00 | 2021-07-08 | WPM | B | V | 2021-11-09 | 19:00 | Safety & Env.Related | 2400127976 | 0010 | 1Y W-MIST NOZ GC-A-0488 FOR GC-G-802 | 21.02.2013 | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /01/GC-A-0488 | FIREWATER MIST SKID FOR G-802 | NOSD | 2021-06-08
| MTN-MECH | 2021-11-08 | 7:00 | 2021-07-13 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400128026 | 0010 | 3M RÅOLIE SHIPPING PUMPE - GEA-P-117D | TL-3M RÅOLIE SHIPPING PUMPE - GEA-P-117D | 1 | 5 | DB/2400115924/2400075413 |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-P-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-07-02
| MTN-MECH | 2021-11-08 | 7:00 | 2021-07-12 | WPM | C | V | 2021-11-09 | 15:00 | Business Critical | 2400128030 | 0010 | 3Y COOLING WATER PUMP, P-5302 | REGISTRATION OF WORKING HOURS | 1 | 5 |  | PO Step | 5 | 5 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /76/GOFA-A-5301 | SKID |  | 2021-04-29
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-08 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400129026 | 0010 | 3Y KØLEVANDSCIRK.PUMP. + EKSP.TANK GC-P- | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /76/GC-T-0500 | COOLING WATER HEAD TANK |  | 2021-05-26
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-10 | WPM | C | I | 2021-11-09 | 11:00 | Business Critical | 2400129028 | 0010 | 3Y WATER CLARIFIER PUMPS | OSP031 HÅNDTERING AF AFFALD FØLGES | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /75/GEA-A-3913 | CHEMICAL INJECTION SKID (WATER CLARIFIER |  | 2021-05-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-08 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400129031 | 0010 | 6M TILSTANDSCHEC S/D VENTIL GC-ESDV-1511 | DETTE CHECK, SKAL UDFØRES I SAMRÅD MED C | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-07-23
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-18 | WPM | A | I | 2021-11-09 | 19:00 | Assurance | 2400129671 | 0010 | 3M INST. + UTILITY AIR DRYER, GC-D-901 A | MICROFILTER, GC-F-901 | 1 | 5 |  | Hold Step | 6 | 6 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-D-901A | AIR DRYER FOR INSTR AND UTILITY AIR |  | 2021-08-08
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-17 | WPM | B | V | 2021-11-10 | 15:00 | Safety & Env.Related | 2400129674 | 0010 | 3M INST. + UTILITY AIR COMP. GC-C-901C | 29.01.2013 | 1 | 5 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-C-901C | SCREW COMPR. FOR INSTR AND UTILITY AIR |  | 2021-08-07
| MTN-MECH | 2021-11-10 | 15:00 | 2021-08-17 | WPM | B | V | 2021-11-13 | 11:00 | Safety & Env.Related | 2400129674 | 0012 | 3M INST. + UTILITY AIR COMP. GC-C-901C | 29.01.2013 | 1 | 5 |  |  | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-C-901C | SCREW COMPR. FOR INSTR AND UTILITY AIR |  | 2021-08-07
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-24 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400129677 | 0010 | 3M LIVBÅD WHITTAKER CA2801 - GOF | INSPECTION GORM F WHITTAKER 3M | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/LIFEBOAT | LIFEBOAT | NOSD | 2021-08-13
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-22 | WPM | B | V | 2021-11-11 | 15:00 | Safety & Env.Related | 2400129681 | 0010 | 6M CHECK AF DELUGE DYSER + RØR | 6M DELUGE TEST GOC | 1 | 5 |  |  | 11 | 11 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /A /01/DELUGE-SKIDS | DELUGE SKIDS | NOSD | 2021-08-06
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-18 | WPM | B | V | 2021-11-23 | 19:00 | Safety & Env.Related | 2400129686 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117B | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  | Hold Step | 48 | 48 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-07-19
| MTN-MECH | 2021-11-08 | 15:00 | 2021-08-26 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400129829 | 0020 | 2Y GOFA-V-3401 - METERING | DEMONTERING OG MONTERING AF METRE | 2 | 5 |  | Hold Step | 16 | 16 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20/METERING | SEPARATION METERING | NOSD | 2021-07-02
| MTN-MECH | 2021-11-08 | 15:00 | 2021-08-26 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400129830 | 0020 | 2Y GOFB-V-3410 - METERING | DEMONTERING OG MONTERING AF METRE | 2 | 5 |  | Refurbish/Return | 16 | 16 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20/METERING | SEPARATION METERING | NOSD | 2021-07-02
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-28 | WPM | D | V | 2021-11-11 | 19:00 | Non Critical | 2400129834 | 0010 | 3M GORM LUB. AND INSP. PLAN | CONDITION INSP ROUND FOR PUMPS/MOTORS | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27 | OILY WATER PROCESSING |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-01 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400129854 | 0010 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 9:00 | 2021-09-01 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400129854 | 0020 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-01 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400129854 | 0030 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | TANK, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 13:00 | 2021-09-01 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400129854 | 0040 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 15:00 | 2021-09-01 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400129854 | 0060 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | CL, RENGØR | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-11 | 11:00 | 2021-09-01 | WPM | C | V | 2021-11-11 | 13:00 | Business Critical | 2400129854 | 0070 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-11 | 13:00 | 2021-09-01 | WPM | C | V | 2021-11-11 | 15:00 | Business Critical | 2400129854 | 0080 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-11 | 15:00 | 2021-09-01 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400129854 | 0090 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-12 | 7:00 | 2021-09-01 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400129854 | 0100 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-12 | 11:00 | 2021-09-01 | WPM | C | V | 2021-11-12 | 13:00 | Business Critical | 2400129854 | 0120 | 6M CRUDE OIL PUMP A-117A, CALENDAR PM | SWITCH, JUSTER SP | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-26 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400129872 | 0010 | 3M LIVBÅDE TYPE VIKING CML 22S | LIVBÅD VIKING CML 22S INSPECTION | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /02/LIFEBOAT | LIFEBOAT | NOSD | 2021-08-15
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-26 | WPM | D | V | 2021-11-11 | 19:00 | Non Critical | 2400129875 | 0010 | 3M LIVBÅDE TYPE VIKING CML 27S | CHECK LIVBÅD VIKING CML 27S | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /02/LIFEBOAT | LIFEBOAT | NOSD | 2021-08-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-01 | WPM | C | I | 2021-11-09 | 9:00 | Business Critical | 2400129883 | 0010 | 6M KØLEVANDGC-03SPUMPER GC-P-403A/B/C | TAG NO. P-403A, P-403B OG P-403C | 1 | 5 |  |  | 3.5 | 3.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /50/GC-P-403A | COOLING WATER PUMP |  | 2021-08-13
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-07 | WPM | C | I | 2021-11-09 | 15:00 | Business Critical | 2400134247 | 0010 | 1Y CHEMICAL INJEC. RACK GA-A-1202, GB-A | TL-1YA CHEMICAL INJEC. RACK GA-A-1202, G | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /A /75/GA-A-1202 | CHEMICAL INJ. RACK | NOSD | 2021-08-02
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-25 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400134248 | 0010 | 1Y BLOCK HCV'S, GC-C-202A | GOC-43Z01 PM-CODE: | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /31/GC-C-202A | IP COMPRESSOR | NOSD | 2021-08-20
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-23 | WPM | C |  | 2021-11-13 | 19:00 | Business Critical | 2400134250 | 0010 | 1Y RENSNING AF DRÆNSYSTEM | P+ID REF: GOCY-05-01057-0001, REV.24 | 1 | 5 |  |  | 18 | 18 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27/P-G | PIPING GROUP |  | 2021-08-18
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C |  | 2021-11-08 | 19:00 | Business Critical | 2400134254 | 0010 | 6M SLANGER FOR HØJTRYKSRENSER | 1. PLACERING AF SLANGERULLER FOR HØ | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /72 | HOT WATER GENERATION AND DISTRIBUTION | NOSD | 2021-08-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-11 | WPM | C | I | 2021-11-09 | 11:00 | Business Critical | 2400134258 | 0010 | 1Y SCALE INHIB, P-3902A/B/C + P-3915A/B | 28.05.2013 | 1 | 5 |  | Hold Step | 4 | 4 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /75/GOFA-A-3902 | SCALE INHIBITOR | NOSD | 2021-08-06
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-23 | WPM | C | V | 2021-11-10 | 13:00 | Business Critical | 2400134259 | 0010 | 1Y RENSNING AF DRÆNSYSTEM | P+ID REF: GOFA-05-01014-0001, REV.19 | 1 | 5 |  |  | 7.5 | 7.5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /28/DRAIN-DISPOSAL | DRAIN DISPOSAL | NOSD | 2021-08-18
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-10 | WPM | D | S | 2021-11-09 | 11:00 | Non Critical | 2400134410 | 0010 | 1Y UTIL/INSTR AIR HOSE REELS | TL-1Y UTIL/INSTR AIR HOSE REELS | 1 | 5 |  |  | 4 | 4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/INST-AIR-HOSEREELS | INST AIR HOSE REELS |  | 2021-07-25
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-09 | WPM | D | V | 2021-11-09 | 19:00 | Non Critical | 2400134418 | 0010 | 3M Preventive Vibration Measurement | COLLECT VIBRATION DATA FROM MOTOR AND PU | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /23 | TRANSFER |  | 2021-09-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-02 | WPM | B | S | 2021-11-08 | 19:00 | Safety & Env.Related | 2400134534 | 0001 | 1M AVIATION FUEL DISPENSER - GOC | AVIATION FUEL - 1M | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-08-29
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-02 | WPM | B | S | 2021-11-08 | 19:00 | Safety & Env.Related | 2400134535 | 0001 | 1M AVIATION FUEL DISPENSER - GOC | AVIATION FUEL - 1M | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-09-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-01 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400134538 | 0010 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-08 | 9:00 | 2021-10-01 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400134538 | 0020 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-08 | 11:00 | 2021-10-01 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400134538 | 0030 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | TANK, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-08 | 13:00 | 2021-10-01 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400134538 | 0040 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-08 | 15:00 | 2021-10-01 | WPM | C | V | 2021-11-11 | 11:00 | Business Critical | 2400134538 | 0060 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | CL, RENGØR | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-11 | 11:00 | 2021-10-01 | WPM | C | V | 2021-11-11 | 13:00 | Business Critical | 2400134538 | 0070 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-11 | 13:00 | 2021-10-01 | WPM | C | V | 2021-11-11 | 15:00 | Business Critical | 2400134538 | 0080 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-11 | 15:00 | 2021-10-01 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400134538 | 0090 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-12 | 7:00 | 2021-10-01 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400134538 | 0100 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-12 | 11:00 | 2021-10-01 | WPM | C | V | 2021-11-12 | 13:00 | Business Critical | 2400134538 | 0120 | 6M CRUDE OIL PUMP A-117B, CALENDAR PM | SWITCH, JUSTER SP | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-12
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-21 | WPM | C | V | 2021-11-08 | 8:12 | Business Critical | 2400134541 | 0010 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | TRANSMITTER, CALIBRER | 0 | 5 |  | GR Onshore 210821 | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 8:12 | 2021-09-21 | WPM | C | V | 2021-11-08 | 10:12 | Business Critical | 2400134541 | 0030 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 10:12 | 2021-09-21 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400134541 | 0040 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | PUSH BUTTON, RENGØR MEKANISK | 0 | 5 |  | GR Onshore 210821 | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-21 | WPM | C | V | 2021-11-08 | 11:48 | Business Critical | 2400134541 | 0070 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | PUSH BUTTON, FUNKTIONS TEST | 0 | 5 |  | GR Onshore 210821 | 0.2 | 0.2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 11:48 | 2021-09-21 | WPM | C | V | 2021-11-08 | 13:48 | Business Critical | 2400134541 | 0100 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 13:48 | 2021-09-21 | WPM | C | V | 2021-11-08 | 15:48 | Business Critical | 2400134541 | 0110 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | TANK, INSPICER | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 15:48 | 2021-09-21 | WPM | C | V | 2021-11-08 | 17:48 | Business Critical | 2400134541 | 0120 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | AKTUATOR, FUNKTIONS TEST | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 17:48 | 2021-09-21 | WPM | C | V | 2021-11-09 | 9:48 | Business Critical | 2400134541 | 0130 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | VENTIL, JUSTER SP | 1 | 5 |  | GR Onshore 210821 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-09 | 9:48 | 2021-09-21 | WPM | C | V | 2021-11-09 | 11:48 | Business Critical | 2400134541 | 0140 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-09 | 11:48 | 2021-09-21 | WPM | C | V | 2021-11-09 | 13:48 | Business Critical | 2400134541 | 0150 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | AKTUATOR, INSPICER | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-09 | 13:48 | 2021-09-21 | WPM | C | V | 2021-11-09 | 17:48 | Business Critical | 2400134541 | 0160 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  | GR Onshore 210821 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-09 | 17:48 | 2021-09-21 | WPM | C | V | 2021-11-10 | 9:48 | Business Critical | 2400134541 | 0170 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | KONVERTER, RENGØR | 1 | 5 |  | GR Onshore 210821 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-10 | 9:48 | 2021-09-21 | WPM | C | V | 2021-11-10 | 11:48 | Business Critical | 2400134541 | 0180 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | KONVERTER, KALIBRER | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-10 | 11:48 | 2021-09-21 | WPM | C | V | 2021-11-10 | 13:48 | Business Critical | 2400134541 | 0190 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | TRANSMITTER, KALIBRER | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-10 | 13:48 | 2021-09-21 | WPM | C | V | 2021-11-10 | 15:48 | Business Critical | 2400134541 | 0200 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | FILTER, UDSKIFT | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-10 | 15:48 | 2021-09-21 | WPM | C | V | 2021-11-13 | 11:48 | Business Critical | 2400134541 | 0220 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | CL, RENGØR | 1 | 5 |  | GR Onshore 210821 | 8 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-13 | 11:48 | 2021-09-21 | WPM | C | V | 2021-11-13 | 13:48 | Business Critical | 2400134541 | 0230 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-13 | 13:48 | 2021-09-21 | WPM | C | V | 2021-11-13 | 15:48 | Business Critical | 2400134541 | 0240 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-13 | 15:48 | 2021-09-21 | WPM | C | V | 2021-11-14 | 7:48 | Business Critical | 2400134541 | 0250 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  | GR Onshore 210821 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-14 | 7:48 | 2021-09-21 | WPM | C | V | 2021-11-14 | 11:48 | Business Critical | 2400134541 | 0260 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  | GR Onshore 210821 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-14 | 11:48 | 2021-09-21 | WPM | C | V | 2021-11-14 | 13:00 | Business Critical | 2400134541 | 0280 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | SWITCH, FUNKTIONS TEST | 0 | 5 |  | GR Onshore 210821 | 0.3 | 0.3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-14 | 13:00 | 2021-09-21 | WPM | C | V | 2021-11-14 | 15:00 | Business Critical | 2400134541 | 0300 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-14 | 15:00 | 2021-09-21 | WPM | C | V | 2021-11-14 | 17:00 | Business Critical | 2400134541 | 0320 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-14 | 17:00 | 2021-09-21 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400134541 | 0350 | 1Y CRUDE OIL PUMP A-117D, CALENDAR PM | TRANSMITTER, KALIBRER | 0 | 5 |  | GR Onshore 210821 | 0.5 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-08-16
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-08 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400134542 | 0010 | 3M CRUDE OIL PUMP A-117E, CALENDAR PM | SMØREOILE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117E | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-27
| MTN-MECH | 2021-11-08 | 9:00 | 2021-10-08 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400134542 | 0020 | 3M CRUDE OIL PUMP A-117E, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117E | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-27
| MTN-MECH | 2021-11-08 | 13:00 | 2021-10-08 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400134542 | 0030 | 3M CRUDE OIL PUMP A-117E, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117E | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-27
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-20 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400134546 | 0010 | 3M CRUDE OIL PUMP A-117C, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-09
| MTN-MECH | 2021-11-08 | 9:00 | 2021-09-20 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400134546 | 0020 | 3M CRUDE OIL PUMP A-117C, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-09
| MTN-MECH | 2021-11-08 | 11:00 | 2021-09-20 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400134546 | 0030 | 3M CRUDE OIL PUMP A-117C, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-09
| MTN-MECH | 2021-11-08 | 15:00 | 2021-09-20 | WPM | C | V | 2021-11-08 | 19:00 | Business Critical | 2400134546 | 0040 | 3M CRUDE OIL PUMP A-117C, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-09
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-08 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400134547 | 0010 | 3M CRUDE OIL PUMP A-117F, CALENDAR PM | SMØREOILE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-27
| MTN-MECH | 2021-11-08 | 9:00 | 2021-10-08 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400134547 | 0020 | 3M CRUDE OIL PUMP A-117F, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-27
| MTN-MECH | 2021-11-08 | 13:00 | 2021-10-08 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400134547 | 0030 | 3M CRUDE OIL PUMP A-117F, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117F | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-27
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-17 | WPM | C | V | 2021-11-08 | 9:00 | Business Critical | 2400134548 | 0010 | 3M CRUDE OIL PUMP A-117G, CALENDAR PM | SMØREOILE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-06
| MTN-MECH | 2021-11-08 | 9:00 | 2021-09-17 | WPM | C | V | 2021-11-08 | 13:00 | Business Critical | 2400134548 | 0020 | 3M CRUDE OIL PUMP A-117G, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-06
| MTN-MECH | 2021-11-08 | 13:00 | 2021-09-17 | WPM | C | V | 2021-11-08 | 15:00 | Business Critical | 2400134548 | 0030 | 3M CRUDE OIL PUMP A-117G, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-06
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-11 | WPM | C | I | 2021-11-11 | 17:00 | Business Critical | 2400134562 | 0010 | 3M H2S SCAVENGER INJECTION | TL-3M H2S SCAVENGER INJECTION | 1 | 5 |  |  | 11.5 | 11.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /75/GC-A-1096 | H2S SCAVENGER CHEM INJECTION PUMP SKID |  | 2021-08-31
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-27 | WPM | D | V | 2021-11-11 | 11:00 | Non Critical | 2400134586 | 0010 | 6M LOW PRESSURE BREATHING AIR MANIFOLDS | BREATHING AIR MANIFOLD INSPECTION | 1 | 5 |  |  | 10 | 10 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2021-09-02
| MTN-MECH | 2021-11-08 | 7:00 | 2021-09-16 | WPM | C | V | 2021-11-12 | 11:00 | Business Critical | 2400134607 | 0010 | 6M SSSV BOOSTER PANEL - GOA | BEMÆRK! | 1 | 5 |  | Hold Step | 13 | 13 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /A /07/GA-FP-1215 | SSSV BOOSTER PANEL N-61/W61 | NOSD | 2021-08-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-08-19 | WPM | B | V | 2021-11-10 | 19:00 | Safety & Env.Related | 2400134635 | 0010 | 3M BRANDVANDS PUMPE GEM-P-408 | FW PUMP INSPECTION AND TEST GEM-M-408 | 1 | 5 |  |  | 9 | 9 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /01/GEM-M-408_1 | FIREWATER SYSTEM |  | 2021-08-09
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-13 | WPM | B | V | 2021-11-23 | 19:00 | Safety & Env.Related | 2400134801 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117D | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  | Hold Step | 48 | 48 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-13
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-12 | WPM | D | I | 2021-11-10 | 15:00 | Non Critical | 2400134802 | 0010 | 6M BREATHING AIR COMPRESSOR GC-A-5401/54 | TL-6M BREATHING AIR COMPRESSOR GC-A-5401 | 1 | 5 |  | Hold Step | 8 | 8 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /02/BREATHING-AIR-SYSTEM | GO /B /02/BREATHING-AIR-SYSTEM | NOSD | 2021-09-17
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-12 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400134804 | 0010 | 3M COOLING WATER PUMP, P-5302 | INSTRUMENTATION FOR, P-5302 | 1 | 5 |  |  | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /76/GOFA-A-5301 | SKID |  | 2021-10-01
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-10 | WPM | B | V | 2021-11-11 | 19:00 | Safety & Env.Related | 2400134805 | 0010 | 6M TILSTANDSCHECK/SMØRING ESD/BD VENTILE | VENTILCHECK | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-09-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-13 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400134806 | 0010 | 6M COOLING WATER PUMP, P-5301 | INSTRUMENTATION FOR, P-5301 | 1 | 5 |  | STPO Step | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /76/GOFA-A-5301 | SKID |  | 2021-09-24
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-17 | WPM | D | V | 2021-11-09 | 15:00 | Non Critical | 2400134876 | 0010 | 6M BREATHING AIR STATION A-5405/5415 | BREATHING AIR PRESS REDUCTION SYSTEM, TY | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2021-09-22
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-18 | WPM | C | V | 2021-11-19 | 19:00 | Business Critical | 2400139143 | 0010 | 6M BOOSTER PUMPER GC-P-101A/B/C/D MODUL2 | BOOSTER-PUMPE | 1 | 5 |  |  | 36 | 36 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /23/GC-P-101A | CRUDE OIL BUSTER PUMP |  | 2021-09-29
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-23 | WPM | D | V | 2021-11-08 | 15:00 | Non Critical | 2400139144 | 0010 | 6M C-202B, S/D VENTILER | 26.11.2012 | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-09-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-23 | WPM | D | V | 2021-11-08 | 19:00 | Non Critical | 2400139145 | 0010 | 6M C-203A, S/D VENTILER | C-203A S/D: | 1 | 5 |  |  | 3 | 3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-09-28
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-23 | WPM | B | V | 2021-11-08 | 15:00 | Safety & Env.Related | 2400139150 | 0010 | 6M C-201/5, S/D VENTILER | C-201/5 S/D: | 1 | 5 |  |  | 2 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-10-07
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-24 | WPM | C | S | 2021-11-11 | 11:00 | Business Critical | 2400139153 | 0010 | 6M SALTVANDSSERVICEPUMPER GC-P-404A/B | 1. TAG NO. PI-0937, PI-0938 OG PI-0939 | 1 | 5 |  |  | 10 | 10 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /50/GC-P-404A | SERVICE WATER SUPPLY PUMP |  | 2021-10-05
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-22 | WPM | B | V | 2021-11-23 | 19:00 | Safety & Env.Related | 2400139156 | 0010 | 1Y RÅOLIE SHIPPING PUMPE - GEA-P-117C | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  | Hold Step | 48 | 48 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-P-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-09-22
| MTN-MECH | 2021-11-09 | 11:00 | 2021-10-21 | WPM | D | I | 2021-11-14 | 9:00 | Non Critical | 2400139157 | 0012 | 6M GLYCOL DEHYDRATION PACKAGE, GC-P-501A | GLYKOL-CIRKULATIONSPUMPE | 1 | 5 |  |  | 14.5 | 14.5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /30/GC-P-501A | GLYCOL CIRCULATING PUMP P-501 A/B |  | 2021-09-26
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-21 | WPM | B | V | 2021-11-10 | 19:00 | Safety & Env.Related | 2400139158 | 0010 | 3M FW PUMP AND ENGINE, GOFA-P-0301 | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 9 | 9 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /01/GOFA-A-1701 | PUMP SYSTEM MODULE | NOSD | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-04 | WPM | C | V | 2021-11-10 | 15:00 | Business Critical | 2400150800 | 0010 | 1Y BLOCK HCV'S, GC-C-202C | GOC-43Z03 PM-CODE: | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /31/GC-C-202C | IP COMPRESSOR | NOSD | 2021-09-29
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-29 | WPM | A | V | 2021-11-09 | 15:00 | Assurance | 2400150801 | 0010 | 3M ONSHORE REG OF OPEN/CLOSE TIMES | GOC-59U01 PM-CODE: | 1 | 3 |  |  | 5 | 5 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-10-19
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-04 | WPM | A | V | 2021-11-08 | 19:00 | Assurance | 2400150802 | 0010 | 3M ONSHORE REG OF OPEN/CLOSE TIMES | GOE-59U01 PM-CODE: | 1 | 3 |  |  | 3 | 3 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-10-25
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-03 | WPM | D |  | 2021-11-09 | 11:00 | Non Critical | 2400150842 | 0010 | 3M AIR FILTER, SMOKE CABINS GOE | UDSKIFTNING AF FILTRE FOR RYGEKABINE | 1 | 5 |  | Hold Step | 4 | 4 | 0 | APPR WMAT AWSD RDBL | APPR OPND | REL PRC SETC MANC | GO /E /82 | LIVING AND WELFARE QTRS | NOSD | 2021-10-19
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-07 | WPM | B | V | 2021-11-11 | 19:00 | Safety & Env.Related | 2400150885 | 0010 | 6M AIR COMP GC-C-901A | 6M COMPRESSOR GC-C-901A | 1 | 5 |  | STPO Step | 12 | 12 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-C-901A | SCREW COMPR. FOR INSTR AND UTILITY AIR |  | 2021-10-22
| MTN-MECH | 2021-11-08 | 15:00 | 2021-11-02 | WPM | B | S | 2021-11-10 | 19:00 | Safety & Env.Related | 2400150903 | 0020 | 3M AVIATION FUEL DISPENSER - GOC | 6M AVIATION DISPENSER UNIT: | 1 | 5 |  |  | 7 | 7 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-10-23
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-10 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400150904 | 0010 | 1Y CRUDE PUMP A-117D, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-10 | WPM | A | V | 2021-11-09 | 11:00 | Assurance | 2400150905 | 0010 | 1Y CRUDE PUMP A-117D, ASSU CHECK SS-01 | TIME SUMMERING 18.12.2018 | 1 | 3 |  |  | 4 | 4 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-10 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400150906 | 0010 | 1Y CRUDE PUMP A-117D, ASSU CHECK IP-01 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-10 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400150907 | 0010 | 1Y CRUDE PUMP A-117C, ASSU CHECK IP-01 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-10 | WPM | B | V | 2021-11-08 | 11:00 | Safety & Env.Related | 2400150908 | 0010 | 1Y CRUDE PUMP A-117C, ASSU CHECK PC-03 | TIME SUMMERING 18.12.2018 | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-10 | WPM | A | V | 2021-11-09 | 11:00 | Assurance | 2400150909 | 0010 | 1Y CRUDE PUMP A-117C, ASSU CHECK SS-01 | TIME SUMMERING 18.12.2018 | 1 | 3 |  |  | 4 | 4 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-05 | WPM | C | I | 2021-11-09 | 19:00 | Business Critical | 2400150911 | 0010 | 1Y LAUNCHER GAS GOE-TYE EP-3803 | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /34/GEA-EP-3803 | GORM GAS EXPORT LAUNCHER |  | 2021-09-30
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-26 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400150916 | 0010 | 1Y BREATHING AIR STATION A-5417 | BREATHING AIR PRESS REDUCTION SYSTEM, TY | 1 | 5 |  | Hold Step | 6 | 6 | 0 | APPR CMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /02/BREATHING-AIR-SYSTEM | BREATHING AIR SYSTEM | NOSD | 2021-09-20
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-03 | WPM | A | V | 2021-11-11 | 19:00 | Assurance | 2400150921 | 0010 | 1Y V-5002, INSTRUMENTER OG PUMPER | TL-YA V-5002, INSTRUMENTER OG PUMPER | 1 | 3 |  |  | 12 | 12 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /27/GC-V-5002 | RETENTION TANK |  | 2021-10-04
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-05 | WPM | C | V | 2021-11-11 | 19:00 | Business Critical | 2400150927 | 0010 | 6M BRISCO PANEL - GOB | BEMÆRK! ARBEJDET UDFØRES EFTER AFTALE OG | 1 | 5 |  | Hold Step | 12 | 12 | 0 | APPR WMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /B /07/WELLHEAD-CONTROL-PANEL | WELLHEAD CONTROL PANEL | NOSD | 2021-10-17
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-29 | WPM | A | V | 2021-11-12 | 11:00 | Assurance | 2400150932 | 0010 | 1Y CORROSION INHIBITOR INJECTION | TL-1YA CORROSION INHIB. INJEC, GOF-P-460 | 1 | 3 |  |  | 13 | 13 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /F /75/GOFA-P-4605 | CORROSION INHIBITOR PUMP |  | 2021-09-29
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-30 | WPM | C | I | 2021-11-08 | 11:00 | Business Critical | 2400150940 | 0010 | 3M DIESEL FORDELINGSPUMPER FIL P-801A/B | REGISTRATION OF WORKING HOURS | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /71/DIESEL-PUMPS | DIESEL PUMPS |  | 2021-10-19
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-29 | WPM | B | V | 2021-11-10 | 19:00 | Safety & Env.Related | 2400150941 | 0010 | 3M BRANDVANDS PUMPE GEM-P-408 | FW PUMP INSPECTION AND TEST GEM-M-408 | 1 | 5 |  |  | 9 | 9 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /01/GEM-M-408_1 | FIREWATER SYSTEM |  | 2021-10-19
| MTN-MECH | 2021-11-08 | 7:00 | 2021-10-04 | WPM | C | I | 2021-11-12 | 15:00 | Business Critical | 2400150943 | 0010 | 3M POT WATER TREATMENT, GOC | VIGTIGT! DETTE CHECK SKAL UDFØRES A | 1 | 5 |  |  | 14 | 14 | 0 | APPR CMAT AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /85/GC-T-420 | TANK | NOSD | 2021-09-23
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-18 | WPM | C | I | 2021-11-14 | 15:00 | Business Critical | 2400151280 | 0010 | 6M INST. + UTILITY AIR DRYER, GC-D-901 A | MICROFILTER, GC-F-901 | 1 | 5 |  | Hold Step | 20 | 20 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /07/GC-D-901A | AIR DRYER FOR INSTR AND UTILITY AIR |  | 2021-10-30
| MTN-MECH | 2021-11-08 | 7:00 | 2021-11-18 | WPM | C | V | 2021-11-09 | 19:00 | Business Critical | 2400151293 | 0010 | 3M RÅOLIE SHIPPING PUMPE - GEA-P-117B | TL-3M RÅOLIE SHIPPING PUMPE - GEA-P-117B | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-P-117B | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-07
| MTN-MECH | 2021-11-15 | 7:00 | 2021-11-25 | WPM | A | V | 2021-11-18 | 11:00 | Assurance | 2400157167 | 0010 | 3M ONSHORE REG OF OPEN/CLOSE TIMES | GOF-59U01 PM-CODE: | 1 | 3 |  |  | 10 | 10 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | NOSD | 2021-11-15
| MTN-MECH | 2021-11-13 | 7:00 | 2021-11-28 | WPM | D | V | 2021-11-16 | 19:00 | Non Critical | 2400157211 | 0010 | 3M GORM LUB. AND INSP. PLAN | CONDITION INSP ROUND FOR PUMPS/MOTORS | 1 | 5 |  |  | 12 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /27 | OILY WATER PROCESSING |  | 2021-11-13
| MTN-MECH | 2021-11-12 | 7:00 | 2021-11-28 | WPM | B | V | 2021-11-12 | 15:00 | Safety & Env.Related | 2400157246 | 0010 | 6M TILSTANDSCHE.S/D VENTIL,GEA-ESDV-3804 | DETTE CHECK, SKAL UDFØRES I SAMRÅD MED C | 1 | 2 |  |  | 2 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /12/GEA-ESDV-38046 | HDA/DFF OIL INLET |  | 2021-11-12
| MTN-MECH | 2021-11-12 | 7:00 | 2021-11-28 | WPM | B | V | 2021-11-13 | 19:00 | Safety & Env.Related | 2400157265 | 0010 | 6M TILSTANDSCHE.HIPPS VENTIL,GEA-ESDV-15 | DETTE CHECK, SKAL UDFØRES I SAMRÅD MED C | 1 | 2 |  |  | 6 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /03/HIPS-SYSTEM | HIPS SYSTEM |  | 2021-11-12
| MTN-MECH | 2021-11-11 | 7:00 | 2021-11-27 | WPM | B | V | 2021-11-12 | 11:00 | Safety & Env.Related | 2400157298 | 0010 | 6M STATE CHECK HIPPS VLV, GEA-ESDV-36 | DETTE CHECK, SKAL UDFØRES I SAMRÅD MED C | 1 | 2 |  |  | 4 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /12/GEA-ESDV-36191 | EMERGENCY SHUTDOWN VALVE |  | 2021-11-11
| MTN-MECH | 2021-11-08 | 7:00 | 2021-12-03 | WPM | A | I | 2021-11-09 | 15:00 | Assurance | 2400157373 | 0010 | 1Y PRODUCED WATER BOOSTER PUMP | TL-PRODUCED WATER BOOSTER PUMP | 1 | 3 |  |  | 5 | 5 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /54/GOFA-P-5009 | DMA PROD. WTR PUMP ECCENTRIC SCREW PUMP | NOSD | 2021-11-03
| MTN-MECH | 2021-11-20 | 7:00 | 2021-12-01 | WPM | C | V | 2021-11-20 | 9:00 | Business Critical | 2400157434 | 0010 | 3M CRUDE OIL PUMP A-117A, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-20
| MTN-MECH | 2021-11-20 | 9:00 | 2021-12-01 | WPM | C | V | 2021-11-20 | 11:00 | Business Critical | 2400157434 | 0020 | 3M CRUDE OIL PUMP A-117A, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-20
| MTN-MECH | 2021-11-20 | 11:00 | 2021-12-01 | WPM | C | V | 2021-11-20 | 15:00 | Business Critical | 2400157434 | 0030 | 3M CRUDE OIL PUMP A-117A, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-20
| MTN-MECH | 2021-11-20 | 15:00 | 2021-12-01 | WPM | C | V | 2021-11-20 | 19:00 | Business Critical | 2400157434 | 0040 | 3M CRUDE OIL PUMP A-117A, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117A | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-20
| MTN-MECH | 2021-11-28 | 7:00 | 2021-12-02 | WPM | B | S | 2021-11-28 | 19:00 | Safety & Env.Related | 2400157435 | 0001 | 1M AVIATION FUEL DISPENSER - GOC | AVIATION FUEL - 1M | 1 | 5 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-11-28
| MTN-MECH | 2021-11-16 | 7:00 | 2021-12-02 | WPM | B | V | 2021-11-16 | 15:00 | Safety & Env.Related | 2400157443 | 0010 | 6M PT-3503, S/D VENTILER | PT-3503 S/D: | 1 | 2 |  |  | 2 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-11-16
| MTN-MECH | 2021-11-17 | 7:00 | 2021-12-03 | WPM | B | V | 2021-11-19 | 15:00 | Safety & Env.Related | 2400157444 | 0010 | 6M C-4201, S/D VENTILER | ESDV/BDV I FORBINDELSE MED C-4201 | 1 | 2 |  |  | 8 | 8 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-11-17
| MTN-MECH | 2021-11-12 | 7:00 | 2021-12-01 | WPM | C | V | 2021-11-21 | 11:00 | Business Critical | 2400157448 | 0010 | 6M RÅOLIE SHIPPING PUMPE - GEA-P-117E | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  |  | 28 | 28 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-P-117E | CRUDE OIL EXPORT PUMP |  | 2021-11-12
| MTN-MECH | 2021-11-17 | 7:00 | 2021-12-03 | WPM | B | V | 2021-11-17 | 15:00 | Safety & Env.Related | 2400157451 | 0010 | 6M PT-3506, S/D VENTILER | PT-3506 S/D: | 1 | 2 |  |  | 2 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 |  | 2021-11-17
| MTN-MECH | 2021-11-12 | 7:00 | 2021-12-12 | WPM | A | V | 2021-11-13 | 19:00 | Assurance | 2400157498 | 0010 | 1Y HEJSEVÆRK | DENNE PROCEDURE ER GÆLDENDE FO | 1 | 3 |  |  | 6 | 6 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /F /78/RUNWAY-BEAMS | RUNWAY BEAMS | NOSD | 2021-11-12
| MTN-MECH | 2021-11-22 | 7:00 | 2021-12-11 | WPM | C | V | 2021-11-30 | 15:00 | Business Critical | 2400157568 | 0010 | 6M RÅOLIE SHIPPING PUMPE - GEA-P-117F | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  |  | 26 | 26 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-P-117F | CRUDE OIL EXPORT PUMP |  | 2021-11-22
| MTN-MECH | 2021-12-10 | 7:00 | 2021-12-21 | WPM | C | V | 2021-12-10 | 9:00 | Business Critical | 2400160549 | 0010 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-12-10
| MTN-MECH | 2021-12-10 | 9:00 | 2021-12-21 | WPM | C | V | 2021-12-10 | 11:00 | Business Critical | 2400160549 | 0020 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-12-10
| MTN-MECH | 2021-12-10 | 11:00 | 2021-12-21 | WPM | C | V | 2021-12-10 | 15:00 | Business Critical | 2400160549 | 0030 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-12-10
| MTN-MECH | 2021-12-10 | 15:00 | 2021-12-21 | WPM | C | V | 2021-12-10 | 19:00 | Business Critical | 2400160549 | 0040 | 3M CRUDE OIL PUMP A-117D, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117D | CRUDE OIL TRANSFER SYSTEM |  | 2021-12-10
| MTN-MECH | 2021-11-08 | 7:00 | 2021-12-20 | WPM | C | V | 2021-11-08 | 8:12 | Business Critical | 2400160550 | 0010 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | TRANSMITTER, CALIBRER | 0 | 5 |  |  | 0.3 | 0.3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 8:12 | 2021-12-20 | WPM | C | V | 2021-11-08 | 10:12 | Business Critical | 2400160550 | 0030 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 10:12 | 2021-12-20 | WPM | C | V | 2021-11-08 | 11:00 | Business Critical | 2400160550 | 0040 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUSH BUTTON, RENGØR MEKANISK | 0 | 5 |  |  | 0.2 | 0.2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 11:00 | 2021-12-20 | WPM | C | V | 2021-11-08 | 11:48 | Business Critical | 2400160550 | 0070 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUSH BUTTON, FUNKTIONS TEST | 0 | 5 |  |  | 0.2 | 0.2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 11:48 | 2021-12-20 | WPM | C | V | 2021-11-08 | 13:48 | Business Critical | 2400160550 | 0100 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 13:48 | 2021-12-20 | WPM | C | V | 2021-11-08 | 15:48 | Business Critical | 2400160550 | 0110 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | TANK, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 15:48 | 2021-12-20 | WPM | C | V | 2021-11-08 | 17:48 | Business Critical | 2400160550 | 0120 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | AKTUATOR, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-08 | 17:48 | 2021-12-20 | WPM | C | V | 2021-11-09 | 9:48 | Business Critical | 2400160550 | 0130 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | VENTIL, JUSTER SP | 1 | 5 |  |  | 1 | 1 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-09 | 9:48 | 2021-12-20 | WPM | C | V | 2021-11-09 | 11:48 | Business Critical | 2400160550 | 0140 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-09 | 11:48 | 2021-12-20 | WPM | C | V | 2021-11-09 | 13:48 | Business Critical | 2400160550 | 0150 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | AKTUATOR, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-09 | 13:48 | 2021-12-20 | WPM | C | V | 2021-11-09 | 17:48 | Business Critical | 2400160550 | 0160 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  |  | 1 | 1 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-09 | 17:48 | 2021-12-20 | WPM | C | V | 2021-11-10 | 9:48 | Business Critical | 2400160550 | 0170 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | KONVERTER, RENGØR | 1 | 5 |  |  | 1 | 1 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-10 | 9:48 | 2021-12-20 | WPM | C | V | 2021-11-10 | 11:48 | Business Critical | 2400160550 | 0180 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | KONVERTER, KALIBRER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-10 | 11:48 | 2021-12-20 | WPM | C | V | 2021-11-10 | 13:48 | Business Critical | 2400160550 | 0190 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | TRANSMITTER, KALIBRER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-10 | 13:48 | 2021-12-20 | WPM | C | V | 2021-11-10 | 15:48 | Business Critical | 2400160550 | 0200 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | FILTER, UDSKIFT | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-10 | 15:48 | 2021-12-20 | WPM | C | V | 2021-11-14 | 15:48 | Business Critical | 2400160550 | 0220 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | SEAL, UDSKIFT | 2 | 5 |  |  | 24 | 24 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-14 | 15:48 | 2021-12-20 | WPM | C | V | 2021-11-17 | 11:48 | Business Critical | 2400160550 | 0230 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | CL, RENGØR | 1 | 5 |  |  | 8 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-17 | 11:48 | 2021-12-20 | WPM | C | V | 2021-11-17 | 13:48 | Business Critical | 2400160550 | 0240 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-17 | 13:48 | 2021-12-20 | WPM | C | V | 2021-11-17 | 15:48 | Business Critical | 2400160550 | 0250 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | LEJE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-17 | 15:48 | 2021-12-20 | WPM | C | V | 2021-11-18 | 7:48 | Business Critical | 2400160550 | 0260 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-18 | 7:48 | 2021-12-20 | WPM | C | V | 2021-11-18 | 11:48 | Business Critical | 2400160550 | 0270 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | MOTOR, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-18 | 11:48 | 2021-12-20 | WPM | C | V | 2021-11-18 | 13:00 | Business Critical | 2400160550 | 0290 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | SWITCH, FUNKTIONS TEST | 0 | 5 |  |  | 0.3 | 0.3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-18 | 13:00 | 2021-12-20 | WPM | C | V | 2021-11-18 | 15:00 | Business Critical | 2400160550 | 0310 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-18 | 15:00 | 2021-12-20 | WPM | C | V | 2021-11-18 | 17:00 | Business Critical | 2400160550 | 0330 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | SWITCH, JUSTER SP | 0 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-18 | 17:00 | 2021-12-20 | WPM | C | V | 2021-11-18 | 19:00 | Business Critical | 2400160550 | 0360 | 2Y CRUDE OIL PUMP A-117C, CALENDAR PM | TRANSMITTER, KALIBRER | 0 | 5 |  |  | 0.5 | 0.5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /E /25/GEA-A-117C | CRUDE OIL TRANSFER SYSTEM |  | 2021-10-26
| MTN-MECH | 2021-11-28 | 7:00 | 2021-12-17 | WPM | C | V | 2021-11-28 | 9:00 | Business Critical | 2400160551 | 0010 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | SMØREOILE, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-28 | 9:00 | 2021-12-17 | WPM | C | V | 2021-11-28 | 11:00 | Business Critical | 2400160551 | 0020 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | MOTOR, SAMPLING OLIE | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-28 | 11:00 | 2021-12-17 | WPM | C | V | 2021-11-28 | 13:00 | Business Critical | 2400160551 | 0040 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | PUMPE, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-28 | 13:00 | 2021-12-17 | WPM | C | V | 2021-11-28 | 15:00 | Business Critical | 2400160551 | 0050 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | TANK, SAMPLING OLIE | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-28 | 15:00 | 2021-12-17 | WPM | C | V | 2021-11-28 | 17:00 | Business Critical | 2400160551 | 0060 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | TANK, INSPICER | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-28 | 17:00 | 2021-12-17 | WPM | C | V | 2021-11-28 | 19:00 | Business Critical | 2400160551 | 0070 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | VENTIL, FUNKTIONS TEST | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-29 | 7:00 | 2021-12-17 | WPM | C | V | 2021-11-29 | 11:00 | Business Critical | 2400160551 | 0080 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | PUMPE, DATA OPSAMLING | 1 | 5 |  |  | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-29 | 11:00 | 2021-12-17 | WPM | C | V | 2021-11-29 | 13:00 | Business Critical | 2400160551 | 0090 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | SEAL, IR MÅLING | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-29 | 13:00 | 2021-12-17 | WPM | C | V | 2021-12-02 | 9:00 | Business Critical | 2400160551 | 0100 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | CL, RENGØR | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-12-02 | 9:00 | 2021-12-17 | WPM | C | V | 2021-12-02 | 11:00 | Business Critical | 2400160551 | 0110 | 6M CRUDE OIL PUMP A-117G, CALENDAR PM | SWITCH, JUSTER SP | 1 | 5 |  |  | 0.5 | 0.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-A-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-11-28
| MTN-MECH | 2021-11-17 | 7:00 | 2021-12-23 | WPM | C | V | 2021-12-04 | 19:00 | Business Critical | 2400160556 | 0010 | 1Y SKJOLD EXPORT PUMPS | TL-1YA SKJOLD EXPORT PUMPS | 1 | 5 |  |  | 54 | 54 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /F /23/GOFB-P-3611 | TRANSFER OF SKJOLD CRUDE OIL |  | 2021-11-17
| MTN-MECH | 2021-12-04 | 7:00 | 2021-12-23 | WPM | C | V | 2021-12-09 | 11:00 | Business Critical | 2400160567 | 0010 | 6M RÅOLIE SHIPPING PUMPE - GEA-P-117G | INSTRUMENT VENTILER - GENERELT | 1 | 5 |  |  | 16 | 16 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /25/GEA-P-117G | CRUDE OIL TRANSFER SYSTEM |  | 2021-12-04
| MTN-RIGG | 2021-11-18 | 7:00 | 2019-12-05 | WDF | 4 |  | 2021-11-19 | 15:00 | 4.Within 2 Months | 2100022553 | 0030 | Order+install new dishwasher+Gorm | Support MAINMECH with installing | 1 | 7 | SR | Keep in plan | 10 | 10 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /C /82 | LIVING AND WELFARE QTRS | NOSD | 2019-10-26
| MTN-RIGG | 2021-11-10 | 11:00 | 2019-05-12 | WDF | 4 | V | 2021-11-10 | 17:00 | 4.Within 2 Months | 2100022717 | 0040 | Replace XCV-0519 Actuator it's possibel | Replace actuator XCV-0511 rigg | 2 | 6 |  |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /07/GC-XCV-0511 | INSTRUMENT AIR TO IP GAS COMPR. | NOSD | 2019-04-02
| MTN-RIGG | 2021-11-08 | 13:00 | 2019-06-07 | WDF | 4 | S | 2021-11-09 | 13:00 | 4.Within 2 Months | 2100022775 | 0030 | CMAT:LG-50013 extern leak | Ass. Rigging | 1 | 7 |  | Hold/CMAT | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-LG-50013 | LEVEL GLASS, HYDROCARBON DRAINS | NOSD | 2019-04-28
| MTN-RIGG | 2021-11-09 | 13:00 | 2019-06-07 | WDF | 4 | S | 2021-11-10 | 13:00 | 4.Within 2 Months | 2100022775 | 0040 | CMAT:LG-50013 extern leak | Ass. Rigging | 1 | 7 |  | Hold/CMAT | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-LG-50013 | LEVEL GLASS, HYDROCARBON DRAINS | NOSD | 2019-04-28
| MTN-RIGG | 2021-11-08 | 7:00 | 2020-01-29 | WDF | 3 | V | 2021-11-08 | 13:00 | 3.Intermedt 1 Month | 2100025637 | 0010 | GEA-PM-117D Trouble shoot noise from blo | Prepare rigging equipment | 2 | 4 |  | Hold Step | 6 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-RIGG | 2021-11-09 | 13:00 | 2020-01-29 | WDF | 3 | V | 2021-11-09 | 16:00 | 3.Intermedt 1 Month | 2100025637 | 0040 | GEA-PM-117D Trouble shoot noise from blo | Rig out ventilation duct | 2 | 4 |  | Hold Step | 3 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-RIGG | 2021-11-09 | 16:00 | 2020-01-29 | WDF | 3 | V | 2021-11-10 | 8:00 | 3.Intermedt 1 Month | 2100025637 | 0060 | GEA-PM-117D Trouble shoot noise from blo | Rig in ventilation duct | 2 | 4 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-RIGG | 2021-11-11 | 14:00 | 2020-01-29 | WDF | 3 | V | 2021-11-11 | 18:00 | 3.Intermedt 1 Month | 2100025637 | 0090 | GEA-PM-117D Trouble shoot noise from blo | Remove rigging equipment | 2 | 4 |  | Hold Step | 4 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /25/GEA-PM-117D | ELECTRIC MOTOR FOR CRUDE OIL PUMP | NOSD | 2020-01-09
| MTN-RIGG | 2021-11-08 | 7:00 | 2018-12-01 | WDF | 5 | I | 2021-11-09 | 19:00 | 5.Within 4 Months | 2100025740 | 0040 | Demount GOFA-P-3907 for refurb & return. | Assist mounting pump, gear & motor. | 1 | 6 |  |  | 12 | 12 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PCNF PRC SETC GMPS MANC | GO /F /75/GOFA-P-3907 | OXYGEN SCAVENGER PUMP | NOSD | 2018-09-02
| MTN-RIGG | 2021-11-10 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-11 | 19:00 | 6.Within 8 Months | 2100025750 | 0010 | Exchange ESDV-33052 | Prepare rigging equipment | 2 | 6 |  | Hold Step | 24 | 24 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-RIGG | 2021-11-17 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-17 | 19:00 | 6.Within 8 Months | 2100025750 | 0040 | Exchange ESDV-33052 | Rig out and in of valve | 2 | 6 |  | Hold Step | 12 | 12 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-RIGG | 2021-11-23 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-24 | 19:00 | 6.Within 8 Months | 2100025750 | 0070 | Exchange ESDV-33052 | Remove rigging equipment | 2 | 6 |  | Hold Step | 24 | 24 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-RIGG | 2021-11-08 | 7:00 | 2020-01-04 | WDF | 3 | I | 2021-11-09 | 15:00 | 3.Intermedt 1 Month | 2100025766 | 0010 | GOFA-P-5002B Leak closed drain pump, pum | prepare for rigging | 1 | 4 |  | Hold Step | 10 | 10 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-P-5002B | PUMP | NOSD | 2019-12-15
| MTN-RIGG | 2021-11-09 | 15:00 | 2020-01-04 | WDF | 3 | I | 2021-11-11 | 11:00 | 3.Intermedt 1 Month | 2100025766 | 0030 | GOFA-P-5002B Leak closed drain pump, pum | Rigger assistance | 1 | 4 |  | Hold Step | 10 | 10 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28/GOFA-P-5002B | PUMP | NOSD | 2019-12-15
| MTN-RIGG | 2021-11-11 | 17:00 | 2018-09-12 | WDF | 6 | S | 2021-11-13 | 17:00 | 6.Within 8 Months | 2100025769 | 0030 | CMAT:RW Repair broken connection/fitting | Rigging of LG-50294 | 1 | 7 | No planning General job | No planning General job | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /F /27/GOFB-LG-50294 | GAUGEREJECT COLLE.VESSEL V-5008 | NOSD | 2018-04-15
| MTN-RIGG | 2021-11-08 | 15:00 | 2018-02-12 | WDF | 5 | V | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100027131 | 0035 | Montering af gc-psv-0532+drip ring | Assist ifbm. oprigning af PSV | 2 | 6 |  |  | 4 | 4 | 0 | APPR SECE SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /C /32/GC-PSV-0532 | PRESSURE SAFETY VALVE GAS COMPRESSION HP | NOSD | 2017-11-14
| MTN-RIGG | 2021-11-08 | 13:00 | 2020-04-25 | WDF | 4 | I | 2021-11-09 | 13:00 | 4.Within 2 Months | 2100029130 | 0020 | GOC GC-TCV-0314 Cooling W. TCV-0314 Stuc | rigging assistance | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /76/GC-TCV-0314 | COOLING WATER FROM E-401A |  | 2020-03-16
| MTN-RIGG | 2021-11-08 | 7:00 | 2020-03-27 | WDF | 3 | S | 2021-11-09 | 19:00 | 3.Intermedt 1 Month | 2100029442 | 0025 | F-402B Filter unit cleaning | Indrigning af filter. | 2 | 4 | FIlters/Backloaded | Refurbish | 24 | 24 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /51/GC-F-402B | COOLING WATER FILTER |  | 2020-03-07
| MTN-RIGG | 2021-11-08 | 7:00 | 2021-10-12 | WDF | 8 | V | 2021-11-08 | 13:00 | 8.Longer than 1 Year | 2100034282 | 0010 | GBN-31 choke to be taken off | Rigging pre work | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /B /55/GB-CVA-1304J | MANUAL OPERATED CHOKE VALVE | NOSD | 2020-12-16
| MTN-RIGG | 2021-11-09 | 7:00 | 2021-10-12 | WDF | 8 | V | 2021-11-09 | 19:00 | 8.Longer than 1 Year | 2100034282 | 0030 | GBN-31 choke to be taken off | Rigging assist. rig out. | 1 | 6 |  | Hold Step | 6 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /B /55/GB-CVA-1304J | MANUAL OPERATED CHOKE VALVE | NOSD | 2020-12-16
| MTN-RIGG | 2021-11-11 | 11:00 | 2021-10-12 | WDF | 8 | V | 2021-11-11 | 17:00 | 8.Longer than 1 Year | 2100034282 | 0070 | GBN-31 choke to be taken off | Rigging post work | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /B /55/GB-CVA-1304J | MANUAL OPERATED CHOKE VALVE | NOSD | 2020-12-16
| MTN-RIGG | 2021-11-08 | 7:00 | 2021-01-05 | WDF | 4 | S | 2021-11-08 | 15:00 | 4.Within 2 Months | 2100041353 | 0010 | GFN-38 Internal leaking HCV manifold | Rigging assistance pre work | 1 | 7 |  | PO Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /10/GOFB-HCV-30083 | SOUR MANIFOLD TO GFN-38 | NE | 2020-11-26
| MTN-RIGG | 2021-11-09 | 9:00 | 2021-01-05 | WDF | 4 | S | 2021-11-10 | 9:00 | 4.Within 2 Months | 2100041353 | 0030 | GFN-38 Internal leaking HCV manifold | Rigging assistance | 1 | 7 |  | PO Step | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /10/GOFB-HCV-30083 | SOUR MANIFOLD TO GFN-38 | NE | 2020-11-26
| MTN-RIGG | 2021-11-08 | 13:00 | 2021-03-10 | WDF | 5 |  | 2021-11-09 | 13:00 | 5.Within 4 Months | 2100042082 | 0020 | WI Weep from valve drain plugs | Rigging assistance | 1 | 7 |  | Hold Step | 6 | 6 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /F /55/GOF-4-WI-035-0405-FC-U | 4 INJECTION WATER LINE |  | 2020-12-10
| MTN-RIGG | 2021-11-08 | 11:00 | 2021-02-17 | WDF | 4 | V | 2021-11-08 | 17:00 | 4.Within 2 Months | 2100043627 | 0020 | Air leak from actuator esdv-12740 | rigging assistance | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /37/GA-ESDV-12740 | EMERGENCY SHUTDOWN VALVE | NE | 2021-01-08
| MTN-RIGG | 2021-12-25 | 9:06 | 2021-05-20 | WDF | 5 | I | 2021-12-25 | 15:06 | 5.Within 4 Months | 2100044957 | 0010 | PCV-0542 is leaking by piston | Rig up hoist equipment | 1 | 2 |  | GR Onshore 251121 | 3 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /71/GC-PCV-0542 | FUEL GAS CONTROL VALVE | NOSD | 2021-02-19
| MTN-RIGG | 2021-12-26 | 7:06 | 2021-05-20 | WDF | 5 | I | 2021-12-26 | 13:06 | 5.Within 4 Months | 2100044957 | 0040 | PCV-0542 is leaking by piston | Rigging assist. rig in/rig out. | 1 | 2 |  | GR Onshore 251121 | 3 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /71/GC-PCV-0542 | FUEL GAS CONTROL VALVE | NOSD | 2021-02-19
| MTN-RIGG | 2021-12-28 | 7:06 | 2021-05-20 | WDF | 5 | I | 2021-12-28 | 11:06 | 5.Within 4 Months | 2100044957 | 0070 | PCV-0542 is leaking by piston | Rig down hoist equipment | 1 | 2 |  | GR Onshore 251121 | 2 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /71/GC-PCV-0542 | FUEL GAS CONTROL VALVE | NOSD | 2021-02-19
| MTN-RIGG | 2021-11-08 | 7:00 | 2021-03-14 | WDF | 3 | V | 2021-11-08 | 15:00 | 3.Intermedt 1 Month | 2100046088 | 0010 | ESDV-01189B - not full closure at trip | Rig up hoist equipment | 1 | 4 |  | Hold Step | 4 | 4 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /31/GC-ESDV-01189B | EMERGENCY SHUTDOWN VALVE | NE | 2021-02-22
| MTN-RIGG | 2021-11-09 | 9:00 | 2021-03-14 | WDF | 3 | V | 2021-11-09 | 17:00 | 3.Intermedt 1 Month | 2100046088 | 0040 | ESDV-01189B - not full closure at trip | Rigging assist. rig in/rig out. | 1 | 4 |  | Hold Step | 4 | 4 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /31/GC-ESDV-01189B | EMERGENCY SHUTDOWN VALVE | NE | 2021-02-22
| MTN-RIGG | 2021-11-11 | 15:00 | 2021-03-14 | WDF | 3 | V | 2021-11-12 | 11:00 | 3.Intermedt 1 Month | 2100046088 | 0060 | ESDV-01189B - not full closure at trip | Rig down hoist equipment | 1 | 4 |  | Hold Step | 4 | 4 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /C /31/GC-ESDV-01189B | EMERGENCY SHUTDOWN VALVE | NE | 2021-02-22
| MTN-RIGG | 2021-11-08 | 7:00 | 2021-07-15 | WDF | 5 | V | 2021-11-08 | 13:00 | 5.Within 4 Months | 2100047676 | 0010 | V-3411 PCV-34225-1 int. leaking | Prepare rigging gear | 1 | 6 |  | GR Onshore 280921 | 3 | 3 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /20/GOFB-PCV-34225_1 | PRES. CTRL IN GAS DISCH FROM LP SEP. | NOSD | 2021-04-16
| MTN-RIGG | 2021-11-08 | 17:00 | 2021-07-15 | WDF | 5 | V | 2021-11-09 | 11:00 | 5.Within 4 Months | 2100047676 | 0040 | V-3411 PCV-34225-1 int. leaking | Rig actuator | 1 | 6 |  | GR Onshore 280921 | 3 | 3 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /20/GOFB-PCV-34225_1 | PRES. CTRL IN GAS DISCH FROM LP SEP. | NOSD | 2021-04-16
| MTN-RIGG | 2021-11-11 | 17:00 | 2021-07-15 | WDF | 5 | V | 2021-11-12 | 9:00 | 5.Within 4 Months | 2100047676 | 0070 | V-3411 PCV-34225-1 int. leaking | Take down rigging gear | 1 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /20/GOFB-PCV-34225_1 | PRES. CTRL IN GAS DISCH FROM LP SEP. | NOSD | 2021-04-16
| MTN-RIGG | 2021-11-08 | 13:00 | 2021-07-26 | WDF | 4 | V | 2021-11-09 | 11:00 | 4.Within 2 Months | 2100050750 | 0030 | Discharge valve on P-117D opens only 90% | Rigging assistance | 1 | 6 |  |  | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GEA-PCV-36049 | CRUDE OIL FLOW TO DISCH. MANIFOLD | NE | 2021-06-16
| MTN-RIGG | 2021-11-08 | 7:00 | 2021-10-21 | WDF | 5 | V | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100051792 | 0005 | ESDV-36920 cannot open | Mount rigging gear, Assist rigging. | 1 | 6 |  | GR Onshore 050821 | 6 | 6 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC MANC | GO /E /26/GEA-ESDV-36920 | EMERGENCY SHUTDOWN VALVE | NOSD | 2021-07-23
| MTN-RIGG | 2021-11-08 | 7:00 | 2021-10-26 | WDF | 5 | V | 2021-11-08 | 15:00 | 5.Within 4 Months | 2100052130 | 0010 | XCV-0509 on C-202A Internal Leaking | Prepare rigging | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /32/GC-XCV-0509 | IP GAS COMPR. | NE | 2021-07-28
| MTN-RIGG | 2021-11-09 | 17:00 | 2021-10-26 | WDF | 5 | V | 2021-11-10 | 15:00 | 5.Within 4 Months | 2100052130 | 0050 | XCV-0509 on C-202A Internal Leaking | Rigging assistance | 1 | 6 |  | Hold Step | 5 | 5 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /32/GC-XCV-0509 | IP GAS COMPR. | NE | 2021-07-28
| MTN-RIGG | 2021-11-12 | 15:00 | 2021-10-26 | WDF | 5 | V | 2021-11-13 | 11:00 | 5.Within 4 Months | 2100052130 | 0080 | XCV-0509 on C-202A Internal Leaking | Rigging post work | 1 | 6 |  | Hold Step | 4 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /32/GC-XCV-0509 | IP GAS COMPR. | NE | 2021-07-28
| MTN-RIGG | 2021-11-10 | 9:00 | 2020-05-09 | WPM | C | V | 2021-11-11 | 9:00 | Business Critical | 2400052002 | 0030 | 1Y GOFA-FT-35979 - PW METERING | Assistere med ned- og optagning af meter | 1 | 5 | SR | Pick/Pack/Myndighedskrav | 6 | 6 | 0 | APPR SMAT RDBL | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | NE | 2020-03-22
| MTN-RIGG | 2021-11-11 | 11:00 | 2021-08-26 | WPM | C | V | 2021-11-13 | 11:00 | Business Critical | 2400129829 | 0030 | 2Y GOFA-V-3401 - METERING | ASSISTERE MED NED- OG OPRIGNING AF METRE | 1 | 5 |  | Hold Step | 12 | 12 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20/METERING | SEPARATION METERING | NOSD | 2021-07-02
| MTN-RIGG | 2021-11-11 | 11:00 | 2021-08-26 | WPM | C | V | 2021-11-13 | 11:00 | Business Critical | 2400129830 | 0030 | 2Y GOFB-V-3410 - METERING | ASSISTERE MED NED- OG OPRIGNING AF METRE | 1 | 5 |  | Refurbish/Return | 12 | 12 | 0 | APPR PMAT AWSD RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /F /20/METERING | SEPARATION METERING | NOSD | 2021-07-02
| MTN-ROPE | 2021-11-08 | 7:00 | 2020-01-20 | WDF | 5 | V | 2021-11-09 | 10:09 | 5.Within 4 Months | 2100023088 | 0020 | Wrap of hole in drain pipefor LAB.GOF | Installation of wrap | 2 | 6 |  | Gr Onshore 170921 | 24 | 24 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /F /28 | CLOSED DRAINS/OPEN DRAINS | NE | 2019-10-22
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-01-22 | WDF | 4 |  | 2021-11-08 | 14:47 | 4.Within 2 Months | 2100023327 | 0020 | AnoID 493 GOF-16-GP-042-4013-BB | MPM team-Permit | 1 | 8 |  |  | 3 | 3 | 0 | APPR APOG AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /32/GOF-16-GP-042-4013-BB-U | 16 PROCESS GAS LINE | NE | 2019-12-13
| MTN-ROPE | 2021-11-08 | 14:47 | 2020-01-22 | WDF | 4 |  | 2021-11-09 | 12:54 | 4.Within 2 Months | 2100023327 | 0030 | AnoID 493 GOF-16-GP-042-4013-BB | MPM clean and paint | 3 | 8 |  |  | 24 | 24 | 0 | APPR APOG AWDO RDBL RFRZ ROUT | INIT OPND | REL PCNF PRC SETC MANC NMAT | GO /F /32/GOF-16-GP-042-4013-BB-U | 16 PROCESS GAS LINE | NE | 2019-12-13
| MTN-ROPE | 2021-11-09 | 12:54 | 2020-01-22 | WDF | 4 |  | 2021-11-09 | 15:25 | 4.Within 2 Months | 2100023327 | 0040 | AnoID 493 GOF-16-GP-042-4013-BB | MPM team NDT before release | 3 | 8 |  |  | 6 | 6 | 0 | APPR APOG AWDO RDBL RFRZ ROUT | INIT OPND | REL PCNF PRC SETC MANC NMAT | GO /F /32/GOF-16-GP-042-4013-BB-U | 16 PROCESS GAS LINE | NE | 2019-12-13
| MTN-ROPE | 2021-11-08 | 11:00 | 2018-12-26 | WDF | 5 | V | 2021-11-18 | 16:18 | 5.Within 4 Months | 2100024246 | 0010 | Suport missing cooling water modul | Suport missing cooling water modul1 | 1 | 8 | Await drafter | (6) | 99.2 | 99.2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-18 | 16:18 | 2018-12-26 | WDF | 5 | V | 2021-11-18 | 16:18 | 5.Within 4 Months | 2100024246 | 0020 | Suport missing cooling water modul | Forberedelse af jobbet | 1 | 8 | Await drafter | (6) | 0 | 11 | 11 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-18 | 16:18 | 2018-12-26 | WDF | 5 | V | 2021-11-18 | 16:18 | 5.Within 4 Months | 2100024246 | 0030 | Suport missing cooling water modul | Forberedelse af jobbet | 1 | 8 | Await drafter | (6) | 0 | 5 | 5 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-18 | 16:18 | 2018-12-26 | WDF | 5 | V | 2021-11-20 | 10:59 | 5.Within 4 Months | 2100024246 | 0040 | Suport missing cooling water modul | Bygge stilladser 2 stk under supports | 2 | 8 | Await drafter | (6) | 29.5 | 45.5 | 16 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-18 | 16:18 | 2018-12-26 | WDF | 5 | V | 2021-11-19 | 17:04 | 5.Within 4 Months | 2100024246 | 0050 | Suport missing cooling water modul | Fremstilling af nye rustfri supports | 2 | 8 | Await drafter | (6) | 20.1 | 20.1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-19 | 17:04 | 2018-12-26 | WDF | 5 | V | 2021-11-20 | 9:21 | 5.Within 4 Months | 2100024246 | 0060 | Suport missing cooling water modul | Demol af gammel supports | 2 | 8 | Await drafter | (6) | 6.7 | 6.7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-20 | 9:21 | 2018-12-26 | WDF | 5 | V | 2021-11-20 | 13:39 | 5.Within 4 Months | 2100024246 | 0070 | Suport missing cooling water modul | Montering af 2 stk nye supports | 2 | 8 | Await drafter | (6) | 6.7 | 6.7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-20 | 13:39 | 2018-12-26 | WDF | 5 | V | 2021-11-21 | 11:53 | 5.Within 4 Months | 2100024246 | 0080 | Suport missing cooling water modul | Afrigning/ demol af stilladser | 2 | 8 | Await drafter | (6) | 16.1 | 16.1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-21 | 11:53 | 2018-12-26 | WDF | 5 | V | 2021-11-21 | 13:32 | 5.Within 4 Months | 2100024246 | 0090 | Suport missing cooling water modul | QC / Dok smede | 1 | 8 | Await drafter | (6) | 1.3 | 1.3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-21 | 13:32 | 2018-12-26 | WDF | 5 | V | 2021-11-21 | 14:25 | 5.Within 4 Months | 2100024246 | 0100 | Suport missing cooling water modul | Afslutte permits | 1 | 8 | Await drafter | (6) | 0.7 | 0.7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-21 | 14:25 | 2018-12-26 | WDF | 5 | V | 2021-11-21 | 15:18 | 5.Within 4 Months | 2100024246 | 0110 | Suport missing cooling water modul | Afslutte permits | 1 | 8 | Await drafter | (6) | 0.7 | 0.7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC CSER MANC NMAT | GO /C /86/SUPPORTS-ABOVE-WATER | MAIN APPURTENANCES SUPPORTS | NOSD | 2018-09-27
| MTN-ROPE | 2021-11-10 | 11:00 | 2019-02-08 | WDF | 5 |  | 2021-11-11 | 14:17 | 5.Within 4 Months | 2100024298 | 0020 | CMAT:HGS19-1 GOC cellar deck replace han | Prepare the job - weld | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 12.1 | 12.1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-11 | 14:17 | 2019-02-08 | WDF | 5 |  | 2021-11-12 | 8:36 | 5.Within 4 Months | 2100024298 | 0030 | CMAT:HGS19-1 GOC cellar deck replace han | Prepare the job- rigger | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-12 | 8:36 | 2019-02-08 | WDF | 5 |  | 2021-11-12 | 14:55 | 5.Within 4 Months | 2100024298 | 0040 | CMAT:HGS19-1 GOC cellar deck replace han | Prepare the job - maler | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-12 | 14:55 | 2019-02-08 | WDF | 5 |  | 2021-11-14 | 7:51 | 5.Within 4 Months | 2100024298 | 0050 | CMAT:HGS19-1 GOC cellar deck replace han | Build scafolding udned stairs - scaff | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 40.2 | 40.2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-14 | 7:51 | 2019-02-08 | WDF | 5 |  | 2021-11-15 | 17:49 | 5.Within 4 Months | 2100024298 | 0060 | CMAT:HGS19-1 GOC cellar deck replace han | Demol korroded handrail / grating - weld | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 17.4 | 17.4 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-15 | 17:49 | 2019-02-08 | WDF | 5 |  | 2021-11-16 | 18:35 | 5.Within 4 Months | 2100024298 | 0070 | CMAT:HGS19-1 GOC cellar deck replace han | Clean and touch up painting - pain | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 10.1 | 10.1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-16 | 18:35 | 2019-02-08 | WDF | 5 |  | 2021-11-19 | 13:01 | 5.Within 4 Months | 2100024298 | 0080 | CMAT:HGS19-1 GOC cellar deck replace han | Install new grating / handrail - weld | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 24.1 | 24.1 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-19 | 13:01 | 2019-02-08 | WDF | 5 |  | 2021-11-20 | 7:20 | 5.Within 4 Months | 2100024298 | 0090 | CMAT:HGS19-1 GOC cellar deck replace han | Demol temp handrail on exist stair- scaf | 1 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 5 | 5 | 0 | APPR RDBL | APPR OPND | REL PRC SETC CSER MANC | GO /C /86/HANDRAIL-L1 | HANDRAIL LEVEL 1 EL +30375 | NOSD | 2018-11-10
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-06-13 | WDF | 6 |  | 2021-11-12 | 9:21 | 6.Within 8 Months | 2100024307 | 0020 | HGS19-1 GOC Module 15 roof repl handrail | MPM Team Replace handrails | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 110 | 110 | 0 | WREA APOG PMAT | WREA OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /86/HANDRAIL-L5 | HANDRAIL LEVEL 5 EL +48964 | NOSD | 2020-01-15
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-06-13 | WDF | 6 |  | 2021-11-11 | 17:04 | 6.Within 8 Months | 2100024314 | 0020 | HGS19-1 GOC Module 7D roof repl handrail | MPM Team Replace handrails | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 100 | 100 | 0 | WREA APOG CMAT | WREA OPND | REL PCNF PRC SETC GMPS MANC | GO /C /86/HANDRAIL-L5 | HANDRAIL LEVEL 5 EL +48964 | NOSD | 2020-01-15
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-06-13 | WDF | 6 |  | 2021-11-10 | 12:16 | 6.Within 8 Months | 2100024316 | 0020 | HGS19-1 GOC Module 7 replace handrail | MPM Team Replace handrails | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 60 | 60 | 0 | APPR APOG SMAT | INIT OPND | REL PCNF PRC SETC GMPS MANC | GO /C /86/HANDRAIL-L3 | HANDRAIL LEVEL 3 EL +42017 | NOSD | 2020-01-15
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-06-13 | WDF | 6 |  | 2021-11-12 | 9:21 | 6.Within 8 Months | 2100024317 | 0020 | HGS19-1 GOC Module 7B replace handrail | MPM Team Replace handrails | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 110 | 110 | 0 | APPR APOG SMAT | INIT OPND | REL PCNF PRC SETC GMPS MANC | GO /C /86/HANDRAIL-L3 | HANDRAIL LEVEL 3 EL +42017 | NOSD | 2020-01-15
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-06-13 | WDF | 6 |  | 2021-11-11 | 8:44 | 6.Within 8 Months | 2100024318 | 0020 | HGS19-1 GOC Module 7A replace handrail | MPM Team Replace handrails | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 80 | 80 | 0 | APPR APOG SMAT | INIT OPND | REL PCNF PRC SETC GMPS MANC | GO /C /86/HANDRAIL-L3 | HANDRAIL LEVEL 3 EL +42017 | NOSD | 2020-01-15
| MTN-ROPE | 2021-11-08 | 11:00 | 2020-06-13 | WDF | 6 |  | 2021-11-12 | 9:21 | 6.Within 8 Months | 2100024319 | 0020 | HGS19-1 GOC Module 5M replace handrail | MPM Team Replace handrails | 3 | 7 | Handrails | Afventer om skal laves af et specielt team til dette | 110 | 110 | 0 | APPR APOG SMAT | INIT OPND | REL PCNF PRC SETC GMPS MANC | GO /C /86/HANDRAIL-L3 | HANDRAIL LEVEL 3 EL +42017 | NOSD | 2020-01-15
| MTN-ROPE | 2021-11-11 | 9:19 | 2019-01-05 | WDF | 5 |  | 2021-11-13 | 15:45 | 5.Within 4 Months | 2100024441 | 0010 | Replacement of chem inj line GOB | Build scaffolding | 1 | 7 | /MPM | PR Step/Vendor??? | 24.1 | 24.1 | 0 | WREA APOG CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC CSER GMPS MANC | GO /B /75/GOB-0.5-CD-039-4065-FC-U | 0.5 DEMULSIFIER LINE | NOSD | 2018-10-07
| MTN-ROPE | 2021-11-08 | 15:00 | 2019-01-05 | WDF | 5 |  | 2021-11-11 | 9:19 | 5.Within 4 Months | 2100024441 | 0030 | Replacement of chem inj line GOB | Replace spools | 1 | 7 | /MPM | PR Step/Vendor??? | 24 | 24 | 0 | WREA APOG CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC CSER GMPS MANC | GO /B /75/GOB-0.5-CD-039-4065-FC-U | 0.5 DEMULSIFIER LINE | NOSD | 2018-10-07
| MTN-ROPE | 2021-11-11 | 13:19 | 2019-01-05 | WDF | 5 |  | 2021-11-13 | 16:21 | 5.Within 4 Months | 2100024441 | 0040 | Replacement of chem inj line GOB | Remove scaffolding | 1 | 7 | /MPM | PR Step/Vendor??? | 21.4 | 21.4 | 0 | WREA APOG CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PPRT PCNF PRC SETC CSER GMPS MANC | GO /B /75/GOB-0.5-CD-039-4065-FC-U | 0.5 DEMULSIFIER LINE | NOSD | 2018-10-07
| MTN-ROPE | 2021-11-08 | 11:00 | 2019-01-05 | WDF | 5 |  | 2021-11-08 | 14:47 | 5.Within 4 Months | 2100024441 | 0060 | Replacement of chem inj line GOB | MPM team offshore preb | 1 | 7 | /MPM | PR Step/Vendor??? | 3 | 3 | 0 | WREA APOG CMAT AWDO RDBL RFRZ ROUT | WREA OPND | REL PPRT PCNF PRC SETC CSER GMPS MANC | GO /B /75/GOB-0.5-CD-039-4065-FC-U | 0.5 DEMULSIFIER LINE | NOSD | 2018-10-07
| MTN-ROPE | 2021-11-08 | 11:00 | 2019-04-08 | WDF | 4 |  | 2021-11-09 | 11:45 | 4.Within 2 Months | 2100027782 | 0010 | AnoID 436 GOF-12-GPS-034-4088-BB | MPM clean and paint | 3 | 8 |  |  | 30.2 | 30.2 | 0 | APPR APOG AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC CSER MANC NMAT | GO /F /11/GOF-12-GPS-034-4088-BB-U | 12 PROCESS GAS SOUR LINE | NOSD | 2019-02-27
| MTN-ROPE | 2021-11-09 | 11:45 | 2019-04-08 | WDF | 4 |  | 2021-11-09 | 15:33 | 4.Within 2 Months | 2100027782 | 0020 | AnoID 436 GOF-12-GPS-034-4088-BB | MPM team-Permit | 1 | 8 |  |  | 3 | 3 | 0 | APPR APOG AWDO RDBL RFRZ ROUT | INIT OPND | REL PRC SETC CSER MANC NMAT | GO /F /11/GOF-12-GPS-034-4088-BB-U | 12 PROCESS GAS SOUR LINE | NOSD | 2019-02-27
| MTN-ROPE | 2021-11-09 | 15:33 | 2019-04-08 | WDF | 4 |  | 2021-11-09 | 16:49 | 4.Within 2 Months | 2100027782 | 0030 | AnoID 436 GOF-12-GPS-034-4088-BB | MPM team NDT before release | 3 | 8 |  |  | 3 | 3 | 0 | APPR APOG AWDO RDBL RFRZ ROUT | INIT OPND | REL PRC SETC CSER MANC NMAT | GO /F /11/GOF-12-GPS-034-4088-BB-U | 12 PROCESS GAS SOUR LINE | NOSD | 2019-02-27
| MTN-ROPE | 2021-10-25 | 14:57 | 2021-04-11 | WDF | 2 | V | 2021-10-25 | 14:57 | 2.Urgent 1 Week | 2100048446 | 0020 | Group 3R trip on GEA-EE-0047 Emg. Lights | Fault finding on group to localise fault | 1 | 1 | MPM |  | 0 | 16 | 22 | APPR SCH RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /E /05/GEA-EE-0047-3R | Q07 - EMERGENCY LIGHT CELLER DECK |  | 2021-04-06
| MTN-ROPE | 2021-11-08 | 15:00 | 2021-07-31 | WDF | 4 | V | 2021-11-10 | 9:57 | 4.Within 2 Months | 2100050909 | 0020 | Dismantle Gorm E Export meter for clean | Dismantel and clean export meter | 2 | 6 |  |  | 30 | 30 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /E /26/GEB-FE-36166 | FLOW ELEMENT (METERING) |  | 2021-06-21
| MTN-ROPE | 2021-12-06 | 11:19 | 2022-03-10 | WDF | 6 | S | 2021-12-06 | 13:51 | 6.Within 8 Months | 2100052868 | 0025 | FW valves missing handle | Prepare Rope access | 4 | 7 |  | GR Onshore 291021 | 8 | 8 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-ROPE | 2021-12-07 | 17:19 | 2022-03-10 | WDF | 6 | S | 2021-12-08 | 12:54 | 6.Within 8 Months | 2100052868 | 0060 | FW valves missing handle | Replace Butterfly 6"Vlv 09736 | 4 | 7 |  | GR Onshore 291021 | 24 | 24 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-ROPE | 2021-11-11 | 10:01 | 2021-11-12 | WDF | 5 | V | 2021-11-11 | 16:20 | 5.Within 4 Months | 2100052928 | 0010 | Delugenozzle followup from 1YA smoketest | Prepare/materials/tools/Permits | 3 | 6 |  |  | 15 | 15 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-11 | 16:20 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 8:30 | 5.Within 4 Months | 2100052928 | 0020 | Delugenozzle followup from 1YA smoketest | GC-XCV-0948-Repl nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 8:30 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 16:58 | 5.Within 4 Months | 2100052928 | 0030 | Delugenozzle followup from 1YA smoketest | GC-XCV-0949-Repl nozzles | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 16:58 | 2021-11-12 | WDF | 5 | V | 2021-11-13 | 13:26 | 5.Within 4 Months | 2100052928 | 0040 | Delugenozzle followup from 1YA smoketest | GC-XCV-0953-Unblock nozzles | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-13 | 13:26 | 2021-11-12 | WDF | 5 | V | 2021-11-14 | 9:53 | 5.Within 4 Months | 2100052928 | 0050 | Delugenozzle followup from 1YA smoketest | GC-XCV-0955-Repl nozzles | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-14 | 9:53 | 2021-11-12 | WDF | 5 | V | 2021-11-14 | 18:21 | 5.Within 4 Months | 2100052928 | 0060 | Delugenozzle followup from 1YA smoketest | GC-XCV-0331-Repl nozzles | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-11 | 16:20 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 8:30 | 5.Within 4 Months | 2100052928 | 0070 | Delugenozzle followup from 1YA smoketest | GE-XCV-1501-Unblock nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 8:30 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 16:58 | 5.Within 4 Months | 2100052928 | 0080 | Delugenozzle followup from 1YA smoketest | GE-XCV-1502-Unblock nozzles | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 16:58 | 2021-11-12 | WDF | 5 | V | 2021-11-13 | 13:26 | 5.Within 4 Months | 2100052928 | 0090 | Delugenozzle followup from 1YA smoketest | GE-XCV-1509-Unblock nozzles | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-13 | 13:26 | 2021-11-12 | WDF | 5 | V | 2021-11-13 | 17:36 | 5.Within 4 Months | 2100052928 | 0100 | Delugenozzle followup from 1YA smoketest | GE-XCV-1568-Repl/unblock nozzzles | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-11 | 16:20 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 8:30 | 5.Within 4 Months | 2100052928 | 0110 | Delugenozzle followup from 1YA smoketest | GEB-XCV-03011-Repl nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 8:30 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 12:40 | 5.Within 4 Months | 2100052928 | 0120 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03108-Repl nozzles | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 12:40 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 16:50 | 5.Within 4 Months | 2100052928 | 0130 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03308-Unblock nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-12 | 16:50 | 2021-11-12 | WDF | 5 | V | 2021-11-13 | 13:18 | 5.Within 4 Months | 2100052928 | 0140 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03408-Install missing nozzle | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-13 | 13:18 | 2021-11-12 | WDF | 5 | V | 2021-11-13 | 17:28 | 5.Within 4 Months | 2100052928 | 0150 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03508-Repl nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-11 | 16:20 | 2021-11-12 | WDF | 5 | V | 2021-11-12 | 8:30 | 5.Within 4 Months | 2100052928 | 0160 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03602-Repl nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-13 | 17:28 | 2021-11-12 | WDF | 5 | V | 2021-11-14 | 9:38 | 5.Within 4 Months | 2100052928 | 0170 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03708-Repl/install nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-14 | 9:38 | 2021-11-12 | WDF | 5 | V | 2021-11-14 | 13:48 | 5.Within 4 Months | 2100052928 | 0180 | Delugenozzle followup from 1YA smoketest | GOFA-XCV-03808-Unblock nozzle | 3 | 6 |  |  | 10 | 10 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-11-14 | 13:48 | 2021-11-12 | WDF | 5 | V | 2021-11-15 | 10:16 | 5.Within 4 Months | 2100052928 | 0190 | Delugenozzle followup from 1YA smoketest | GOFB-XCV-03387-Unblck/replc nozzle | 3 | 6 |  |  | 20 | 20 | 0 | APPR WMAT | APPR OPND | REL PRC SETC MACM | GO /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2021-08-14
| MTN-ROPE | 2021-12-19 | 9:03 | 2021-09-08 | WDF | 3 | V | 2021-12-19 | 12:50 | 3.Intermedt 1 Month | 2100053787 | 0010 | GE-A-1502 Fusible Loop leaking | Prepare matr/tools/permit | 2 | 4 |  |  | 6 | 6 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PRC SETC MACM | GO /E /01/GE-XCV-1502 | DELUGE VALVE SYSTEM | NOSD | 2021-08-19
| MTN-ROPE | 2021-12-22 | 12:50 | 2021-09-08 | WDF | 3 | V | 2021-12-23 | 16:00 | 3.Intermedt 1 Month | 2100053787 | 0040 | GE-A-1502 Fusible Loop leaking | Replace Fusible Nozzles | 4 | 4 |  |  | 48 | 48 | 0 | APPR SECE WMAT AWDO RFRZ ROUT | APPR OPND | REL PRC SETC MACM | GO /E /01/GE-XCV-1502 | DELUGE VALVE SYSTEM | NOSD | 2021-08-19
| MTN-ROPE | 2021-11-08 | 7:00 | 2021-09-23 | WDF | 3 | V | 2021-11-08 | 18:22 | 3.Intermedt 1 Month | 2100054714 | 0010 | Faulty firedamper GC-SOD-380 | Erect scaffold, remove grating, barrier | 2 | 4 |  |  | 18 | 18 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/GC-SOD-0380 | FIRE DAMPER EXHAUST AIR LOW. LEV. | NOSD | 2021-09-03
| MTN-ROPE | 2021-11-12 | 14:22 | 2021-09-23 | WDF | 3 | V | 2021-11-13 | 9:57 | 3.Intermedt 1 Month | 2100054714 | 0060 | Faulty firedamper GC-SOD-380 | Remove scaffold, etc. | 2 | 4 |  |  | 12 | 12 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /C /09/GC-SOD-0380 | FIRE DAMPER EXHAUST AIR LOW. LEV. | NOSD | 2021-09-03
| MTN-ROPE | 2021-12-30 | 9:07 | 2021-12-28 | WDF | 5 | V | 2021-12-31 | 12:16 | 5.Within 4 Months | 2100055031 | 0040 | Clean Gorm E fast loop | Re-eastblish Insulation fast loop | 1 | 6 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GE-AE-2901 | SENSOR FOR AT-2901 (METERING) |  | 2021-09-29
| MTN-ROPE | 2021-11-23 | 10:14 | 2021-11-02 | WDF | 4 | V | 2021-11-23 | 11:30 | 4.Within 2 Months | 2100055550 | 0010 | Equipotential bond broken XGE-1001-3 | Prepare rope access | 2 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /C /03/AREA-10-GAS-DETECTORS | AREA 10 GAS DETECTORS | NOSD | 2021-09-23
| MTN-ROPE | 2021-11-23 | 10:14 | 2021-11-02 | WDF | 4 | V | 2021-11-23 | 11:30 | 4.Within 2 Months | 2100055550 | 0030 | Equipotential bond broken XGE-1001-3 | Demount Wiring | 1 | 6 |  |  | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /C /03/AREA-10-GAS-DETECTORS | AREA 10 GAS DETECTORS | NOSD | 2021-09-23
| MTN-ROPE | 2021-11-23 | 10:14 | 2021-11-02 | WDF | 4 | V | 2021-11-23 | 11:30 | 4.Within 2 Months | 2100055550 | 0050 | Equipotential bond broken XGE-1001-3 | Mount Wiring | 1 | 6 |  |  | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /C /03/AREA-10-GAS-DETECTORS | AREA 10 GAS DETECTORS | NOSD | 2021-09-23
| MTN-ROPE | 2021-11-23 | 12:58 | 2021-11-02 | WDF | 4 | V | 2021-11-23 | 14:14 | 4.Within 2 Months | 2100055550 | 0070 | Equipotential bond broken XGE-1001-3 | Remove rope access | 2 | 6 |  |  | 2 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MACM | GO /C /03/AREA-10-GAS-DETECTORS | AREA 10 GAS DETECTORS | NOSD | 2021-09-23
| MTN-ROUS | 2021-12-31 | 7:00 | 2018-07-15 | WDF | 4 | V | 2022-01-05 | 11:00 | 4.Within 2 Months | 2100023717 | 0021 | REPL LB 704 with new overhauled | Exchange of LB 704 with overhauled LB. | 3 | 6 | Udsat ubestemt tid | /Hold step/Paperwork | 48 | 48 | 0 | APPR WMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF PRC SETC MANC | GO /C /02/GC-M-704 | ESCAPE CAPSULE NO 4 | NOSD | 2018-06-05
| MTN-ROUS | 2021-11-09 | 15:00 | 2018-04-29 | WDF | 3 | S | 2021-11-11 | 15:00 | 3.Intermedt 1 Month | 2100025689 | 0020 | GORM F. H2S SCAVENGER TANK T-3902 | Cleaning of drip tray | 2 | 4 |  |  | 12 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /75/GOFB-T-3902 | H2S SCAVENGER TANK | NOSD | 2018-04-09
| MTN-ROUS | 2021-11-13 | 15:00 | 2020-09-25 | WDF | 5 | I | 2021-11-15 | 11:00 | 5.Within 4 Months | 2100032963 | 0070 | Exchange Bio pump - P-121 | Return P-121 for repair | 2 | 6 |  |  | 10 | 10 | 0 | APPR SMAT RDBL | APPR OPND | REL PCNF PRC SETC GMPS MANC | GO /E /75/GEA-P-121 | BIOCIDE INJECTION SYSTEM |  | 2020-06-27
| MTN-ROUS | 2021-11-08 | 7:00 | 2020-09-14 | WDF | 4 | I | 2021-11-10 | 15:00 | 4.Within 2 Months | 2100036018 | 0010 | GOC/71: Replace GC-HOSB-5791 Diesel hose | GC-HOSB-5791 Diesel hose replacement | 1 | 6 | /alig Vest cran |  | 8 | 8 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /71/GC-HOSB-5791 | BUNKER HOSE - DIESEL | NOSD | 2020-08-05
| MTN-ROUS | 2021-11-20 | 7:00 | 2022-02-14 | WDF | 8 | S | 2021-11-22 | 15:00 | 8.Longer than 1 Year | 2100040606 | 0050 | Replace pump unit on aviation fuel skid | Return / backload heli fuel pump unit | 1 | 7 |  | Hold Step | 8 | 8 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /81/GC-P-802 | FUEL PUMP, HELICOPTER REFUELLING SYSTEM | NOSD | 2021-04-20
| MTN-ROUS | 2021-11-13 | 7:00 | 2021-11-24 | WPM | C | V | 2021-11-14 | 19:00 | Business Critical | 2400157260 | 0010 | 3M LIVBÅD WHITTAKER CA2801 - GOF | INSPECTION GORM F WHITTAKER 3M | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /F /02/LIFEBOAT | LIFEBOAT | NOSD | 2021-11-13
| MTN-SCAF | 2021-11-10 | 7:00 | 2019-04-01 | WDF | 6 | I | 2021-11-10 | 10:00 | 6.Within 8 Months | 2100025685 | 0010 | SMAT:Ventilatordæksel på El-motor rusten | Prepare Rigging | 2 | 6 |  |  | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEA-PM-3931 | PUMP ELECTRIC MOTOR FOR P-3931 | NOSD | 2018-11-02
| MTN-SCAF | 2021-11-10 | 18:00 | 2019-04-01 | WDF | 6 | I | 2021-11-11 | 8:00 | 6.Within 8 Months | 2100025685 | 0050 | SMAT:Ventilatordæksel på El-motor rusten | Remove/place motor | 2 | 6 |  |  | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC | GO /E /75/GEA-PM-3931 | PUMP ELECTRIC MOTOR FOR P-3931 | NOSD | 2018-11-02
| MTN-SCAF | 2021-11-08 | 7:00 | 2018-04-29 | WDF | 3 | S | 2021-11-09 | 15:00 | 3.Intermedt 1 Month | 2100025689 | 0010 | GORM F. H2S SCAVENGER TANK T-3902 | Build of scaffolding | 2 | 4 |  |  | 20 | 20 | 0 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /75/GOFB-T-3902 | H2S SCAVENGER TANK | NOSD | 2018-04-09
| MTN-SCAF | 2021-11-13 | 15:00 | 2018-04-29 | WDF | 3 | S | 2021-11-15 | 8:00 | 3.Intermedt 1 Month | 2100025689 | 0040 | GORM F. H2S SCAVENGER TANK T-3902 | Remove of scaffolding | 2 | 4 |  |  | 17 | 20 | 3 | APPR RDBL | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /F /75/GOFB-T-3902 | H2S SCAVENGER TANK | NOSD | 2018-04-09
| MTN-SCAF | 2021-11-08 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-09 | 19:00 | 6.Within 8 Months | 2100025750 | 0005 | Exchange ESDV-33052 | Prepare scaffolding | 2 | 6 |  | Hold Step | 24 | 24 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-SCAF | 2021-11-15 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-16 | 19:00 | 6.Within 8 Months | 2100025750 | 0035 | Exchange ESDV-33052 | Remove scaffolding | 2 | 6 |  | Hold Step | 24 | 24 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-SCAF | 2021-11-18 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-19 | 19:00 | 6.Within 8 Months | 2100025750 | 0045 | Exchange ESDV-33052 | build scaffolding | 2 | 6 |  | Hold Step | 24 | 24 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-SCAF | 2021-11-25 | 7:00 | 2020-08-15 | WDF | 6 | V | 2021-11-26 | 19:00 | 6.Within 8 Months | 2100025750 | 0080 | Exchange ESDV-33052 | Remove scaffolding | 2 | 6 |  | Hold Step | 24 | 24 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC GMPS MANC | GO /F /12/GOFC-ESDV-33052 | EMERGENCY SHUTDOWN VALVE | NE | 2020-03-18
| MTN-SCAF | 2021-11-08 | 7:00 | 2020-05-05 | WDF | 3 | S | 2021-11-10 | 9:00 | 3.Intermedt 1 Month | 2100030939 | 0009 | Seawater filter GC-F-402C change brushin | Build scaffold for easy access | 2 | 8 | OTL/+2400106126 | (4)After/2100029442 | 26 | 26 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER |  | 2020-04-15
| MTN-SCAF | 2021-11-14 | 7:00 | 2020-05-05 | WDF | 3 | S | 2021-11-15 | 13:00 | 3.Intermedt 1 Month | 2100030939 | 0040 | Seawater filter GC-F-402C change brushin | Remove scaffolding | 2 | 8 | OTL/+2400106126 | (4)After/2100029442 | 18 | 18 | 0 | APPR SMAT RDBL | APPR OPND | REL PRC SETC GMPS MANC | GO /C /51/GC-F-402C | COOLING WATER FILTER |  | 2020-04-15
| MTN-SCAF | 2021-11-11 | 7:00 | 2021-02-08 | WDF | 3 | V | 2021-11-11 | 17:00 | 3.Intermedt 1 Month | 2100044432 | 0005 | GBN-43 Choke - Runs badly | Small scaffold | 1 | 2 |  |  | 5 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL PPRT PCNF PRC SETC MANC | GO /B /10/GB-CVA-1304F | CHOKE VALVE |  | 2021-01-19
| MTN-SCAF | 2021-12-10 | 14:35 | 2021-01-25 | WDF | 3 | S | 2022-01-06 | 18:35 | 3.Intermedt 1 Month | 2100044832 | 0020 | Leakage on seawage vaccum system | Scaff for Sewage job. | 1 | 8 |  | No planning General job | 164 | 200 | 36 | APPR APOG | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /C /82/GC-M-900 | SEWAGE TREATMENT PLANT | NOSD | 2021-01-20
| MTN-SCAF | 2021-11-08 | 7:00 | 2021-05-25 | WDF | 4 | V | 2021-11-09 | 9:00 | 4.Within 2 Months | 2100048240 | 0020 | disasembvle and clean Flame arrestors. | Prepare scaffolding | 1 | 6 |  | Hold Step | 7 | 7 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-SCAF | 2021-11-09 | 9:00 | 2021-05-25 | WDF | 4 | V | 2021-11-10 | 15:00 | 4.Within 2 Months | 2100048240 | 0030 | disasembvle and clean Flame arrestors. | Build scaffold for both flame arrestors | 2 | 6 |  | Hold Step | 18 | 18 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-SCAF | 2021-11-16 | 15:00 | 2021-05-25 | WDF | 4 | V | 2021-11-17 | 17:00 | 4.Within 2 Months | 2100048240 | 0080 | disasembvle and clean Flame arrestors. | Remove scaffolding at both flame arresto | 2 | 6 |  | Hold Step | 14 | 14 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC GMPS MANC | GO /A /28/GA-FLA-302 | FLAME ARRESTOR | NE | 2021-04-15
| MTN-SCAF | 2021-12-06 | 11:19 | 2022-03-10 | WDF | 6 | S | 2021-12-07 | 11:19 | 6.Within 8 Months | 2100052868 | 0010 | FW valves missing handle | Prepare permit/rectify Scaffolding | 3 | 7 |  | GR Onshore 291021 | 18 | 18 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-SCAF | 2021-12-09 | 11:19 | 2022-03-10 | WDF | 6 | S | 2021-12-09 | 17:19 | 6.Within 8 Months | 2100052868 | 0090 | FW valves missing handle | Scaffold removal | 4 | 7 |  | GR Onshore 291021 | 12 | 12 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /01/GC-HCV-09735 | LO - HAND CONTROL VALVE | NOSD | 2021-10-11
| MTN-SCAF | 2021-11-08 | 12:43 | 2022-03-10 | WDF | 6 | S | 2021-11-09 | 12:43 | 6.Within 8 Months | 2100052869 | 0010 | FW valve handle missing on GEA-HCV-03047 | Prepare permit/rectify Scaffolding | 3 | 7 |  |  | 18 | 18 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /01/GEA-HCV-03047 | LO - HCV FOR DELUGE | NOSD | 2021-10-11
| MTN-SCAF | 2021-11-11 | 12:43 | 2022-03-10 | WDF | 6 | S | 2021-11-12 | 8:43 | 6.Within 8 Months | 2100052869 | 0080 | FW valve handle missing on GEA-HCV-03047 | Scaffold removal | 3 | 7 |  |  | 12 | 12 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /E /01/GEA-HCV-03047 | LO - HCV FOR DELUGE | NOSD | 2021-10-11
| MTN-SCAF | 2021-11-08 | 7:00 | 2021-10-10 | WDF | 4 | V | 2021-11-08 | 11:00 | 4.Within 2 Months | 2100053955 | 0010 | XFE-01103 GOF in Fault in F/G system | Erect scaffold | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /03/GOFA-XFE-01103 | FLAME DETECTOR PROC. NO. 28 | NOSD | 2021-08-31
| MTN-SCAF | 2021-11-08 | 7:00 | 2021-10-10 | WDF | 4 | V | 2021-11-08 | 11:00 | 4.Within 2 Months | 2100053955 | 0070 | XFE-01103 GOF in Fault in F/G system | Dismantle scaffold | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /03/GOFA-XFE-01103 | FLAME DETECTOR PROC. NO. 28 | NOSD | 2021-08-31
| MTN-SCAF | 2021-12-24 | 9:07 | 2021-12-28 | WDF | 5 | V | 2021-12-26 | 9:07 | 5.Within 4 Months | 2100055031 | 0020 | Clean Gorm E fast loop | Scaffolding at connection flanged | 2 | 6 |  |  | 24 | 24 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /25/GE-AE-2901 | SENSOR FOR AT-2901 (METERING) |  | 2021-09-29
| MTN-SCAF | 2021-11-08 | 7:00 | 2021-10-14 | WDF | 3 | V | 2021-11-08 | 11:00 | 3.Intermedt 1 Month | 2100055574 | 0010 | Gas detector out of order | Erect scaffold | 1 | 4 |  | STPO Step | 2 | 2 | 0 | APPR SECE WMAT AWDO ROUT | APPR OPND | REL PRC SETC MANC | GO /B /03/GOBZ-XGE-01156 | IR GAS DETECTOR | NOSD | 2021-09-24
| MTN-SCAF | 2021-11-08 | 11:48 | 2021-10-14 | WDF | 3 | V | 2021-11-08 | 15:48 | 3.Intermedt 1 Month | 2100055574 | 0070 | Gas detector out of order | Dismantle scaffold | 1 | 4 |  | STPO Step | 2 | 2 | 0 | APPR SECE WMAT AWDO ROUT | APPR OPND | REL PRC SETC MANC | GO /B /03/GOBZ-XGE-01156 | IR GAS DETECTOR | NOSD | 2021-09-24
| MTN-SCAF | 2021-11-08 | 7:00 | 2021-10-15 | WPM | D | I | 2021-11-11 | 19:00 | Non Critical | 2400134829 | 0010 | 1Y TRANSPORTABLE STIGER GOC | 14.02.2013 | 1 | 8 |  |  | 24 | 24 | 0 | APPR RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /C /84 | WORKSHOP/WAREHOUSE | NOSD | 2021-08-29
| MTN-TELE | 2021-11-08 | 7:00 | 2020-03-05 | WDF | 5 | V | 2021-11-08 | 7:00 | 5.Within 4 Months | 2100023211 | 0010 | CCR VHF Radios display unreadable | Installation of CCR VHF Radios | 2 | 8 |  | (6) 020721/Afventer nye materialer | 0 | 8 | 13 | APPR SMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /08 | COMMUNICATION/TELECOM | NOSD | 2019-12-06
| MTN-TELE | 2021-11-08 | 7:00 | 2020-03-05 | WDF | 5 | V | 2021-11-08 | 8:12 | 5.Within 4 Months | 2100023211 | 0020 | CCR VHF Radios display unreadable | Test of CCR VHF Radios | 2 | 8 |  | (6) 020721/Afventer nye materialer | 1 | 1 | 0 | APPR SMAT RDBL | APPR OPND | REL PPRT PCNF PRC SETC GMPS MANC | GO /C /08 | COMMUNICATION/TELECOM | NOSD | 2019-12-06
| MTN-TELE | 2021-11-08 | 7:00 | 2018-02-08 | WDF | 5 | V | 2021-11-08 | 7:00 | 5.Within 4 Months | 2100023822 | 0010 | SMAT:Rep af ABB batteriladere DSSB120 | Klargør værktøj & permit, afhold toolbox | 1 | 8 | Need new addapter. | (6) | 0 | 4 | 4 | APPR PROK RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /C /04 | SUBSEA/SURFACE CONTROL & SUPERVISION | NOSD | 2017-11-10
| MTN-TELE | 2021-11-08 | 7:00 | 2018-02-08 | WDF | 5 | V | 2021-11-08 | 19:00 | 5.Within 4 Months | 2100023822 | 0020 | SMAT:Rep af ABB batteriladere DSSB120 | Isolering af ABB bateriladere DSSB120 | 1 | 8 | Need new addapter. | (6) | 5 | 5 | 0 | APPR PROK RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /C /04 | SUBSEA/SURFACE CONTROL & SUPERVISION | NOSD | 2017-11-10
| MTN-TELE | 2021-11-09 | 7:00 | 2018-02-08 | WDF | 5 | V | 2021-11-10 | 19:00 | 5.Within 4 Months | 2100023822 | 0030 | SMAT:Rep af ABB batteriladere DSSB120 | Reparation af ABB bateriladere DSSB120 | 1 | 8 | Need new addapter. | (6) | 10 | 14 | 4 | APPR PROK RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /C /04 | SUBSEA/SURFACE CONTROL & SUPERVISION | NOSD | 2017-11-10
| MTN-TELE | 2021-11-09 | 7:00 | 2018-02-08 | WDF | 5 | V | 2021-11-09 | 16:36 | 5.Within 4 Months | 2100023822 | 0040 | SMAT:Rep af ABB batteriladere DSSB120 | De-isolering af ABB bateriladere DSSB120 | 1 | 8 | Need new addapter. | (6) | 4 | 4 | 0 | APPR PROK RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /C /04 | SUBSEA/SURFACE CONTROL & SUPERVISION | NOSD | 2017-11-10
| MTN-TELE | 2021-11-09 | 16:36 | 2018-02-08 | WDF | 5 | V | 2021-11-10 | 14:12 | 5.Within 4 Months | 2100023822 | 0050 | SMAT:Rep af ABB batteriladere DSSB120 | Test, Qc / Close out | 1 | 8 | Need new addapter. | (6) | 4 | 4 | 0 | APPR PROK RDBL | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /C /04 | SUBSEA/SURFACE CONTROL & SUPERVISION | NOSD | 2017-11-10
| MTN-TELE | 2021-11-08 | 7:00 | 2017-11-16 | WDF | 8 | V | 2021-11-12 | 16:36 | 8.Longer than 1 Year | 2100025418 | 0010 | Purge panel for GB-FP-1300 | Purge panel for GB-FP-1300 | 1 | 8 | Telekom SD code?? | (6) | 24 | 24 | 0 | APPR APOG RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /B /04/GB-CP-1300 | SCADA RIO | NOSD | 2017-01-20
| MTN-TELE | 2021-11-08 | 7:00 | 2020-06-16 | WDF | 4 | V | 2021-11-08 | 9:24 | 4.Within 2 Months | 2100029712 | 0070 | GPE replace input card | Awaits materials | 1 | 6 |  | Refurbish | 1 | 1 | 0 | APPR WMAT RFRZ ROUT | APPR OPND | REL PRT PCNF PRC SETC MANC | GO /E /03/FIRE-GAS-CONTROL-PANELS | FIRE & GAS CONTROL PANELS | NOSD | 2020-05-07
| MTN-TELE | 2021-12-24 | 7:00 | 2021-02-02 | WDF | 5 | V | 2021-12-24 | 14:12 | 5.Within 4 Months | 2100039447 | 0109 | Findings after PA-PPM 2400065563 | Isolate JB | 1 | 6 | Need PA-TEAM |  | 3 | 3 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC CSER GMPS MANC | GO /F /08/PA-SYSTEM | PA SPEAKER SYSTEM | NOSD | 2020-11-04
| MTN-TELE | 2021-12-24 | 7:00 | 2021-02-02 | WDF | 5 | V | 2021-12-24 | 17:48 | 5.Within 4 Months | 2100039447 | 0210 | Findings after PA-PPM 2400065563 | Replace JB | 2 | 6 | Need PA-TEAM |  | 9 | 9 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC CSER GMPS MANC | GO /F /08/PA-SYSTEM | PA SPEAKER SYSTEM | NOSD | 2020-11-04
| MTN-TELE | 2021-12-24 | 17:48 | 2021-02-02 | WDF | 5 | V | 2021-12-25 | 13:00 | 5.Within 4 Months | 2100039447 | 0309 | Findings after PA-PPM 2400065563 | Deisolate JB after replacement | 1 | 6 | Need PA-TEAM |  | 3 | 3 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC CSER GMPS MANC | GO /F /08/PA-SYSTEM | PA SPEAKER SYSTEM | NOSD | 2020-11-04
| MTN-TELE | 2021-12-24 | 15:24 | 2021-02-02 | WDF | 5 | V | 2021-12-24 | 17:48 | 5.Within 4 Months | 2100039447 | 0410 | Findings after PA-PPM 2400065563 | Test after completed work | 1 | 6 | Need PA-TEAM |  | 1 | 1 | 0 | APPR SMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC CSER GMPS MANC | GO /F /08/PA-SYSTEM | PA SPEAKER SYSTEM | NOSD | 2020-11-04
| MTN-TELE | 2021-12-01 | 11:45 | 2021-05-14 | WDF | 3 | V | 2021-12-01 | 12:57 | 3.Intermedt 1 Month | 2100049128 | 0010 | XSE-01110 goes into fault periodically | Inhibit loop | 1 | 4 | Awating action SR | Action SR | 0.5 | 0.5 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /03/GEB-XSE-01110 | SMOKE DETECTOR LOOP XSE-01110 | NOSD | 2021-04-24
| MTN-TELE | 2021-12-01 | 12:57 | 2021-05-14 | WDF | 3 | V | 2021-12-02 | 12:57 | 3.Intermedt 1 Month | 2100049128 | 0020 | XSE-01110 goes into fault periodically | Troubleshoot on the loop fault | 2 | 4 | Awating action SR | Action SR | 10 | 10 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /03/GEB-XSE-01110 | SMOKE DETECTOR LOOP XSE-01110 | NOSD | 2021-04-24
| MTN-TELE | 2021-12-02 | 12:57 | 2021-05-14 | WDF | 3 | V | 2021-12-03 | 8:09 | 3.Intermedt 1 Month | 2100049128 | 0030 | XSE-01110 goes into fault periodically | Test loop | 2 | 4 | Awating action SR | Action SR | 6 | 6 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /03/GEB-XSE-01110 | SMOKE DETECTOR LOOP XSE-01110 | NOSD | 2021-04-24
| MTN-TELE | 2021-12-03 | 8:09 | 2021-05-14 | WDF | 3 | V | 2021-12-03 | 9:21 | 3.Intermedt 1 Month | 2100049128 | 0040 | XSE-01110 goes into fault periodically | Remove inhibit | 1 | 4 | Awating action SR | Action SR | 0.5 | 0.5 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /E /03/GEB-XSE-01110 | SMOKE DETECTOR LOOP XSE-01110 | NOSD | 2021-04-24
| MTN-TELE | 2021-12-24 | 9:04 | 2021-07-23 | WDF | 3 | V | 2021-12-24 | 9:04 | 3.Intermedt 1 Month | 2100051790 | 0020 | GE-XFE-01051 goes into alarm periodicall | Adjust Flame Detector (FGS) | 1 | 4 |  | Action SR | 0 | 2 | 5 | APPR SECE AWDO ROUT | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /E /03/GEB-XFE-01051 | FLAME DETECTOR | NOSD | 2021-07-03
| MTN-TELE | 2021-12-24 | 9:04 | 2021-07-23 | WDF | 3 | V | 2021-12-24 | 13:52 | 3.Intermedt 1 Month | 2100051790 | 0030 | GE-XFE-01051 goes into alarm periodicall | Calibrate Flame Detector (FGS) | 1 | 4 |  | Action SR | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /E /03/GEB-XFE-01051 | FLAME DETECTOR | NOSD | 2021-07-03
| MTN-TELE | 2021-12-24 | 13:52 | 2021-07-23 | WDF | 3 | V | 2021-12-24 | 18:40 | 3.Intermedt 1 Month | 2100051790 | 0040 | GE-XFE-01051 goes into alarm periodicall | Check Flame Detector (FGS) | 1 | 4 |  | Action SR | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PCNF PRC SETC MANC NMAT | GO /E /03/GEB-XFE-01051 | FLAME DETECTOR | NOSD | 2021-07-03
| MTN-TELE | 2021-11-08 | 11:00 | 2021-10-10 | WDF | 4 | V | 2021-11-08 | 15:48 | 4.Within 2 Months | 2100053955 | 0030 | XFE-01103 GOF in Fault in F/G system | Calibrate Flame Detector (FGS) | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /03/GOFA-XFE-01103 | FLAME DETECTOR PROC. NO. 28 | NOSD | 2021-08-31
| MTN-TELE | 2021-11-08 | 7:00 | 2021-10-10 | WDF | 4 | V | 2021-11-08 | 11:48 | 4.Within 2 Months | 2100053955 | 0040 | XFE-01103 GOF in Fault in F/G system | Check Flame Detector (FGS) | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /03/GOFA-XFE-01103 | FLAME DETECTOR PROC. NO. 28 | NOSD | 2021-08-31
| MTN-TELE | 2021-11-08 | 7:00 | 2021-10-10 | WDF | 4 | V | 2021-11-08 | 11:48 | 4.Within 2 Months | 2100053955 | 0050 | XFE-01103 GOF in Fault in F/G system | Clean Flame Detector (FGS) | 1 | 6 |  |  | 2 | 2 | 0 | APPR SECE AWDO ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /03/GOFA-XFE-01103 | FLAME DETECTOR PROC. NO. 28 | NOSD | 2021-08-31
| MTN-TELE | 2021-11-08 | 7:00 | 2021-10-14 | WDF | 3 | V | 2021-11-08 | 9:24 | 3.Intermedt 1 Month | 2100055574 | 0030 | Gas detector out of order | Demount Instrumentation | 1 | 4 |  | STPO Step | 1 | 1 | 0 | APPR SECE WMAT AWDO ROUT | APPR OPND | REL PRC SETC MANC | GO /B /03/GOBZ-XGE-01156 | IR GAS DETECTOR | NOSD | 2021-09-24
| MTN-TELE | 2021-11-08 | 7:00 | 2021-10-14 | WDF | 3 | V | 2021-11-08 | 11:48 | 3.Intermedt 1 Month | 2100055574 | 0040 | Gas detector out of order | Calibrate Infra Red Gas Detector (FGS) | 1 | 4 |  | STPO Step | 2 | 2 | 0 | APPR SECE WMAT AWDO ROUT | APPR OPND | REL PRC SETC MANC | GO /B /03/GOBZ-XGE-01156 | IR GAS DETECTOR | NOSD | 2021-09-24
| MTN-TELE | 2021-11-08 | 9:24 | 2021-10-14 | WDF | 3 | V | 2021-11-08 | 11:48 | 3.Intermedt 1 Month | 2100055574 | 0050 | Gas detector out of order | Mount Instrumentation | 1 | 4 |  | STPO Step | 1 | 1 | 0 | APPR SECE WMAT AWDO ROUT | APPR OPND | REL PRC SETC MANC | GO /B /03/GOBZ-XGE-01156 | IR GAS DETECTOR | NOSD | 2021-09-24
| MTN-TELE | 2021-11-08 | 7:00 | 2020-05-24 | WPM | A | V | 2021-11-08 | 14:12 | Assurance | 2400051801 | 0010 | ESD GORM - DAGMAR, UHF LINK | DETTE CHECK ER SAMMENHØRENDE MED PM | 1 | 8 | Sammen med DUCSAT?? | (3) | 3 | 3 | 0 | APPR SECE DFCR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /08/EXTERNAL-COMMUNICATION | EXTERNAL COMMUNICATION | NOSD | 2020-04-06
| MTN-TELE | 2021-12-24 | 7:00 | 2021-07-05 | WPM | C | I | 2021-12-25 | 9:24 | Business Critical | 2400127903 | 0010 | 6M TRANSM., RADAR BEACON, MONITOR RX | GOC-14E01 PM-CODE: | 1 | 5 | Coled stacked |  | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL PRT PRC SETC MANC NMAT | GO /C /08/NDB-TX-WITH-ANTENNA | NDB TRANSMITTER WITH ANTENNA | NOSD | 2021-06-16
| MTN-TELE | 2021-11-08 | 7:00 | 2021-08-05 | WPM | D | I | 2021-11-09 | 9:24 | Non Critical | 2400128761 | 0010 | 2Y KALIBRERING AF GASSONIC 1701 (GOC) | KALIBRERING AF GASSONIC 1701 | 1 | 5 |  | Refurbish | 6 | 6 | 0 | APPR WMAT RDBL | APPR OPND | REL PRC SETC MANC | GO /C /84 | WORKSHOP/WAREHOUSE | NOSD | 2021-05-24
| MTN-TELE | 2021-11-11 | 7:00 | 2021-11-16 | WPM | C | V | 2021-11-11 | 16:36 | Business Critical | 2400151162 | 0010 | 1M G.P. ELLIOT F+G RTU PRESSURIZED | GOE-01Z02 PM-CODE: | 1 | 5 |  |  | 4 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /03/FIRE-GAS-CONTROL-PANELS | FIRE & GAS CONTROL PANELS | NOSD | 2021-11-11
| MTN-TELE | 2021-11-16 | 7:00 | 2021-11-21 | WPM | C | V | 2021-11-17 | 9:24 | Business Critical | 2400151236 | 0020 | 2W H2S ANALYSER, GC-AT-05844A/B | 1W H2S EXPORTGAS H2S | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /31/GC-AT-05844A | H2S MONITORING, GAS EXP. GC-E-203A ST. A | NOSD | 2021-11-16
| MTN-TELE | 2021-11-14 | 7:00 | 2021-11-18 | WPM | A | V | 2021-11-14 | 14:12 | Assurance | 2400151279 | 0010 | 1M GOC-1M. G.P. ELLIOT F+G RTU | GOC-01Z01 PM-CODE: | 1 | 3 |  |  | 3 | 3 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /03/FIRE-GAS-CONTROL-PANELS | FIRE & GAS CONTROL PANELS | NOSD | 2021-11-14
| MTN-TELE | 2021-11-13 | 7:00 | 2021-11-23 | WPM | A | V | 2021-11-13 | 14:12 | Assurance | 2400157165 | 0010 | 3M UHF PORTABLE FIRE RADIOES | 30.08.2012 | 1 | 3 |  |  | 3 | 3 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /A /08/EXTERNAL-COMMUNICATION | EXTERNAL COMMUNICATION | NOSD | 2021-11-13
| MTN-TELE | 2021-11-14 | 7:00 | 2021-11-24 | WPM | A | V | 2021-11-15 | 11:48 | Assurance | 2400157219 | 0010 | 3M H2S DETECTOR GORM C | H2S GASDETEKTOR VEDLIGEHOLD | 1 | 3 |  |  | 7 | 7 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /03/TOXIC-GAS-DETECTORS | TOXIC GAS DETECTORS | NOSD | 2021-11-14
| MTN-TELE | 2021-11-17 | 7:00 | 2021-11-28 | WPM | C | V | 2021-11-18 | 14:12 | Business Critical | 2400157237 | 0010 | 3M FIRE DAMPER GOC A100 MODUL 9 | TL-3M, FIRE DAMPER GOC A100 MODUL 9 | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-11-17
| MTN-TELE | 2021-11-08 | 7:00 | 2021-11-23 | WPM | C |  | 2021-11-08 | 19:00 | Business Critical | 2400157250 | 0010 | 1Y GOE-YA. ABB SCADA RTU ABB SCADA RTU | GOE-20A01 PM-CODE: | 1 | 5 |  |  | 5 | 5 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC MANC NMAT | GO /E /04/CONTROL-PANELS | CONTROL PANELS | NOSD | 2021-10-18
| MTN-TELE | 2021-11-17 | 7:00 | 2021-11-28 | WPM | C | V | 2021-11-18 | 14:12 | Business Critical | 2400157268 | 0010 | 3M FIRE DAMPER GOC A-1588 MODUL 15 | TL-3M, FIRE DAMPER GOC A-1588 MODUL 15 | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-11-17
| MTN-TELE | 2021-11-11 | 7:00 | 2021-12-11 | WPM | A | V | 2021-11-12 | 9:24 | Assurance | 2400157497 | 0010 | 1Y CRANE RADIOES RADIOES | MEKANISK INSPEKTION | 1 | 3 |  |  | 6 | 6 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /08/EXTERNAL-COMMUNICATION | EXTERNAL COMMUNICATION | NOSD | 2021-11-11
| MTN-TELE | 2021-12-01 | 7:00 | 2021-12-06 | WPM | C | V | 2021-12-02 | 9:24 | Business Critical | 2400157528 | 0020 | 2W H2S ANALYSER, GC-AT-05844A/B | 1W H2S EXPORTGAS H2S | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /31/GC-AT-05844A | H2S MONITORING, GAS EXP. GC-E-203A ST. A | NOSD | 2021-12-01
| MTN-TELE | 2021-11-08 | 7:00 | 2021-12-06 | WPM | A | V | 2021-11-09 | 14:12 | Assurance | 2400157552 | 0010 | 1Y GOF-YA. ABB ESD RTU PRESSURIZED | GOF-02B02 PM-CODE: | 1 | 3 |  |  | 8 | 8 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC NMAT | GO /F /03/FIRE-GAS-CONTROL-PANELS | FIRE & GAS CONTROL PANELS | NOSD | 2021-11-06
| MTN-TELE | 2021-11-25 | 7:00 | 2021-12-14 | WPM | C | S | 2021-11-26 | 14:12 | Business Critical | 2400160453 | 0010 | 6M LIFEBOAT RADIO, VHF EMERGENCY BEACON | TL-LIFE-BOAT RADIOES, VHF EMERGENCY BEAC | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /08/VHF-RADIO-SYSTEM-WITH-ANTENNA | VHF RADIO SYSTEM WITH ANTENNA | NOSD | 2021-11-25
| MTN-TELE | 2021-11-27 | 7:00 | 2021-12-13 | WPM | A | V | 2021-11-28 | 9:24 | Assurance | 2400160456 | 0010 | 6M LIFEBOAT RADIO, VHF EMERGENCY BEACON | TL-LIFE-BOAT RADIOES, VHF EMERGENCY BEAC | 1 | 3 |  |  | 6 | 6 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /08/EXTERNAL-COMMUNICATION | EXTERNAL COMMUNICATION | NOSD | 2021-11-27
| MTN-TELE | 2021-12-10 | 7:00 | 2021-12-21 | WPM | C | V | 2021-12-11 | 9:24 | Business Critical | 2400160518 | 0020 | 1.5M H2S ANALYSER GC-AT-05844A | 6 MDR PPM PÅ GC-AT-05844A | 1 | 5 |  |  | 6 | 6 | 0 | APPR AWSD RDBL | APPR OPND | REL PRC SETC NMAT | GO /C /31/GC-AT-05844A | H2S MONITORING, GAS EXP. GC-E-203A ST. A | NOSD | 2021-12-10
| MTN-TELE | 2021-12-14 | 7:00 | 2021-12-18 | WPM | A | V | 2021-12-14 | 14:12 | Assurance | 2400160555 | 0010 | 1M GOC-1M. G.P. ELLIOT F+G RTU | GOC-01Z01 PM-CODE: | 1 | 3 |  |  | 3 | 3 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /03/FIRE-GAS-CONTROL-PANELS | FIRE & GAS CONTROL PANELS | NOSD | 2021-12-14
| MTN-TELE | 2021-11-16 | 7:00 | 2021-12-16 | WPM | A | V | 2021-11-17 | 19:00 | Assurance | 2400160560 | 0010 | 1Y G.P. ELLIOT F+G RTU PRESSURIZED | GOE-01Z02 PM-CODE: | 1 | 3 |  |  | 10 | 10 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /E /03/FIRE-GAS-CONTROL-PANELS | FIRE & GAS CONTROL PANELS | NOSD | 2021-11-16
| MTN-TELE | 2021-12-09 | 7:00 | 2021-12-20 | WPM | C | V | 2021-12-10 | 14:12 | Business Critical | 2400160568 | 0010 | 3M FIRE DAMPER A-310A/B NOEDGEN | TL-3M, FIRE DAMPER A-310A/B NOEDGEN | 1 | 5 |  |  | 8 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC NMAT | GO /C /09/FIRE-DAMPERS | FIRE DAMPERS |  | 2021-12-09
| MTN-TURB | 2021-11-08 | 7:00 | 2021-08-17 | WPM | A | V | 2021-11-13 | 19:00 | Assurance | 2400129678 | 0010 | 1Y GC-G-803 SOLAR GEN | TL-9M GC-G-803, SOLAR GEN | 1 | 3 |  | Hold Step | 18 | 18 | 0 | APPR SECE WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRC SETC MANC | GO /C /60/GC-A-803 | MAIN GENERATOR UNIT |  | 2021-07-18